## _REFERENCE888777888 (hidden)
WorkSheet Name | Report Code | Company Id | Job Id | Start Date | End Date | Payroll Subledger | Pay Period Id

## LEVEL 3
Project Details
Project | Robindale & 215 | [7 empty] | Total Cost | 68910227.7334 |  | Unit Breakdown |  |  |  | Parking
Budget Level | Level 3 | [10 empty] | Unit Type | Number | % |  | Cover Parking |  | 286 | [8 empty] | Railing Estimate |  |  | Building 3 | 147 | Stucco |  |  | Building 3 | 61455
Product | Senior | [7 empty] | Cost Per Unit | 189835.3381 |  | Studios | 0 | 0% |  | Cover Accesible Parking | [10 empty] | Building 1 |  |  |  | 98 | Building 1
Start Date | [11 empty] | 1 Br - 1 Ba | 218 | 60.06% |  | Open Parking |  | 112 | [8 empty] | Northwest | 190 |  |  | 176 | Northwest | 19256
Timeline | 24 | [7 empty] | Cost Per SF | 190.06 |  | 2 Br - 1 Ba | 145 | 39.94% |  | Accessible Parking |  | 14 | [8 empty] | Southwest | 146 |  |  | 70 | Southwest | 8980
Floors | 2 | [10 empty] | 2 Br - 2 Ba | 0 | 0% |  | Waiver |  | 0 | [8 empty] | Northeast | 118 |  |  | 491 | Northeast | 8850
Bldg. SF | 362571 | [7 empty] | Efficiency | 78.18% |  | 3 Br - 2 Ba | 0 | 0% |  | Total Parking Provided |  | 412 | [8 empty] | Southeast | 306 |  |  |  | Southeast | 19965
Acres | 17.35 | [10 empty] | Totals | 363 | 100% |  | Parking Ratio |  | 1.135 | [8 empty] | More | 132 | 892 |  |  | More | 24325 | 81376
Site SF | 755766
Buildings | 3 | [25 empty] | Building 2 & 5 |  |  | Building 4 | 112 | Building 2 & 5 |  |  | Building 4 | 29517
[27 empty] | Northwest |  |  |  | 160 | Northwest
Description | Cost Code | Cost Category | Sub job | Source | UMO | Quantity | U.P. | Escal % | Total U.P. | Sub Total | Total | Description / Details
General Requirement | 01 | S |  |  | Mo | 24 | 139138.8787 | 0% | 139138.8787 | 3339333.0883
General Requirements | 01 | [9 empty] | 3339333.0883
Potholing | 02-3213 | S | ON-SITE | Allowance |  | 1 | 16000 | 0% | 16000 | 16000
Existing Conditions | 02 | [9 empty] | 16000
Slabs | 03-3101 | S | BUILDING | Proposal | LS | 1 | 2185768 | 0% | 2185768 | 2185768 |  | Proposal (Alpha) - High Bid |  | NRC Concrete ($1,542,922) - Low Bid
Deepened Footings | 03-3101 | S | BUILDING | N/A |  |  |  |  | 0 | 0 | [14 empty] | Grading & Paving | 1833769
Concrete Slab Repairs | 03-3101 | RR | BUILDING | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500 | [14 empty] | Wets | 1812662
Pump House Concrete | 03-3101 | S | PUMPHOUSE | Allowance | LS | 1 | 8500 |  | 8500 | 8500 | [14 empty] | Slabs | 1542922
Trash Enclosure Concrete | 03-3102 | S | OTHER SITE | Proposal | EA | 14 | 2958 | 0% | 2958 | 41412 |  | Proposal (Alpha) | [12 empty] | Wood Framing | 6634921
Pool Area Shower Concrete | 03-3105 | S | POOL AREA | Allowance | LS | 1 | 23959 | 0% | 23959 | 23959 | [14 empty] | Plumbing | 3325080
Cabana Concrete | 03-3107 | S | POOL AREA | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500 | [14 empty] | Electrical | 4641350
Pool Equipment Foundation | 03-3108 | S | POOL EQUIP | Allowance | LS | 1 | 4290 | 0% | 4290 | 4290 |  | Proposal (Alpha) | [12 empty] | Mechanical
Lightweight Concrete | 03-3116 | S | BUILDING | Proposal | LS | 1 | 274310 | 0% | 274310 | 274310 |  | Propsal (Nevada Gyp) - Low Bid |  | Sound-Crete ($289,353) - High Bid | [10 empty] | Finished Carpentry
Deck Concrete | 03-5001 | S | BUILDING | Proposal | LS | 1 | 32600 | 0% | 32600 | 32600 |  | Propsal (Nevada Gyp) - Low Bid |  | Sound-Crete ($41,260) - High Bid | [10 empty] | Drywall & Paint | 3860853
Concrete | 03 | [9 empty] | 2584839 | [13 empty] | Masonry | 737195
Elevator Shaft | 04-2201 | S | BUILDING | N/A | Stop | 0 | 11500 | 0% | 11500 | 0 |  | Wood framed. | [12 empty] | Structural Steel | 121085
Trash Enclosure | 04-2202 | S | OTHER SITE | Budget | Count | 14 | 7000 | 0% | 7000 | 98000 |  | See Off and Onsite Budget |  | AWAITING UPDATED PROPOSALS | [10 empty] | Site Iron | 608507
Masonry Veneer | 04-4301 | S | ON-SITE | N/A |  |  | 0 |  | 0 | 0 | [14 empty] | Elevators
Masonry Veneer Pool Area | 04-4305 | S | POOL AREA | Allowance | LS | 3 | 5000 | 0% | 5000 | 15000 |  |  |  | AWAITING UPDATED PROPOSALS | [10 empty] | Sprinkler Systems
Pool Eq. Shower | 04-4306 | A | POOL EQUIP | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000 |  |  |  | AWAITING UPDATED PROPOSALS | [10 empty] | Fire Alarm
Masonry | 04 | [9 empty] | 128000 | [13 empty] | Insulation | 572070
Structural Steel | 05-1201 | S | BUILDING | Proposal | LS | 1 | 109485 | 0% | 109485 | 109485 |  | Proposal (Imperial Iron) | [12 empty] | Stucco | 897250
Elevator Shaft Iron | 05-1202 | S | BUILDING | Proposal | LS | 1 | 9600 | 0% | 9600 | 9600 |  | Proposal (Imperial Iron) | [12 empty] | Roofing | 1492534
Stair Handrails | 05-5201 | S | BUILDING | West Henderson | Flight | 19 | 3000 | 0% | 3000 | 57000 |  | West Henderson proposal - Desert Steel | [12 empty] | Dry Utilities
Garage Stair Railings | 05-5201 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0 | [14 empty] | Lightweight Concrete | 306910
Cabana Iron | 05-7004 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0 | [14 empty] | Decks
Pool Equipment Gate | 05-7005 | S | POOL EQUIP | Budget | Count | 2 | 1950 | 0% | 1950 | 3900 |  | See Off and Onsite Budget |  | AWAITING UPDATED PROPOSALS | [10 empty] | Const. Clean
Iron Railings | 05-7300 | S | BUILDING | West Henderson | LF | 2595 | 92.5 | 0% | 92.5 | 240037.5 |  | West Henderson proposal - Desert Steel | [12 empty] | Security Systems
Cable Railings | 05-7316 | S | COMMON AREA | N/A |  |  | 0 | 0% | 0 | 0 | [14 empty] | Windows & Sliders
Metals | 05 | [9 empty] | 420022.5 | [13 empty] | Pools & Spa
Framing | 06-1100 | S | BUILDING | Proposal | LS | 1 | 6634921 | 0% | 6634921 | 6634921 |  | Proposal (National Builders) - Low Bid |  |  | Rafael Construction ($9,293,005) - High Bidder | [9 empty] | Carports & Iron
Framing Pump House | 06-1100 | S | PUMPHOUSE | Bruner | SF | 600 | 18.68 | 0% | 18.68 | 11208 | [14 empty] | Site Concrete | 547947
Framing - Crane | 06-1100 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [14 empty] | Cabinets - Units
Cabana Framing | 06-1109 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [14 empty] | Cabinets - Common Areas
BBQ Framing | 06-1110 | S | COMMON AREA | Allowance | LS | 4 | 2500 | 0% | 2500 | 10000 | [14 empty] | Countertops - Units
Fireplace Framing | 06-1111 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [14 empty] | Countertops - Common Areas
Trellis | 06-1114 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [14 empty] | Unit Tub/Shower Surrounds
Pool Equipment Framing | 06-1114 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0 | [14 empty] | Flooring - Units
Finish Carpentry - Units | 06-2001 | S | BUILDING | West Henderson | Liavable SF | 269691 | 3.55 | 10% | 3.905 | 1053143.355 |  | Per WH proposal based on liavable SF. | [12 empty] | Flooring - Common Areas
Finish Carpentry - Common | 06-2001 | S | COMMON AREA | Bruner | SF | 362571 | 1.08 | 10% | 1.188 | 430736.136 |  | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies. | [12 empty] | Site Landscaping
Finish Carpentry - Pump House | 06-2001S | S | PUMPHOUSE | Allowance | LS | 1 | 4000 | 0% | 4000 | 4000 | [14 empty] | Blinds
BBQ Trim | 06-2006 | S | COMMON AREA | Allowance | LS | 4 | 1250 | 0% | 1250 | 5000 | [14 empty] | Unit Appliances
Shutters | 06-4919 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [14 empty] | Interior Furniture
Wood, Plastics, & Composites | 06 | [9 empty] | 8149008.491 | [13 empty] | Exterior Furniture
Insulation | 07-2101 | S | BUILDING | Proposal | LS | 1 | 571320 | 0% | 571320 | 571320 |  | Proposal (Battle Born) - Low Bid |  | TruTeam ($852,000) - Middle Bid |  |  | Gold Star ($858,434) - High Bid | [7 empty] | Solar Panels
Insulation - PH | 07-2101 | S | PUMPHOUSE | Proposal | LS | 1 | 750 | 0% | 750 | 750 |  | Proposal (Battle Born) | [12 empty] | DAS System
Roofing | 07-3001 | S | BUILDING | Proposal | LS | 1 | 1088690 | 0% | 1088690 | 1088690 |  | Proposal (TORC) |  | Xbuilt ($1,492,543) - High Bid | [10 empty] | Street Signs
Roofing - PH | 07-3001 | S | PUMPHOUSE | Proposal | LS | 1 | 8295 | 0% | 8295 | 8295 |  | Proposal (TORC) |  | Xbuilt ($4,478) | [10 empty] | Temp Power
Cabana Roofing | 07-3002 | S | COMMON AREA | Proposal | LS | 1 | 15685 | 0% | 15685 | 15685 |  | Proposal (Xbuilt) |  | TORC (Not Included) | [10 empty] | Surveying/Testing
Pump House Roofing | 07-3002 | S | PUMPHOUSE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500 | [14 empty] | Gym Equipment
Pool Equipment Roofing | 07-3003 | S | POOL EQUIP | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500 | [14 empty] | Gym Flooring
Trash Enclosure Cover | 07-6101 | S | OTHER SITE | Proposal | LS | 1 | 250000 | 0% | 250000 | 250000 |  | Proposal (Hirschi) | [12 empty] | Electrical Fixtures
Pigeon Proofing | 07-7001 | S | BUILDING | Allowance | SF | 362571 | 0.08 | 0% | 0.08 | 29005.68 | [14 empty] | Pavers and Pool Deck
Gutters and Downspouts | 07-7124 | S | BUILDING | Allowance | SF | 362571 | 0.05 | 0% | 0.05 | 18128.55 | [14 empty] | Signage
Roof Ladders | 07-7210 | S | BUILDING | Allowance | Count | 6 | 1550 | 0% | 1550 | 9300 |  | 2 Per building | [12 empty] | Site Security
Roof Access Doors | 07-7233 | S | BUILDING | Allowance | Count | 6 | 2500 | 0% | 2500 | 15000 |  | 2 Per building | [12 empty] | Masonry Veneer
Roof Winch | 07-7250 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [15 empty] | 28935055
Thermal & Moisture Protection | 07 | [9 empty] | 2021174.23
Entry Doors | 08-1001 | S | COMMON AREA | Allowance | Count | 3 | 8000 | 0% | 8000 | 24000
Common Doors | 08-1002 | S | COMMON AREA | Included |  |  |  | 0% | 0 | 0
Pocket Doors - 3 Panel | 08-1002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Garage Doors | 08-3619 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Windows and Sliding Glass Doors | 08-5301 | S | BUILDING | West Henderson | Per Unit | 363 | 1449.9974 | 0% | 1449.9974 | 526349.0692 |  | Contempo unit windows Proposal plus $100 per unit for frontage windows.
Windows Repair and Replacement | 08-5301 | RR | BUILDING | Allowance | Per Unit | 363 | 75 | 0% | 75 | 27225
Pool Equipment Windows | 08-5303 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Pool Glass Walls | 08-8001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Fixed Glass | 08-8002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED Install | 08-8302 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Framed | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Polished Edges (Units) | 08-8301 | S | BUILDING | Bruner | Bathroom | 363 | 175 | 0% | 175 | 63525 |  | Updated based on Bruner budget
Mirrors - Polished Edges (Restrooms) | 08-8301 | S | BUILDING | Allowance | Count | 6 | 300 | 0% | 300 | 1800
Openings | 08 | [9 empty] | 642899.0692
Cost Prep Labor | 09-0101 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cost Prep Mat - Home Depot | 09-0102 | S | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Clean Up - Final | 09-0103 | S | BUILDING | Bruner | SF | 362571 | 0.85 | 0% | 0.85 | 308185.35 |  | Includes Dumpters
Clean Up - During Construction - Labor | 09-0104 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000
Dumpsters | 09-0113 | S | DUMPSTERS | Allowance | Unit | 363 | 79 | 0% | 79 | 28677
Clean Up - Hauling Exterior | 09-0121 | S | ON-SITE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Included in Construction Cleaning Contract.
Stucco | 09-2423 | S | BUILDING | Proposal | LS | 1 | 897250 | 0% | 897250 | 897250 |  | Proposal (Desert Plastering) - Low Bid |  |  | Builder's First Source ($993,890) - High Bid
Stucco - Pump House | 09-2423S | A | PUMPHOUSE | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Stucco - Walls | 09-2424 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Area | 09-2428 | A | POOL AREA | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Stucco - Cabana | 09-2429 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Equipment | 09-2430 | S | POOL EQUIP | Pebble | LS | 1 | 5000 | 0% | 5000 | 5000
Stucco - Repairs | 09-2423A | RR | BUILDING | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Drywall | 09-2905 | S | BUILDING | Proposal | LS | 1 | 2629350 | 0% | 2629350 | 2629350 |  | Proposal (Classic Drywall & Paint)
Drywall - Repairs | 09-2905A | RR | BUILDING | Allowance | Unit | 363 | 85 | 0% | 85 | 30855
Drywall - Pump House | 09-2905S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Tile Tubs and Showers | 09-3001 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Common Tile | 09-3002 | S | COMMON AREA | Torrey Pines | Unit | 363 | 468.71 | 0% | 468.71 | 170141.73 |  | Based on Torrey Pines awarded proposal
Kitchen Backsplash | 09-3003 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Tile | 09-3008 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Flooring - Units | 09-6001 | S | BUILDING | Bruner | SY | 31493.6667 | 16.2966 | 0% | 16.2966 | 513238.1887 |  | Sheet Vinyl - Seamless
Common Wood | 09-6401 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common Vinyl | 09-6517 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Hall Flooring | 09-6520 | S | COMMON AREA | Torrey Pines | SF | 362571 | 0.75 | 0% | 0.75 | 271928.25 |  | Torrey Pines approved proposal
Hall Flooring - Elevators | 09-6520A | A | COMMON AREA | Allowance | Count | 6 | 750 | 0% | 750 | 4500
Common - Plank | 09-6521 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common - VCT | 09-6522 | S | COMMON AREA | N/A | SF | 0 | 0 | 0% | 0 | 0
Common - Rubber Floor (Ecore) | 09-6566 | S | COMMON AREA | Bruner | SF | 1901.9 | 19.54 | 0% | 19.54 | 37163.126 |  | Bruner proposal
Common - Carpet Stairs | 09-6802 | S | COMMON AREA | Pebble | Count | 19 | 1848.1429 | 0% | 1848.1429 | 35114.7143 |  | Pebble contracted Price (RMI) plus an additional $300)
Hall Runner Install | 09-6803 | S | COMMON AREA | Pebble | SF | 362571 | 0 | 0% | 0 | 0 |  | Based on Torrey Pines, assumption is that we are not doing hall runners (if so, $0.05 per SF)
Hall Runner Materials | 09-6804 | S | COMMON AREA | Pebble | SF | 362571 | 0 | 0% | 0 | 0 |  | Based on Torrey Pines, assumption is that we are not doing hall runners (if so, $0.30 per SF)
Painting - Repairs | 09-9101A | RR | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Painting | 09-9101 | S | BUILDING | Proposal | LS | 1 | 695819 | 0% | 695819 | 695819 |  | Proposal (Classic Drywall & Paint)
Painting - Pump House | 09-9101S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Painting - Walls | 09-9102 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Painting - Pool Area | 09-9106 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Wall Covering |  | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Walls - Specialty | 09-9110 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Finishes | 09 | [9 empty] | 5743722.359
Entry Directory | 10-1300 | S | ON-SITE | N/A |  |  | 5478 | 0% | 5478 | 0
Unit Carport Signs | 10-1401 | S | CARPORT | Pebble | Unit | 363 | 212 | 0% | 212 | 76956 |  | Per Pebble budget
Site Signage | 10-1404 | S | ON-SITE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Entry Sign Letters | 10-1419 | S | ON-SITE | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Offsite Street Signs | 10-1454 | S | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Bath Accessories | 10-2816 | S | BUILDING | Pebble | Per Bathroom | 363 | 41 | 0% | 41 | 14883 |  | Per Pebble Budget
Shower Doors | 10-2919 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places | 10-3000 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places - Pool Area | 10-3200 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
BBQ Units | 10-3355 | S | POOL AREA | Arzano | LS | 4 | 3360 | 0% | 3360 | 13440
Lock Boxes | 10-4116 | S | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fire Extinguishers | 10-4416 | S | BUILDING | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 |  | Is this not included in the sprinkler contract? Yes but seperate cost code.
Mail Boxes | 10-5523 | S | BUILDING | Pebble | Unit | 363 | 230 | 0% | 230 | 83490 |  | Per Pebble Budget
Closet Shelving | 10-5723 | S | BUILDING | Bruner | Unit | 363 | 332 | 0% | 332 | 120516
Window Awnings Small | 10-7313 | S | BUILDING | Torrey Pines | Count | 30 | 2500 | 0% | 2500 | 75000
Window Awnings Large | 10-7313 | S | BUILDING | Torrey Pines | Count | 10 | 8500 | 0% | 8500 | 85000
Specialties | 10 | [9 empty] | 525785
Appliances | 11-3013 | S | BUILDING | Bruner | Unit | 363 | 3169.7043 | 5% | 3328.1895 | 1208132.8053
Appliances - Laundry Room | 11-3013 | S | BUILDING | Torrey Pines | Units | 363 | 343.7053 | 0% | 343.7053 | 124765.0105 |  | Based on Torret Pines ($65k) Laundry room appliance cost per unit.
Appliances - Common | 11-3013 | S | BUILDING | Allowance | LS | 1 | 35000 | 0% | 35000 | 35000 |  | Kithcen and laundry rooms
Equipment | 11 | [9 empty] | 1367897.8159
Dumpsters | 12-0131 | S | DUMPSTERS | N/A | 0 | 0 | 0 | 0% | 0 | 0 |  | Included in Construction Cleaning Contract | [9 empty] | W.H Units | Box Count | Robin. Units | # of Units | Total Counts
Blinds | 12-2100 | S | BUILDING | Torrey Pines | Per Unit | 363 | 443 | 0% | 443 | 160809 |  | Incudes New Requirement for Cordless Blinds. | [9 empty] | A1A | 16 | 1A | 168 | 2688
Cabinets Units | 12-3531 | S | BUILDING | West Henderson | Boxes | 6830 | 137.8 | 0% | 137.8 | 941174 |  | Based on Thermafoil White, W.H. units (A1A, B1B, B3A, and B2C) to approximate counts. Add $150,260 if upgrading to Morning Dew ($159.80 / SF) | [6 empty] | Counts to the side |  |  | B1B | 14 | 1B | 52 | 728
Cabinet Common Areas | 12-3535 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000 | [11 empty] | B3A | 24 | 2A | 125 | 3000
Counter Tops Units | 12-3601 | S | BUILDING | Bruner | Unit | 363 | 1868.4433 | 0% | 1868.4433 | 678244.9175 |  | Based on Arctic White SF cost from Bruner and Takeoffs. Add $79,844 if upgrading to Carrera Trigato ($28.40 / SF) | [6 empty] | Counts to the side |  |  | B2C | 23 | 2B | 18 | 414
Counter Tops Common Areas | 12-3605 | A | BUILDING | Allowance | LS | 1 | 65000 | 0% | 65000 | 65000 | [15 empty] | 6830
Counter Tops Pool Area | 12-3608 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Top | 12-3609 | S | POOL AREA | Allowance | LS | 4 | 6000 | 0% | 6000 | 24000
Furnishings | 12 | [9 empty] | 1944227.9175 | [10 empty] | Units | Countertop SF | # of Units | Total Counts
Pools and Spas | 13-1113 | S | POOL AREA | West Henderson | LS | 1 | 290932.3333 | 0% | 290932.3333 | 290932.3333 |  | WH plus $37k for a 2nd spa. | [9 empty] | 1A | 55.2 | 168 | 9273.6
Carports | 13-3401 | S | CARPORT | Torrey Pines | Count | 286 | 2292 | 0% | 2292 | 655512 |  | Proposal | [9 empty] | 1B | 77.08 | 52 | 4008.16
Pool Equipment Cover | 13-3402 | S | POOL EQUIP | Decatur | Count | 1 | 7049 | 0% | 7049 | 7049 | [11 empty] | 2A | 64.88 | 125 | 8110
Special Construction | 13 | [9 empty] | 953493.3333 | [10 empty] | 2B | 64.6 | 18 | 1162.8
Trash Chute | 13-G | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Trash Chute | 13-G | [9 empty] | 0 | [13 empty] | 22554.56
Elevator | 14-2400 | S | BUILDING | Proposal | LS | 1 | 693215 | 0% | 693215 | 693215 |  | Proposal (Otis) | [7 empty] | 40316.4167
Pool and Spa Lifts | 14-4101 | S | POOL AREA | Allowance | Count | 2 | 6500 | 0% | 6500 | 13000 | [9 empty] | 80632.8333
Conveying Equipment | 14 | [9 empty] | 706215
Sprinkler Design & Permit | 21-0600 | S | BUILDING | Proposal | LS | 1 | 51000 | 0% | 51000 | 51000
Sprinkler System | 21-1313 | S | BUILDING | Proposal | LS | 1 | 1081100 | 0% | 1081100 | 1081100 |  | Proposal (Nevada Fire Protection)
Fire Pump | 21-3000 | S | PUMPHOUSE | Bruner | Count | 1 | 125000 | 0% | 125000 | 125000 |  | Focus Bruner proposal (2nd lowest) | [7 empty] | 0.081633
Fire Suppression | 21 | [9 empty] | 1257100
1 Bathroom Unit | 22-1001 | S | BUILDING | Proposal | Count | 363 | 10350 | 0% | 10350 | 3757050 |  | Proposal (Focus) - Middle bid |  | JMAC ($3,325,080) - Low Bid |  |  | Modern ($4,123,227) - High Bid
2 Bathroom Unit | 22-1001 | S | BUILDING | N/A | 0 | 0 | 0 | 0% | 0 | 0
Plumbing - Pump House | 22-1001S | S | PUMPHOUSE | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pool Area | 22-1003 | S | POOL AREA | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Pool Equipment | 22-1007 | S | POOL EQUIP | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Plumbing | 22 | [9 empty] | 3790550
HVAC Standard | 23-3001 | S | BUILDING | Bruner | Unit | 363 | 9845.3608 | 0% | 9845.3608 | 3573865.9794 |  | Allstate signed off proposal
HVAC - Pump House | 23-3001S | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
HVAC | 23 | [9 empty] | 3588865.9794
Electrical | 26-1001 | S | BUILDING | Proposal | LS | 1 | 4199740 | 0% | 4199740 | 4199740 |  | Proposal (Northstar)
Electrical - Pump House | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Electrical Fixtures | 26-5001 | S | BUILDING | Allowance | Unit | 363 | 700 | 0% | 700 | 254100
Building Electrical Fixtures | 26-5002 | S | BUILDING | West Henderson | Unit | 363 | 120 | 0% | 120 | 43560 |  | Per Unit allowance from West Henderson
Hall Lighting Fixtures | 26-5003 | S | BUILDING | West Henderson | Unit | 363 | 115 | 0% | 115 | 41745 |  | Per unit allowance from West Henderson
Carports Electrical | 26-1001 | S | CARPORT | West Henderson | Space | 286 | 200 | 0% | 200 | 57200 |  | Per unit allowance from West Henderson
Carport Fixtures | 26-5001 | S | CARPORT | Allowance | Space | 286 | 50 | 0% | 50 | 14300
Cabana Electrical | 26-1001 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Cabana Fixtures | 26-5004 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Street Lights | 26-5613 | S | Offsite | Budget | Count | 4 | 15000 | 0% | 15000 | 60000 |  | See Budget
Site Lighting Electrical | 26-1005 | S | ON-SITE | Proposal | LS | 1 | 260330 | 0% | 260330 | 260330 |  | Proposal (Northstar)
Site Lighting Fixtures | 26-5602 | S | ON-SITE | Allowance | Acre | 17.35 | 1750 | 0% | 1750 | 30362.5
Pool Lighting Electrical | 26-1004 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Lighting Fixtures | 26-5603 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Equipment Electrical | 26-1007 | S | POOL EQUIP | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pump House Electrical | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Pump House Fixtures | 26-5001 | S | PUMPHOUSE | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Electrical | 26 | [9 empty] | 5025337.5
TV and Media | 27-2201 | A | BUILDING | Allowance | LS | 3 | 1000 | 0% | 1000 | 3000 |  | Per Building
DAS System | 27-3010 | S | BUILDING | Torrey Pines | SF | 362571 | 0.45 | 0% | 0.45 | 163156.95
Pool ADA Phone | 27-3201 | S | POOL AREA | Allowance | LS | 1 | 800 | 0% | 800 | 800 |  | Per Pool
Communications | 27 | [9 empty] | 166956.95
Security System | 28-1001 | S | BUILDING | Bruner | Unit | 363 | 551.2887 | 0% | 551.2887 | 200117.7835
Site Security System | 28-2001 | S | ON-SITE | Pebble | Mo | 24 | 5642.8571 | 0% | 5642.8571 | 135428.5714 |  | Pebble monthly cost to date.
Fire Alarm / Two Way Comm AOR | 28-4601 | S | BUILDING | Proposal | LS | 1 | 472900 | 0% | 472900 | 472900 |  | Proposal (Nevada Fire Protection)
Fire Alarm - Pump House | 28-4601S | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Electronic Safety & Security | 28 | [9 empty] | 818446.3549
Construction Water | 31-0121 | S | ON-SITE | Allowance | Acre | 17.35 | 6500 | 0% | 6500 | 112775
Dust Control | 31-0122 | S | ON-SITE | Allowance | Acre | 17.35 | 3500 | 0% | 3500 | 60725
Track Out Pad / DEMO | 31-0505 | S | ON-SITE | Budget | LS | 1 | 100000 | 0% | 100000 | 100000
Rock Dirt Haul Off | 31-1492 | S | ON-SITE | Budget | LS | 1 | 50000 | 0% | 50000 | 50000
Mass Grading | 31-2201 | S | ON-SITE | Budget | LS | 1 | 835870 | 0% | 835870 | 835870 |  | Proposal (Civil Werx)
Fine Grade | 31-2216 | S | ON-SITE | Budget | LS | 1 | 997899 | 0% | 997899 | 997899 |  | Proposal (Civil Werx)
Hard Dig | 31-2319 | S | ON-SITE | Budget | LS | 1 | 100000 | 0% | 100000 | 100000
Dewatering | 31-2322 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Storm Water Prevention | 31-2501 | S | ON-SITE | Allowance | Acre | 17.35 | 2500 | 0% | 2500 | 43375
Earthwork | 31 | [9 empty] | 2300644
Bond Repair | 32-0100 | RR | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Street Cleaning | 32-0111 | S | OTHER SITE | Allowance | LS | 2 | 2500 | 0% | 2500 | 5000
Asphalt Sawcut and Removal | 32-0506 | S | ON-SITE | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000 |  | See Budget File
Paving | 32-1216 | S | ON-SITE | Proposal | LS | 1 | 1017448 | 0% | 1017448 | 1017448 |  | Proposal (America United Construction)
Seal Coat | 32-1236 | S | ON-SITE | Allowance | SF | 215053 | 0.25 | 0% | 0.25 | 53763.25
Pavers | 32-1401 | S | OTHER SITE | Pebble | SF | 3000 | 8.5 | 0% | 8.5 | 25500 |  | Allowance
Pool Decks | 32-1402 | S | POOL AREA | Pebble | SF | 8023 | 8.5 | 0% | 8.5 | 68195.5 |  | Pool Deck
Curbs and Gutters | 32-1613 | S | ON-SITE | Proposal | LS | 1 | 111739.5 | 0% | 111739.5 | 111739.5 |  | Proposal (Alpha)
Tack On Curb | 32-1614 | S | ON-SITE | Proposal | LS | 1 | 91538.5 | 0% | 91538.5 | 91538.5 |  | Proposal (Alpha)
Concrete Flatwork | 32-1623 | S | ON-SITE | Proposal | LS | 1 | 272612.25 | 0% | 272612.25 | 272612.25 |  | Proposal (Alpha)
Bus Pad | 32-1625 | S | OTHER SITE | N/A |  |  |  | 0% | 0 | 0
Pool Hardscape | 32-1626 | S | POOL AREA | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Street Signs / Striping | 32-1700 | S | ON-SITE | Allowance | Acre | 17.35 | 3000 | 0% | 3000 | 52050
Walls Iron | 32-3101 | S | ON-SITE | Proposal | LS | 1 | 188811.6 | 0% | 188811.6 | 188811.6 |  | Proposal (Hirschi)
Trash Enclosure Iron Gates | 32-3103 | S | OTHER SITE | Proposal | LS | 1 | 516903 | 0% | 516903 | 516903 |  | Proposal (Hirschi)
Site Railings | 32-3104 | A | OTHER SITE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Dog Run Fence | 32-3105 | S | ON-SITE | Proposal | LS | 1 | 50256.35 | 0% | 50256.35 | 50256.35 |  | Proposal (Hirschi)
Pool Fence | 32-3106 | S | POOL AREA | Proposal | LS | 1 | 31577 | 0% | 31577 | 31577 |  | Proposal (Hirschi)
Pool Fence Gates | 32-3106 | S | POOL AREA | Proposal | LS | 1 | 28505 | 0% | 28505 | 28505 |  | Proposal (Hirschi)
Entry Security Gates | 32-3111 | S | ON-SITE | Proposal | LS | 1 | 12867.5 | 0% | 12867.5 | 12867.5 |  | Crash Gate
Entry Security Gates Electrical | 32-3112 | S | ON-SITE | N/A |  |  | 3555 | 0% | 3555 | 0
Entry Gate Transmitters | 32-3113 | S | ON-SITE | N/A |  |  | 44 | 0% | 44 | 0
Entry Gates | 32-3114 | S | ON-SITE | Budget | LS | 0 | 1950 | 0% | 1950 | 0
Temp Fencing | 32-3120 | S | ON-SITE | Allowance | LS | 17.35 | 5000 | 0% | 5000 | 86750
Walls Masonry | 32-3201 | S | ON-SITE | Budget | LS | 1 | 301295.73 | 0% | 301295.73 | 301295.73 |  | See Budget |  | AWAITING UPDATED PROPOSALS
Walls Pilaster Caps | 32-3202 | S | ON-SITE | West Henderson | LS | 1 | 31250 | 0% | 31250 | 31250 |  | Preliminary Civil Plans |  | AWAITING UPDATED PROPOSALS
Retaining Walls | 32-3204 | S | ON-SITE | West Henderson | LS | 1 | 539517.35 | 0% | 539517.35 | 539517.35 |  | See Budget |  | AWAITING UPDATED PROPOSALS
Pool Walls | 32-3208 | A | POOL AREA | Allowance | LS | 2 | 7500 | 0% | 7500 | 15000
Site Furniture Permanent | 32-3343 | A | BUILDING | Allowance | LS | 1 | 7000 | 0% | 7000 | 7000
Site Landscaping | 32-9001 | S | ON-SITE | West Henderson | SF | 316370.92 | 9 | 0% | 9 | 2847338.28 |  | West Henderson proposal with 304k lanscaping sf is under $8.50 /sf
Site Landscaping Lighting | 32-9001 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Site Landscaping Planter Pots | 32-9433 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Offsite Asphalt Sawcut and Removal | 32-0506 | S | Offsite | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Offsite Paving | 32-1216 | S | Offsite | Proposal | LS | 1 | 385892 | 0% | 385892 | 385892 |  | Proposal (America United Construction)
Offsite Curbs and Gutters | 32-1613 | S | Offsite | Proposal | LS | 1 | 27195 | 0% | 27195 | 27195 |  | Proposal (Alpha)
Offsite Concrete Flatwork | 32-1623 | S | Offsite | Budget | LS | 1 |  | 0% | 0 | 0
Offsite Parvin Realignment | 32-5500 | S | Offsite | Budget | LS | 1 | 0 | 0% | 0 | 0
Exterior Improvements | 32 | [9 empty] | 6828005.81
Temp Power | 33-0501 | A |  | Allowance | Unit | 363 | 375 | 0% | 375 | 136125
Traffic Control, AC Removal and Patch | 33-1001 | A | Offsite | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Water | 33-1001 | S | ON-SITE | Budget | LS | 1 | 969787 | 0% | 969787 | 969787 |  | Proposal (ACME)
Sewer | 33-3001 | S | ON-SITE | Budget | LS | 1 | 285724 | 0% | 285724 | 285724 |  | Proposal (ACME)
Storm Drain | 33-4001 | S | ON-SITE | Allowance | LS | 1 | 19814 | 0% | 19814 | 19814 |  | Proposal (ACME)
Sub Drains | 33-4116 | A |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Gas | 33-5001 | S | Offsite | Budget | LS | 1 | 0 | 15% | 0 | 0
Electric | 33-7101 | S |  | Budget | LS | 1 | 411575 | 0% | 411575 | 411575 |  | See Budget
Secondary Conduit | 33-7102 | A |  | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Bollards | 33-7103 | S |  | Allowance | LS | 1 | 15600 | 0% | 15600 | 15600
Cable TV | 33-8201 | S |  | N/A |  |  |  | 0% | 0 | 0
Phone | 33-8202 | S |  | N/A |  |  |  | 0% | 0 | 0
Off Site Water | 33-1001 | S | Offsite | Budget | LS | 1 | 402748 | 0% | 402748 | 402748 |  | Proposal (ACME)
Off Site Sewer | 33-3001 | S | Offsite | Proposal | LS | 1 | 51375 | 0% | 51375 | 51375 |  | Proposal (ACME)
Off Site Storm Drain | 33-4001 | S | Offsite | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Off Site Electric | 33-7101 | S | Offsite | Budget | LS | 1 | 61000 | 0% | 61000 | 61000
Utilities | 33 | [9 empty] | 2418748
Bridge |  |  | ON-SITE | Allowance | LS | 2 | 594250 | 0% | 594250 | 1188500 |  | UNchanged
Other |  |  | ON-SITE | Allowance | LS | 1 | 300000 | 0% | 300000 | 300000 |  | Current prelim plan calls for 47,604 Sf 6" concrete with 18" on center rebard. Estimated cost $600k but chosed with $300k allowance since this may change.
Brigde Over Duct Creek Wash | 33 | [9 empty] | 1488500
Traffic Control | 34-4116 | A | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Transportation | 34 | [9 empty] | 7500
Solar PV System | 48-1413 | S |  | Allowance | LS | 1 | 977434 | 0% | 977434 | 977434 |  | Unchanged
Solar PV Conduit | 48-1414 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Unchanged
Car Charging Stations | 48-1913 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Unchanged
Electrical Power Generation | 48 | [9 empty] | 1077434
Staking | 49-0601 | S |  | Pebble | LS | 17.35 | 9000 | 0% | 9000 | 156150 |  | Using Pebble Cost to Date as Benchmark.
Re Staking | 49-0602 | S |  | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Using Pebble Cost to Date as Benchmark.
Certs and Verifications | 49-0603 | S |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000 |  | Using Pebble Cost to Date as Benchmark.
Slab Testing | 49-0801 | S |  | Allowance | EAH | 3 | 15000 | 0% | 15000 | 45000 |  | Using Pebble Cost to Date as Benchmark.
Grading Testing | 49-0802 | S |  | Pebble | LS | 17.35 | 5000 | 0% | 5000 | 86750 |  | Using Pebble Cost to Date as Benchmark.
Other Testing | 49-0803 | S |  | Pebble | LS | 17.35 | 5000 | 0% | 5000 | 86750 |  | Using Pebble Cost to Date as Benchmark.
Masonry Testing | 49-0807 | S |  | Allowance | LS | 17.35 | 2500 | 0% | 2500 | 43375 |  | Using Pebble Cost to Date as Benchmark.
Pavement Testing | 49-0808 | S |  | Allowance | LS | 17.35 | 1500 | 0% | 1500 | 26025 |  | Using Pebble Cost to Date as Benchmark.
Third Party Inspections | 49-0950 | S |  | Pebble | LS | 17.35 | 2500 | 0% | 2500 | 43375 |  | Using Pebble Cost to Date as Benchmark.
Field Surveys, Staking | 49 | [9 empty] | 502425
BABA | [5 empty] | 0% |  |  |  | 0
Bid Risk | [5 empty] | 2% |  |  |  | 1113111.0294
Bid Risk & BABA | Bid Risk | [9 empty] | 1113111.0294
Golf Carts | 11-1001 | S |  | Allowance | LS | 2 | 10000 | 0% | 10000 | 20000
Convenience Store Equipment | 11-2101 | S |  | N/A |  |  |  | 0% | 0 | 0
Pet Wash | 11-2102 | S |  | N/A | LS | 0 | 21000 | 0% | 21000 | 0
Office Equipment | 11-2801 | S |  | Allowance | LS | 1 | 20000 | 0% | 20000 | 20000
Gym Exercise Equipment | 11-6613 | S |  | Decatur | SF | 1901.9 | 47.98 | 0% | 47.98 | 91253.162
Playground / Basketball Hoop | 11-6813 | S |  | N/A |  |  |  | 0% | 0 | 0 | [10 empty] | 3720000
Maintenance Shop Equipment | 11-8101 | S |  | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Maintenance Shop Start Up Supplies | 11-8102 | S |  | Alowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fixed Asset Misc. | 11-8105 | S |  | N/A |  |  |  | 0% | 0 | 0
Interior Furniture | 12-5000 | S |  | Allowance | LS | 1 | 700000 | 0% | 700000 | 700000 |  | Per Armen Email with an old proposal on Robindale interior and exteior furniture
Exterior Furniture | 12-5483 | S |  | Allowance | LS | 3 | 100000 | 0% | 100000 | 300000 |  | Per Armen Email with an old proposal on Robindale interior and exteior furniture
Rec Building TV Media Computer | 27-2201 | S |  | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Rec Building Telephone System | 27-3202 | S |  | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Maintenance Radios | 27-3243 | S |  | Allowance | LS | 2 | 1500 | 0% | 1500 | 3000
FFE | FFE Extra | [9 empty] | 1181753.162
Construction Contingency | 55-9800 |  |  |  |  | 5% |  |  |  | 2782777.5736
Construction Contingency | 55 | [9 empty] | 2782777.5736
Sub Bonds | 50-9950 | B |  |  |  | 1.7% |  |  |  | 946144.375
Sub Bonds | 50 | [9 empty] | 946144.375
GL Insurance | 50-0001 |  |  |  | 3.03 per $1,000 | 5 |  |  |  | 310777.7574
Misc. | 50-0001 |  |  |  | 5% of GL Ins. | 5% |  |  |  | 15538.8879
Umbrella | 50-0001 |  |  |  | 95% of GL Ins. | 0.95 |  |  |  | 295238.8695
GL Insurance | 50 | [9 empty] | 621555.5147
Overhead | 56 |  |  |  |  | 2% |  |  |  | 1112938.67
Contractor Fee | 56 |  |  |  |  | 6% |  |  |  | 3338816.01
OH & Contractor Fee | 56 | [9 empty] | 4451754.68
Total Hard Costs | [10 empty] | 68910227.7334
0
General Requirements | 01 |  |  | 3339333.0883 | [8 empty] | 6% General Conditions
Existing Conditions | 02 |  |  | 16000 | [8 empty] | 55655551.4723
Concrete | 03 |  |  | 2584839 | [8 empty] | 3339333.0883 | 2782777.5736
Parking Garage | 03-G |  |  | #N/A | [8 empty] | 139138.8787
Masonry | 04 |  |  | 128000
Metals | 05 |  |  | 420022.5
Wood, Plastics, & Composites | 06 |  |  | 8149008.491
Thermal & Moisture Protection | 07 |  |  | 2021174.23
Openings | 08 |  |  | 642899.0692
Finishes | 09 |  |  | 5743722.359
Specialties | 10 |  |  | 525785
Equipment | 11 |  |  | 1367897.8159
Furnishings | 12 |  |  | 1944227.9175
Special Construction | 13 |  |  | 953493.3333
Trash Chute | 13-G |  |  | 0
Conveying Equipment | 14 |  |  | 706215
Fire Suppression | 21 |  |  | 1257100
Plumbing | 22 |  |  | 3790550
HVAC | 23 |  |  | 3588865.9794
Electrical | 26 |  |  | 5025337.5
Communications | 27 |  |  | 166956.95
Electronic Safety & Security | 28 |  |  | 818446.3549
Earthwork | 31 |  |  | 2300644
Exterior Improvements | 32 |  |  | 6828005.81
Utilities | 33 |  |  | 2418748
Transportation | 34 |  |  | 7500
Electrical Power Generation | 48 |  |  | 1077434
Field Surveys, Staking | 49 |  |  | 502425
5th Story Factor |  |  |  | #N/A
Bid Risk |  |  |  | 0
FFE |  |  |  | 1181753.162
Construction Contingency | 55 |  |  | 0
Sub Bonds | 50 |  |  | 0
GL Insurance | 50 |  |  | 621555.5147
Contractor Fee | 56 |  |  | 0
Total Hard Costs |  |  |  | 68910227.7334
#N/A
Cost Code
Total
01 - General Requirements | 01 |  |  |  | 3339333.0883
02 - Existing Conditions | 02 |  |  |  | 16000
03 - Concrete | 03 |  |  |  | 2584839
04 - Masonry | 04 |  |  |  | 128000
05 - Metals | 05 |  |  |  | 420022.5
06 - Wood, Plastics, & Composites | 06 |  |  |  | 8149008.491
07 - Thermal & Moisture Protection | 07 |  |  |  | 2021174.23
08 - Openings | 08 |  |  |  | 642899.0692
09 - Finishes | 09 |  |  |  | 5743722.359
10 - Specialties | 10 |  |  |  | 525785
11 - Equipment | 11 |  |  |  | 1367897.8159
12 - Furnishings | 12 |  |  |  | 1944227.9175
13 - Special Construction | 13 |  |  |  | 953493.3333
14 - Conveying Equipment | 14 |  |  |  | 706215
21 - Fire Suppression | 21 |  |  |  | 1257100
22 - Plumbing | 22 |  |  |  | 3790550
23 - HVAC | 23 |  |  |  | 3588865.9794
26 - Electrical | 26 |  |  |  | 5025337.5
27 - Communications | 27 |  |  |  | 166956.95
28 - Electronic Safety & Security | 28 |  |  |  | 818446.3549
31 - Earthwork | 31 |  |  |  | 2300644
32 - Exterior Improvements | 32 |  |  |  | 6828005.81
33 - Utilities | 33 |  |  |  | 3907248
34 - Transportation | 34 |  |  |  | 7500
48 - Electrical Power Generation | 48 |  |  |  | 1077434
49 - Field Surveys, Staking | 49 |  |  |  | 502425
Bid Risk | Bid Risk |  |  |  | 1113111.0294
FFE Extra | FFE Extra |  |  |  | 1181753.162
50 - Sub Bonds | 50 |  |  |  | 1567699.8898
55 - Construction Contingency | 55 |  |  |  | 2782777.5736
56 - Contractor Fee | 56 |  |  |  | 4451754.68
Total |  |  |  |  | 68910227.7334
check |  |  |  |  | 0
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units | 09-6001 |  |  |  | 513238.1887 | 09
Common Wood | 09-6401 |  |  |  | 0 | 09
Common Vinyl | 09-6517 |  |  |  | 0 | 09
Hall Flooring | 09-6520 |  |  |  | 271928.25 | 09
Hall Flooring - Elevators | 09-6520A |  |  |  | 4500 | 09
Common - Plank | 09-6521 |  |  |  | 0 | 09
Common - VCT | 09-6522 |  |  |  | 0 | 09
Common - Rubber Floor | 09-6566 |  |  |  | 37163.126 | 09
Common - Carpet | 09-6802 |  |  |  | 35114.7143 | 09
Appliances | 11-3013 |  |  |  | 1367897.8159 | 11
Blinds | 12-2100 |  |  |  | 160809 | 12
Total Appliances, Flooring & Blinds |  |  |  |  | 2390651.0948
Site Work
Major Categories
Existing Conditions | 2 |  |  |  | 16000
Earthwork | 31 |  |  |  | 2300644
Exterior Improvements | 32 |  |  |  | 6828005.81
Utilities | 33 |  |  |  | 3907248
Transportation | 34 |  |  |  | 7500
Electrical Power Generation | 48 |  |  |  | 1077434
Minor Categories
Carports | 13-3401 |  |  |  | 655512
Dumpsters | 06-0111 |  |  |  | 0
Gazebo |  |  |  |  | 0
Other Site |  |  |  |  | 0
Pools and Spas | 13-1113 |  |  |  | 290932.3333
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Pump House Concrete | 03-3101 |  |  |  | 2201768
Total Site Work |  |  |  |  | 17285044.1433
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  | already included in 32
Offsite Paving | 32-1216OFFSITE |  |  | already included in 32
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  | already included in 32
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  | already included in 32
Storm Drain | 33-4001OFFSITE |  |  | already included in 33
Off Site Water | 33-1001OFFSITE |  |  | already included in 33
Off Site Sewer | 33-3001OFFSITE |  |  | already included in 33
Off Site Electric | 33-7101OFFSITE |  |  | already included in 33
Traffic Control | 34-4116OFFSITE |  |  | already included in 34
Pump House Concrete | 03-3101
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  |  | 0
Offsite Paving | 32-1216OFFSITE |  |  |  | 0
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  |  | 0
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  |  | 0
Off Site Water | 33-1001OFFSITE |  |  |  | 0
Off Site Sewer | 33-3001OFFSITE |  |  |  | 0
Storm Drain | 33-4001OFFSITE |  |  |  | 0
Off Site Electric | 33-7101OFFSITE |  |  |  | 0
Traffic Control | 34-4116OFFSITE |  |  |  | 0
Other Ineligible Costs
Major Categories
Parking Garage | 03-G |  |  |  | 0
Minor Categories
Pump House Concrete | 03-3101 |  |  |  | 2201768
Pool Area Shower Concrete | 03-3105 |  |  |  | 23959
Cabana Concrete | 03-3107 |  |  |  | 6500
Pool Equipment Foundation | 03-3108 |  |  |  | 4290
Deck Concrete | 03-5001 |  |  |  | 32600
Masonry Veneer Pool Area | 04-4305 |  |  |  | 15000
Pool Equipment Shower Stone | 04-4306 |  |  |  | 15000
Cabana Iron | 05-7004 |  |  |  | 0
Pool Equipment Gate | 05-7005 |  |  |  | 3900
Cabana Framing | 06-1109 |  |  |  | 0
BBQ Framing | 06-1110 |  |  |  | 10000
Fireplace Framing | 06-1111 |  |  |  | 0
Trellis | 06-1114 |  |  |  | 0
BBQ Trim | 06-2006 |  |  |  | 5000
Cabana Roofing | 07-3002 |  |  |  | 23185
Pump House Roofing | 07-3002 |  |  |  | 23185
Pool Equipment Windows | 08-5303 |  |  |  | 0
Pool Glass Walls | 08-8001 |  |  |  | 0
Stucco - Pump House | 09-2423 |  |  |  | 897250
Stucco - Cabana | 09-2423 |  |  |  | 897250
Stucco - Pool Wall | 09-2423 |  |  |  | 897250
Unit Carport Signs | 10-1401 |  |  |  | 76956
Fire Places - Pool Area | 10-3200 |  |  |  | 0
BBQ Units | 10-3355 |  |  |  | 13440
BBQ Top | 12-3609 |  |  |  | 24000
Pools and Spas | 13-1113 |  |  |  | 290932.3333
Carports | 13-3401 |  |  |  | 655512
Pool Equipment Cover | 13-3402 |  |  |  | 7049
Pool and Spa Lifts | 14-4101 |  |  |  | 13000
Pool Area | 22-1003 |  |  |  | 25000
Pool Equipment | 22-1007 |  |  |  | 6000
Carports Electrical | 26-1001 |  |  |  | 4286940
Carport Fixtures | 26-5001 |  |  |  | 269900
Cabana Electrical | 26-1001 |  |  |  | 4286940
Cabana Fixtures | 26-5004 |  |  |  | 5000
Pool Lighting Electrical | 26-1004 |  |  |  | 12500
Pool Lighting Fixtures | 26-5603 |  |  |  | 12500
Pool Equipment Electrical | 26-1007 |  |  |  | 2500
Pump House Electrical | 26-1001 |  |  |  | 4286940
Pump House Fixtures | 26-5001 |  |  |  | 269900
Pool Decks | 32-1402 |  |  |  | 68195.5
Pool Hardscape | 32-1626 |  |  |  | 10000
Pool Fence | 32-3106 |  |  |  | 60082
Pool Walls | 32-3208 |  |  |  | 15000
Pet Wash | 11-2102 |  |  |  | 0
Office Equipment | 11-2801 |  |  |  | 20000
Gym Exercise Equipment | 11-6613 |  |  |  | 91253.162
Playground / Basketball Hoop | 11-6813 |  |  |  | 0
Rec Building TV Media Computer | 27-2201 |  |  |  | 28000
Rec Building Telephone System | 27-3202 |  |  |  | 2500

## Comparison - Level 3
| Level 2.1 |  | Level 3 |  | Variance
Units |  | 363 |  | 363 |  | 0
Building Gross Square Feet |  | 362571 |  | 362571 |  | 0
Total Cost |  | 68033845.6858 |  | 68938904.7334 |  | -905059.0477 |  |  |  |  | Studios | 0 | 0% | Southeast | 306 |  |  |  | Southeast | 19965
Cost Per Unit |  | 187421.0625 |  | 189914.3381 |  | -2493.2756 |  |  |  |  | 1 Br - 1 Ba | 218 | 60.06% | More | 132 | 438 |  |  | More | 24325 | 44290
Cost Per SF |  | 187.6428 |  | 190.139 |  | -2.4962 |  |  |  |  | 2 Br - 1 Ba | 145 | 39.94%
[11 empty] | 2 Br - 2 Ba | 0 | 0% | Building 2 & 5 |  |  | Building 4 | 112 | Building 2 & 5 |  |  | Building 4 | 29517
Description | Sub Total | Total | Sub Total | Total | Variance | % Change | Description / Details |  |  |  | Totals | 363 | 100%
General Requirement | 3292398.3063 |  | 3339333.0883 |  | -46934.7821 | -1.426%
General Requirements |  | 3292398.3063 |  | 3339333.0883 | -46934.7821 | -1.426%
Potholing | 16000 |  | 16000 |  | 0 | 0%
Existing Conditions |  | 16000 |  | 16000 | 0 | 0%
Slabs | 2125443.32 |  | 2185768 |  | -60324.68 | -2.838% | Updated per Bids
Concrete Slab Repairs | 7500 |  | 7500 |  | 0 | 0% |  |  |  |  | Project Details
Pump House Concrete | 8500 |  | 8500 |  | 0 | 0% |  |  |  |  | Project | Robindale &215
Trash Enclosure Concrete | 70000 |  | 41412 |  | 28588 | 40.84% | Updated per Bids |  |  |  | Budget Level | Level 1
Pool Area Shower Concrete | 23959 |  | 23959 |  | 0 | 0% |  |  |  |  | Product | Senior
Cabana Concrete | 6500 |  | 6500 |  | 0 | 0%
Pool Equipment Foundation | 6500 |  | 4290 |  | 2210 | 34% | Updated per Bids |  |  |  | Timeline | 30
Lightweight Concrete | 481539.8 |  | 274310 |  | 207229.8 | 43.03% | Updated per Bids |  |  |  | Floors | 2
Deck Concrete | 45894.0515 |  | 32600 |  | 13294.0515 | 28.97% | Updated per Bids |  |  |  | Bldg. SF | 362571
Concrete |  | 2775836.1715 |  | 2584839 | 190997.1715 | 6.881% |  |  |  |  | Acres | 17.35
Elevator Shaft | 0 |  | 0 |  | 0 | n/a |  |  |  |  | Site SF | 755766
Trash Enclosure | 98000 |  | 98000 |  | 0 | 0% |  |  |  |  | Buildings | 3
Masonry Veneer Pool Area | 15000 |  | 15000 |  | 0 | 0%
Pool Eq. Shower | 15000 |  | 15000 |  | 0 | 0%
Masonry |  | 128000 |  | 128000 | 0 | 0%
Structural Steel | 150000 |  | 109485 |  | 40515 | 27.01% | Updated per Bids
Elevator Shaft Iron | 25500 |  | 9600 |  | 15900 | 62.35% | Updated per Bids
Stair Handrails | 57000 |  | 57000 |  | 0 | 0%
Pool Equipment Gate | 1950 |  | 3900 |  | -1950 | -100% | Updated per Bids - Only 1 pool equipment gate
Iron Railings | 240037.5 |  | 240037.5 |  | 0 | 0%
Cable Railings | 0 |  | 0 |  | 0 | n/a
Metals |  | 474487.5 |  | 420022.5 | 54465 | 11.48%
Framing | 6772826.28 |  | 6634921 |  | 137905.28 | 2.036% | Updated per Bids
Framing Pump House | 11208 |  | 11208 |  | 0 | 0%
Framing - Crane | 0 |  | 0 |  | 0 | n/a
Cabana Framing | 0 |  | 0 |  | 0 | n/a
BBQ Framing | 10000 |  | 10000 |  | 0 | 0%
Fireplace Framing | 0 |  | 0 |  | 0 | n/a
Trellis | 0 |  | 0 |  | 0 | n/a
Pool Equipment Framing | 0 |  | 0 |  | 0 | n/a
Finish Carpentry - Units | 1053143.355 |  | 1053143.355 |  | 0 | 0%
Finish Carpentry - Common | 430736.136 |  | 430736.136 |  | 0 | 0% |  |  |  | 920930.34
Finish Carpentry - Pump House | 4000 |  | 4000 |  | 0 | 0% |  |  |  | 571320
BBQ Trim | 5000 |  | 5000 |  | 0 | 0% |  |  |  | -349610.34
Shutters | 0 |  | 0 |  | 0 | n/a
Wood, Plastics, & Composites |  | 8286913.771 |  | 8149008.491 | 137905.28 | 1.664% |  |  |  | 2.33
Insulation | 906427.5 |  | 571320 |  | 335107.5 | 36.97% | Updated per Bids |  |  | 2.59
Insulation - PH | 2000 |  | 750 |  | 1250 | 62.5% | Updated per Bids |  |  | 2.7
Roofing | 1277484.28 |  | 1088690 |  | 188794.28 | 14.78% | Updated per Bids
Roofing - PH | 10000 |  | 8295 |  | 1705 | 17.05% | Updated per Bids
Cabana Roofing | 0 |  | 15685 |  | -15685 | n/a | Updated per Bids
Pump House Roofing | 7500 |  | 7500 |  | 0 | 0%
Pool Equipment Roofing | 7500 |  | 7500 |  | 0 | 0%
Trash Enclosure Cover | 84000 |  | 250000 |  | -166000 | -197.6% | Updated per Bids
Pigeon Proofing | 29005.68 |  | 29005.68 |  | 0 | 0%
Gutters and Downspouts | 18128.55 |  | 18128.55 |  | 0 | 0%
Roof Ladders | 9300 |  | 9300 |  | 0 | 0%
Roof Access Doors | 15000 |  | 15000 |  | 0 | 0%
Roof Winch | 0 |  | 0 |  | 0 | n/a
Thermal & Moisture Protection |  | 2366346.01 |  | 2021174.23 | 345171.78 | 14.59%
Entry Doors | 24000 |  | 24000 |  | 0 | 0%
Common Doors | 0 |  | 0 |  | 0 | n/a
Pocket Doors - 3 Panel | 0 |  | 0 |  | 0 | n/a
Garage Doors | 0 |  | 0 |  | 0 | n/a
Windows and Sliding Glass Doors | 526350 |  | 526349.0692 |  | 0.93077 | 0.0001768%
Windows Repair and Replacement | 27225 |  | 27225 |  | 0 | 0%
Pool Equipment Windows | 0 |  | 0 |  | 0 | n/a
Pool Glass Walls | 0 |  | 0 |  | 0 | n/a
Fixed Glass | 0 |  | 0 |  | 0 | n/a
Mirrors - LED | 0 |  | 0 |  | 0 | n/a
Mirrors - LED Install | 0 |  | 0 |  | 0 | n/a
Mirrors - Framed | 0 |  | 0 |  | 0 | n/a
Mirrors - Polished Edges (Units) | 63525 |  | 63525 |  | 0 | 0%
Mirrors - Polished Edges (Restrooms) | 1800 |  | 1800 |  | 0 | 0%
Openings |  | 642900 |  | 642899.0692 | 0.93077 | 0.0001448%
Cost Prep Labor | 0 |  | 0 |  | 0 | n/a
Cost Prep Mat - Home Depot | 10000 |  | 10000 |  | 0 | 0%
Clean Up - Final | 308185.35 |  | 308185.35 |  | 0 | 0%
Clean Up - During Construction - Labor | 75000 |  | 75000 |  | 0 | 0%
Dumpsters | 28677 |  | 28677 |  | 0 | 0%
Clean Up - Hauling Exterior | 10000 |  | 10000 |  | 0 | 0%
Stucco | 950639.2965 |  | 897250 |  | 53389.2965 | 5.616% | Updated per Bids
Stucco - Pump House | 6000 |  | 6000 |  | 0 | 0%
Stucco - Walls | 0 |  | 0 |  | 0 | n/a
Stucco - Pool Area | 2000 |  | 2000 |  | 0 | 0%
Stucco - Cabana | 0 |  | 0 |  | 0 | n/a
Stucco - Pool Equipment | 5000 |  | 5000 |  | 0 | 0% |  |  |  | 2875188.03
Stucco - Repairs | 1500 |  | 1500 |  | 0 | 0% |  |  |  | 2629350
Drywall | 2773668.15 |  | 2629350 |  | 144318.15 | 5.203% | Updated per Bids |  |  | -245838.03
Drywall - Repairs | 30855 |  | 30855 |  | 0 | 0%
Drywall - Pump House | 1000 |  | 1000 |  | 0 | 0%
Tile Tubs and Showers | 0 |  | 0 |  | 0 | n/a
Common Tile | 170141.73 |  | 170141.73 |  | 0 | 0%
Kitchen Backsplash | 0 |  | 0 |  | 0 | n/a
Cabana Tile | 0 |  | 0 |  | 0 | n/a
Flooring - Units | 513238.1887 |  | 513238.1887 |  | 0 | 0%
Common Wood | 0 |  | 0 |  | 0 | 0%
Common Vinyl | 0 |  | 0 |  | 0 | 0%
Hall Flooring | 271928.25 |  | 271928.25 |  | 0 | 0%
Hall Flooring - Elevators | 4500 |  | 4500 |  | 0 | 0%
Common - Plank | 0 |  | 0 |  | 0 | 0%
Common - VCT | 0 |  | 0 |  | 0 | 0%
Common - Rubber Floor (Ecore) | 37163.126 |  | 37163.126 |  | 0 | 0%
Common - Carpet Stairs | 35114.7143 |  | 35114.7143 |  | 0 | 0%
Hall Runner Install | 0 |  | 0 |  | 0 | n/a
Hall Runner Materials | 0 |  | 0 |  | 0 | n/a
Painting - Repairs | 10000 |  | 10000 |  | 0 | 0%
Painting | 717890.58 |  | 695819 |  | 22071.58 | 3.075% | Updated per Bids
Painting - Pump House | 1000 |  | 1000 |  | 0 | 0%
Painting - Walls | 0 |  | 0 |  | 0 | n/a
Painting - Pool Area | 0 |  | 0 |  | 0 | n/a
Wall Covering | 0 |  | 0 |  | 0 | n/a
Walls - Specialty | 0 |  | 0 |  | 0 | n/a
Finishes |  | 5963501.3854 |  | 5743722.359 | 219779.0265 | 3.685%
Entry Directory | 0 |  | 0 |  | 0 | n/a
Unit Carport Signs | 76956 |  | 76956 |  | 0 | 0%
Site Signage | 7500 |  | 7500 |  | 0 | 0%
Entry Sign Letters | 6500 |  | 6500 |  | 0 | 0%
Offsite Street Signs | 7500 |  | 7500 |  | 0 | 0%
Bath Accessories | 14883 |  | 14883 |  | 0 | 0%
Shower Doors | 0 |  | 0 |  | 0 | n/a
Fire Places | 0 |  | 0 |  | 0 | n/a
Fire Places - Pool Area | 0 |  | 0 |  | 0 | n/a
BBQ Units | 13440 |  | 13440 |  | 0 | 0%
Lock Boxes | 5000 |  | 5000 |  | 0 | 0%
Fire Extinguishers | 30000 |  | 30000 |  | 0 | 0%
Mail Boxes | 83490 |  | 83490 |  | 0 | 0%
Closet Shelving | 120516 |  | 120516 |  | 0 | 0%
Window Awnings Small | 75000 |  | 75000 |  | 0 | 0%
Window Awnings Large | 85000 |  | 85000 |  | 0 | 0%
Specialties |  | 525785 |  | 525785 | 0 | 0%
Appliances | 1208132.8053 |  | 1208132.8053 |  | 0 | 0%
Appliances - Laundry Room | 124765.0105 |  | 124765.0105 |  | 0 | 0%
Appliances - Common | 35000 |  | 35000 |  | 0 | 0%
Equipment |  | 1367897.8159 |  | 1367897.8159 | 0 | 0%
Dumpsters | 28677 |  | 28677 |  | 0 | 0%
Blinds | 160809 |  | 160809 |  | 0 | 0%
Cabinets Units | 941174 |  | 941174 |  | 0 | 0%
Cabinet Common Areas | 75000 |  | 75000 |  | 0 | 0%
Counter Tops Units | 678244.9175 |  | 678244.9175 |  | 0 | 0%
Counter Tops Common Areas | 65000 |  | 65000 |  | 0 | 0%
Counter Tops Pool Area | 0 |  | 0 |  | 0 | n/a
BBQ Top | 24000 |  | 24000 |  | 0 | 0%
Furnishings |  | 1972904.9175 |  | 1972904.9175 | 0 | 0%
Pools and Spas | 290932.3333 |  | 290932.3333 |  | 0 | 0%
Carports | 655512 |  | 655512 |  | 0 | 0%
Pool Equipment Cover | 7049 |  | 7049 |  | 0 | 0%
Special Construction |  | 953493.3333 |  | 953493.3333 | 0 | 0%
Trash Chute | 0 |  | 0 |  | 0 | n/a
Trash Chute |  | 0 |  | 0 | 0 | 0
Elevator | 483797 |  | 693215 |  | -209418 | -43.29% | Updated per Bids
Pool and Spa Lifts | 13000 |  | 13000 |  | 0 | 0%
Conveying Equipment |  | 496797 |  | 706215 | -209418 | -42.15%
Sprinkler Design & Permit | 25000 |  | 51000 |  | -26000 | -104% | Updated per Bids
Sprinkler System | 960813.15 |  | 1081100 |  | -120286.85 | -12.52% | Updated per Bids
Fire Pump | 125000 |  | 125000 |  | 0 | 0%
Fire Suppression |  | 1110813.15 |  | 1257100 | -146286.85 | -13.17%
1 Bathroom Unit | 3655047 |  | 3757050 |  | -102003 | -2.791% | Updated per Bids
2 Bathroom Unit | 0 |  | 0 |  | 0 | n/a
Plumbing - Pump House | 2500 |  | 2500 |  | 0 | 0%
Pool Area | 25000 |  | 25000 |  | 0 | 0%
Pool Equipment | 6000 |  | 6000 |  | 0 | 0%
Plumbing |  | 3688547 |  | 3790550 | -102003 | -2.765%
HVAC Standard | 3573865.9794 |  | 3573865.9794 |  | 0 | 0%
HVAC - Pump House | 15000 |  | 15000 |  | 0 | 0%
HVAC |  | 3588865.9794 |  | 3588865.9794 | 0 | 0%
Electrical | 3846878.31 |  | 4199740 |  | -352861.69 | -9.173% | Updated per Bids
Electrical - Pump House | 10000 |  | 10000
Electrical Fixtures | 254100 |  | 254100 |  | 0 | 0%
Building Electrical Fixtures | 43560 |  | 43560 |  | 0 | 0%
Hall Lighting Fixtures | 41745 |  | 41745 |  | 0 | 0%
Carports Electrical | 57200 |  | 57200 |  | 0 | 0%
Carport Fixtures | 14300 |  | 14300 |  | 0 | 0%
Cabana Electrical | 5000 |  | 5000 |  | 0 | 0%
Cabana Fixtures | 5000 |  | 5000 |  | 0 | 0%
Street Lights | 60000 |  | 60000 |  | 0 | 0%
Site Lighting Electrical | 43375 |  | 260330 |  | -216955 | -500.2% | Updated per Bids
Site Lighting Fixtures | 30362.5 |  | 30362.5 |  | 0 | 0%
Pool Lighting Electrical | 12500 |  | 12500 |  | 0 | 0%
Pool Lighting Fixtures | 12500 |  | 12500 |  | 0 | 0%
Pool Equipment Electrical | 2500 |  | 2500 |  | 0 | 0%
Pump House Electrical | 15000 |  | 15000 |  | 0 | 0%
Pump House Fixtures | 1500 |  | 1500 |  | 0 | 0%
Electrical |  | 4455520.81 |  | 5025337.5 | -569816.69 | -12.79%
TV and Media | 3000 |  | 3000 |  | 0 | 0%
DAS System | 163156.95 |  | 163156.95 |  | 0 | 0%
Pool ADA Phone | 800 |  | 800 |  | 0 | 0%
Communications |  | 166956.95 |  | 166956.95 | 0 | 0%
Security System | 200117.7835 |  | 200117.7835 |  | 0 | 0%
Site Security System | 135428.5714 |  | 135428.5714 |  | 0 | 0%
Fire Alarm / Two Way Comm AOR | 701583.54 |  | 472900 |  | 228683.54 | 32.6% | Updated per Bids
Fire Alarm - Pump House | 10000 |  | 10000 |  | 0 | 0%
Electronic Safety & Security |  | 1047129.8949 |  | 818446.3549 | 228683.54 | 21.84%
Construction Water | 112775 |  | 112775 |  | 0 | 0%
Dust Control | 60725 |  | 60725 |  | 0 | 0%
Track Out Pad / DEMO | 100000 |  | 100000 |  | 0 | 0%
Rock Dirt Haul Off | 50000 |  | 50000 |  | 0 | 0%
Mass Grading | 1257581.3634 |  | 835870 |  | 421711.3634 | 33.53% | Updated per Bids
Fine Grade | 52966.135 |  | 997899 |  | -944932.865 | -1784% | Updated per Bids
Hard Dig | 100000 |  | 100000 |  | 0 | 0%
Dewatering | 0 |  | 0 |  | 0 | n/a
Storm Water Prevention | 43375 |  | 43375 |  | 0 | 0%
Earthwork |  | 1777422.4984 |  | 2300644 | -523221.5016 | -29.44%
Bond Repair | 5000 |  | 5000 |  | 0 | 0%
Street Cleaning | 5000 |  | 5000 |  | 0 | 0%
Asphalt Sawcut and Removal | 25000 |  | 25000 |  | 0 | 0%
Paving | 601630.93 |  | 1017448 |  | -415817.07 | -69.11% | Updated per Bids
Seal Coat | 53763.25 |  | 53763.25 |  | 0 | 0%
Pavers | 25500 |  | 25500 |  | 0 | 0%
Pool Decks | 68195.5 |  | 68195.5 |  | 0 | 0%
Curbs and Gutters | 114991.74 |  | 111739.5 |  | 3252.24 | 2.828% | Updated per Bids
Tack On Curb | 134729.4 |  | 91538.5 |  | 43190.9 | 32.06% | Updated per Bids
Concrete Flatwork | 338206.8875 |  | 272612.25 |  | 65594.6375 | 19.39% | Updated per Bids
Bus Pad | 0 |  | 0 |  | 0 | n/a
Pool Hardscape | 10000 |  | 10000 |  | 0 | 0%
Street Signs / Striping | 52050 |  | 52050 |  | 0 | 0%
Walls Iron | 164035.4 |  | 188811.6 |  | -24776.2 | -15.1% | Updated per Bids
Trash Enclosure Iron Gates | 34790 |  | 516903 |  | -482113 | -1386% | Updated per Bids
Site Railings | 15000 |  | 15000 |  | 0 | 0%
Dog Run Fence | 16500 |  | 50256.35 |  | -33756.35 | -204.6% | Updated per Bids
Pool Fence | 21000 |  | 31577 |  | -10577 | -50.37% | Updated per Bids
Pool Fence Gates | 3900 |  | 28505 |  | -24605 | -630.9% | Updated per Bids
Entry Security Gates | 6000 |  | 12867.5 |  | -6867.5 | -114.5% | Updated per Bids
Entry Security Gates Electrical | 0 |  | 0 |  | 0 | n/a
Entry Gate Transmitters | 0 |  | 0 |  | 0 | n/a
Entry Gates | 0 |  | 0 |  | 0 | n/a
Temp Fencing | 86750 |  | 86750 |  | 0 | 0%
Walls Masonry | 493481.675 |  | 301295.73 |  | 192185.945 | 38.94% | Updated per Bids
Walls Pilaster Caps | 31250 |  | 31250 |  | 0 | 0%
Retaining Walls | 303105.8 |  | 539517.35 |  | -236411.55 | -78% | Updated per Bids
Pool Walls | 15000 |  | 15000 |  | 0 | 0%
Site Furniture Permanent | 7000 |  | 7000 |  | 0 | 0%
Site Landscaping | 2847338.28 |  | 2847338.28 |  | 0 | 0%
Site Landscaping Lighting | 0 |  | 0 |  | 0 | n/a
Site Landscaping Planter Pots | 0 |  | 0 |  | 0 | n/a
Offsite Asphalt Sawcut and Removal | 5000 |  | 5000 |  | 0 | 0%
Offsite Paving | 341251.0625 |  | 385892 |  | -44640.9375 | -13.08% | Updated per Bids
Offsite Curbs and Gutters | 45316 |  | 27195 |  | 18121 | 39.99% | Updated per Bids
Offsite Concrete Flatwork | 25863 |  | 0 |  | 25863 | 100% | Updated per Bids
Offsite Parvin Realignment | 0 |  | 0 |  | 0 | n/a
Exterior Improvements |  | 5896648.925 |  | 6828005.81 | -931356.885 | -15.79%
Temp Power | 136125 |  | 136125 |  | 0 | 0% |  |  | 136125 | 0
Traffic Control, AC Removal and Patch | 10000 |  | 10000 |  | 0 | 0% |  |  | 10000 | 0
Water | 1292500.98 |  | 969787 |  | 322713.98 | 24.97% | Updated per Bids |  | 1306636 | -14135.02
Sewer | 516087 |  | 285724 |  | 230363 | 44.64% | Updated per Bids |  | 823398 | -307311
Storm Drain | 25000 |  | 19814 |  | 5186 | 20.74% | Updated per Bids |  | 50000 | -25000
Sub Drains | 5000 |  | 5000 |  | 0 | 0% |  |  | 5000 | 0
Gas | 0 |  | 0 |  | 0 | n/a |  |  | 0 | 0
Electric | 350575.2 |  | 411575 |  | -60999.8 | -17.4% | Updated per Bids |  | 452076 | -101500.8
Secondary Conduit | 25000 |  | 25000 |  | 0 | 0% |  |  | 0 | 25000
Bollards | 15600 |  | 15600 |  | 0 | 0% |  |  | 15600 | 0
Cable TV | 0 |  | 0 |  | 0 | n/a |  |  | 0 | 0
Phone | 0 |  | 0 |  | 0 | n/a |  |  | 0 | 0
Off Site Water | 387993.65 |  | 402748 |  | -14754.35 | -3.803% | Updated per Bids |  | 345550 | 42443.65
Off Site Sewer | 91720 |  | 51375 |  | 40345 | 43.99% | Updated per Bids |  | 75000 | 16720
Off Site Storm Drain | 25000 |  | 25000 |  | 0 | 0% |  |  | 25000 | 0
Off Site Electric | 61000 |  | 61000 |  | 0 | 0% |  |  | 61000 | 0
Utilities |  | 2941601.83 |  | 2418748 | 522853.83 | 17.77%
Bridge | 1188500 |  | 1188500 |  | 0 | 0%
Other | 300000 |  | 300000 |  | 0 | 0%
Brigde Over Duct Creek Wash |  | 1488500 |  | 1488500 | 0 | 0%
Traffic Control | 7500 |  | 7500 |  | 0 | 0%
Transportation |  | 7500 |  | 7500 | 0 | 0%
Solar PV System | 977434 |  | 977434 |  | 0 | 0%
Solar PV Conduit | 50000 |  | 50000 |  | 0 | 0%
Car Charging Stations | 50000 |  | 50000 |  | 0 | 0%
Electrical Power Generation |  | 1077434 |  | 1077434 | 0 | 0%
Staking | 156150 |  | 156150 |  | 0 | 0%
Re Staking | 10000 |  | 10000 |  | 0 | 0%
Certs and Verifications | 5000 |  | 5000 |  | 0 | 0%
Slab Testing | 45000 |  | 45000 |  | 0 | 0%
Grading Testing | 86750 |  | 86750 |  | 0 | 0%
Other Testing | 86750 |  | 86750 |  | 0 | 0%
Masonry Testing | 43375 |  | 43375 |  | 0 | 0%
Pavement Testing | 26025 |  | 26025 |  | 0 | 0%
Third Party Inspections | 43375 |  | 43375 |  | 0 | 0%
Field Surveys, Staking |  | 502425 |  | 502425 | 0 | 0%
BABA | 0 |  | 0 |  | 0 | n/a
Bid Risk | 1097466.1021 |  | 1113111.0294 |  | -15644.9274 | -1.426%
Bid Risk & BABA |  | 1097466.1021 |  | 1113111.0294 | -15644.9274 | -1.426%
Golf Carts | 20000 |  | 20000 |  | 0 | 0%
Convenience Store Equipment | 0 |  | 0 |  | 0 | n/a
Pet Wash | 0 |  | 0 |  | 0 | 0%
Office Equipment | 20000 |  | 20000 |  | 0 | 0%
Gym Exercise Equipment | 91253.162 |  | 91253.162 |  | 0 | 0%
Playground / Basketball Hoop | 0 |  | 0 |  | 0 | n/a |  |  |  | 3720000
Maintenance Shop Equipment | 15000 |  | 15000 |  | 0 | 0%
Maintenance Shop Start Up Supplies | 5000 |  | 5000 |  | 0 | 0%
Fixed Asset Misc. | 0 |  | 0 |  | 0 | n/a
Interior Furniture | 700000 |  | 700000 |  | 0 | 0%
Exterior Furniture | 300000 |  | 300000 |  | 0 | 0%
Rec Building TV Media Computer | 25000 |  | 25000 |  | 0 | 0%
Rec Building Telephone System | 2500 |  | 2500 |  | 0 | 0%
Maintenance Radios | 3000 |  | 3000 |  | 0 | 0%
FFE |  | 1181753.162 |  | 1181753.162 | 0 | 0%
Construction Contingency | 2743665.2552 |  | 2782777.5736 |  | -39112.3184 | -1.426%
Construction Contingency | 2743665.2552 | 2743665.2552 |  | 2782777.5736 | -39112.3184 | -1.426%
Sub Bonds | 932846.1868 |  | 946144.375 |  | -13298.1883 | -1.426%
Sub Bonds | 932846.1868 | 932846.1868 |  | 946144.375 | -13298.1883 | -1.426%
GL Insurance | 306866.5255 |  | 310777.7574 |  | -3911.2318 | -1.275%
Misc. | 15343.3263 |  | 15538.8879 |  | -195.5616 | -1.275%
Umbrella | 291523.1992 |  | 295238.8695 |  | -3715.6702 | -1.275%
GL Insurance |  | 613733.051 |  | 621555.5147 | -7822.4637 | -1.275%
Overhead | 1112938.67 |  | 1112938.67 |  | 0 | 0%
Contractor Fee | 3338816.01 |  | 3338816.01 |  | 0 | 0%
Contractor Fee |  | 4451754.68 |  | 4451754.68 | 0 | 0%
Total Hard Costs |  | 68033845.6858 |  | 68938904.7334 | -905059.0477 | -1.33%
|  | 3676511.442 |  | 0
General Requirements | [7 empty] | 6% General Conditions
Existing Conditions | [7 empty] | 55684228.4723
Concrete | [7 empty] | 3341053.7083
Parking Garage | [7 empty] | 111368.4569
Masonry
Metals
Wood, Plastics, & Composites
Thermal & Moisture Protection
Openings
Finishes
Specialties
Equipment
Furnishings
Special Construction
Trash Chute
Conveying Equipment
Fire Suppression
Plumbing
HVAC
Electrical
Communications
Electronic Safety & Security
Earthwork
Exterior Improvements
Utilities
Transportation
Electrical Power Generation
Field Surveys, Staking
5th Story Factor
Bid Risk
FFE
Construction Contingency
Sub Bonds
GL Insurance
Contractor Fee
Total Hard Costs
01 - General Requirements
02 - Existing Conditions
03 - Concrete
04 - Masonry
05 - Metals
06 - Wood, Plastics, & Composites
07 - Thermal & Moisture Protection
08 - Openings
09 - Finishes
10 - Specialties
11 - Equipment
12 - Furnishings
13 - Special Construction
14 - Conveying Equipment
21 - Fire Suppression
22 - Plumbing
23 - HVAC
26 - Electrical
27 - Communications
28 - Electronic Safety & Security
31 - Earthwork
32 - Exterior Improvements
33 - Utilities
34 - Transportation
48 - Electrical Power Generation
49 - Field Surveys, Staking
Bid Risk
FFE Extra
50 - Sub Bonds
55 - Construction Contingency
56 - Contractor Fee
Total
check
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units
Common Wood
Common Vinyl
Hall Flooring
Hall Flooring - Elevators
Common - Plank
Common - VCT
Common - Rubber Floor
Common - Carpet
Appliances
Blinds
Total Appliances, Flooring & Blinds
Site Work
Major Categories
Existing Conditions
Earthwork
Exterior Improvements
Utilities
Transportation
Electrical Power Generation
Minor Categories
Carports
Dumpsters
Gazebo
Other Site
Pools and Spas
Offsite Street Signs
Street Lights
Pump House Concrete
Total Site Work
Offsite Asphalt Sawcut and Removal
Offsite Paving
Offsite Curbs and Gutters
Offsite Concrete Flatwork
Storm Drain
Off Site Water
Off Site Sewer
Off Site Electric
Traffic Control
Pump House Concrete
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs
Street Lights
Offsite Asphalt Sawcut and Removal
Offsite Paving
Offsite Curbs and Gutters
Offsite Concrete Flatwork
Off Site Water
Off Site Sewer
Storm Drain
Off Site Electric
Traffic Control
Other Ineligible Costs
Major Categories
Parking Garage
Minor Categories
Pump House Concrete
Pool Area Shower Concrete
Cabana Concrete
Pool Equipment Foundation
Deck Concrete
Masonry Veneer Pool Area
Pool Equipment Shower Stone
Cabana Iron
Pool Equipment Gate
Cabana Framing
BBQ Framing
Fireplace Framing
Trellis
BBQ Trim
Cabana Roofing
Pump House Roofing
Pool Equipment Windows
Pool Glass Walls
Stucco - Pump House
Stucco - Cabana
Stucco - Pool Wall
Unit Carport Signs
Fire Places - Pool Area
BBQ Units
BBQ Top
Pools and Spas
Carports
Pool Equipment Cover
Pool and Spa Lifts
Pool Area
Pool Equipment
Carports Electrical
Carport Fixtures
Cabana Electrical
Cabana Fixtures
Pool Lighting Electrical
Pool Lighting Fixtures
Pool Equipment Electrical
Pump House Electrical
Pump House Fixtures
Pool Decks
Pool Hardscape
Pool Fence
Pool Walls
Pet Wash
Office Equipment
Gym Exercise Equipment
Playground / Basketball Hoop
Rec Building TV Media Computer
Rec Building Telephone System

## LEVEL 2.1
Project Details
Project | Robindale & 215 | [7 empty] | Total Cost | 68005168.6858 |  | Unit Breakdown |  |  | Parking
Budget Level | Level 2 | [10 empty] | Unit Type | Number | % | Cover Parking | 286 | [8 empty] | Railing Estimate |  |  | Building 3 | 147 | Stucco |  |  | Building 3 | 61455
Product | Senior | [7 empty] | Cost Per Unit | 187342.0625 |  | Studios | 0 | 0% | Cover Accesible Parking | [9 empty] | Building 1 |  |  |  | 98 | Building 1
Start Date | [11 empty] | 1 Br - 1 Ba | 218 | 60.06% | Open Parking | 157 | [8 empty] | Northwest | 190 |  |  | 176 | Northwest | 19256
Timeline | 24 |  |  | 80 |  |  |  |  | Cost Per SF | 187.5637 |  | 2 Br - 1 Ba | 145 | 39.94% | Accessible Parking | 14 | [8 empty] | Southwest | 146 |  |  | 70 | Southwest | 8980
Floors | 2 |  |  | 12.5 | [7 empty] | 2 Br - 2 Ba | 0 | 0% | Waiver | 0 | [8 empty] | Northeast | 118 |  |  | 491 | Northeast | 8850
Bldg. SF | 362571 | [7 empty] | Efficiency | 78.18% |  | 3 Br - 2 Ba | 0 | 0% | Total Parking Provided | 457 | [8 empty] | Southeast | 306 |  |  |  | Southeast | 19965
Acres | 17.35 | [10 empty] | Totals | 363 | 100% | Parking Ratio | 1.259 | [8 empty] | More | 132 | 892 |  |  | More | 24325 | 81376
Site SF | 755766
Buildings | 3 | [23 empty] | Building 2 & 5 |  |  | Building 4 | 112 | Building 2 & 5 |  |  | Building 4 | 29517
[25 empty] | Northwest |  |  |  | 160 | Northwest
Description | Cost Code | Cost Category | Sub job | Source | UMO | Quantity | U.P. | Escal % | Total U.P. | Sub Total | Total | Description / Details
General Requirement | 01 | S |  |  | Mo | 24 | 137183.2628 | 0% | 137183.2628 | 3292398.3063
General Requirements | 01 | [9 empty] | 3292398.3063
Potholing | 02-3213 | S | ON-SITE | Allowance |  | 1 | 16000 | 0% | 16000 | 16000
Existing Conditions | 02 | [9 empty] | 16000
Slabs | 03-3101 | S | BUILDING | Torrey Pines | SF | 177268 | 11.99 | 0% | 11.99 | 2125443.32 |  | 4" over 4" slab profile. WH that has a proposal at $9.16 by NRC but all other competitors are over $12/sf.
Deepened Footings | 03-3101 | S | BUILDING | N/A |  |  |  |  | 0 | 0
Concrete Slab Repairs | 03-3101 | RR | BUILDING | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Pump House Concrete | 03-3101 | S | PUMPHOUSE | Allowance | LS | 1 | 8500 |  | 8500 | 8500
Trash Enclosure Concrete | 03-3102 | S | OTHER SITE | Allowance | EA | 14 | 5000 | 0% | 5000 | 70000
Pool Area Shower Concrete | 03-3105 | S | POOL AREA | Allowance | LS | 1 | 23959 | 0% | 23959 | 23959
Cabana Concrete | 03-3107 | S | POOL AREA | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Pool Equipment Foundation | 03-3108 | S | POOL EQUIP | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Lightweight Concrete | 03-3116 | S | BUILDING | Bruner | SF | 171978.5 | 2.8 | 0% | 2.8 | 481539.8 |  | Nevada Gypsum 1" with Mat.
Deck Concrete | 03-5001 | S | BUILDING | Bruner | SF | 2236 | 20.5251 | 0% | 20.5251 | 45894.0515
Concrete | 03 | [9 empty] | 2775836.1715
Elevator Shaft | 04-2201 | S | BUILDING | N/A | Stop | 0 | 11500 | 0% | 11500 | 0 |  | Wood framed.
Trash Enclosure | 04-2202 | S | OTHER SITE | West H. | Count | 14 | 7000 | 0% | 7000 | 98000
Masonry Veneer | 04-4301 | S | ON-SITE | N/A |  |  | 0 |  | 0 | 0
Masonry Veneer Pool Area | 04-4305 | S | POOL AREA | Allowance | LS | 3 | 5000 | 0% | 5000 | 15000
Pool Eq. Shower | 04-4306 | A | POOL EQUIP | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Masonry | 04 | [9 empty] | 128000
Structural Steel | 05-1201 | S | BUILDING | Allowance | LS | 1 | 150000 | 0% | 150000 | 150000 |  | Place holder. No Plans
Elevator Shaft Iron | 05-1202 | S | BUILDING | Allowance | Count | 6 | 4250 | 0% | 4250 | 25500
Stair Handrails | 05-5201 | S | BUILDING | West H. | Flight | 19 | 3000 | 0% | 3000 | 57000
Garage Stair Railings | 05-5201 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Cabana Iron | 05-7004 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
Pool Equipment Gate | 05-7005 | S | POOL EQUIP | Torrey Pines | Count | 1 | 1950 | 0% | 1950 | 1950
Iron Railings | 05-7300 | S | BUILDING | West H. | LF | 2595 | 92.5 | 0% | 92.5 | 240037.5
Cable Railings | 05-7316 | S | COMMON AREA | N/A |  |  | 0 | 0% | 0 | 0
Metals | 05 | [9 empty] | 474487.5
Framing | 06-1100 | S | BUILDING | Bruner | SF | 362571 | 18.68 | 0% | 18.68 | 6772826.28 |  | Unchanged
Framing Pump House | 06-1100 | S | PUMPHOUSE | Bruner | SF | 600 | 18.68 | 0% | 18.68 | 11208
Framing - Crane | 06-1100 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Framing | 06-1109 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Framing | 06-1110 | S | COMMON AREA | Allowance | LS | 4 | 2500 | 0% | 2500 | 10000
Fireplace Framing | 06-1111 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Trellis | 06-1114 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Pool Equipment Framing | 06-1114 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Finish Carpentry - Units | 06-2001 | S | BUILDING | WH | Liavable SF | 269691 | 3.55 | 10% | 3.905 | 1053143.355 |  | Per WH proposal based on liavable SF.
Finish Carpentry - Common | 06-2001 | S | COMMON AREA | Bruner | SF | 362571 | 1.08 | 10% | 1.188 | 430736.136 |  | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies.
Finish Carpentry - Pump House | 06-2001S | S | PUMPHOUSE | Allowance | LS | 1 | 4000 | 0% | 4000 | 4000
BBQ Trim | 06-2006 | S | COMMON AREA | Allowance | LS | 4 | 1250 | 0% | 1250 | 5000
Shutters | 06-4919 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Wood, Plastics, & Composites | 06 | [9 empty] | 8286913.771
Insulation | 07-2101 | S | BUILDING | Bruner Ave | SF | 362571 | 2.5 | 0% | 2.5 | 906427.5 |  | Red Rock proposal.
Insulation - PH | 07-2101 | S | PUMPHOUSE | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Roofing | 07-3001 | S | BUILDING | Bruner | Squares | 2143.43 | 596 | 0% | 596 | 1277484.28
Roofing - PH | 07-3001 | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Cabana Roofing | 07-3002 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Pump House Roofing | 07-3002 | S | PUMPHOUSE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Pool Equipment Roofing | 07-3003 | S | POOL EQUIP | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Trash Enclosure Cover | 07-6101 | S | OTHER SITE | Bruner | Count | 14 | 6000 | 0% | 6000 | 84000
Pigeon Proofing | 07-7001 | S | BUILDING | Allowance | SF | 362571 | 0.08 | 0% | 0.08 | 29005.68
Gutters and Downspouts | 07-7124 | S | BUILDING | Allowance | SF | 362571 | 0.05 | 0% | 0.05 | 18128.55
Roof Ladders | 07-7210 | S | BUILDING | Allowance | Count | 6 | 1550 | 0% | 1550 | 9300 |  | 2 Per building
Roof Access Doors | 07-7233 | S | BUILDING | Allowance | Count | 6 | 2500 | 0% | 2500 | 15000 |  | 2 Per building
Roof Winch | 07-7250 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Thermal & Moisture Protection | 07 | JASON | [8 empty] | 2366346.01
Entry Doors | 08-1001 | S | COMMON AREA | Allowance | Count | 3 | 8000 | 0% | 8000 | 24000
Common Doors | 08-1002 | S | COMMON AREA | Included |  |  |  | 0% | 0 | 0
Pocket Doors - 3 Panel | 08-1002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Garage Doors | 08-3619 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Windows and Sliding Glass Doors | 08-5301 | S | BUILDING | West H. | Per Unit | 363 | 1450 | 0% | 1450 | 526350 |  | Contempo unit windows Proposal plus $100 per unit for frontage windows.
Windows Repair and Replacement | 08-5301 | RR | BUILDING | Allowance | Per Unit | 363 | 75 | 0% | 75 | 27225
Pool Equipment Windows | 08-5303 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Pool Glass Walls | 08-8001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Fixed Glass | 08-8002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED Install | 08-8302 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Framed | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Polished Edges (Units) | 08-8301 | S | BUILDING | Bruner | Bathroom | 363 | 175 | 0% | 175 | 63525 |  | Updated based on Bruner budget
Mirrors - Polished Edges (Restrooms) | 08-8301 | S | BUILDING | Allowance | Count | 6 | 300 | 0% | 300 | 1800
Openings | 08 | JASON | [8 empty] | 642900
Cost Prep Labor | 09-0101 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cost Prep Mat - Home Depot | 09-0102 | S | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Clean Up - Final | 09-0103 | S | BUILDING | Bruner | SF | 362571 | 0.85 | 0% | 0.85 | 308185.35 |  | Includes Dumpters
Clean Up - During Construction - Labor | 09-0104 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000
Dumpsters | 09-0113 | S | DUMPSTERS | Allowance | Unit | 363 | 79 | 0% | 79 | 28677
Clean Up - Hauling Exterior | 09-0121 | S | ON-SITE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Included in Construction Cleaning Contract.
Stucco | 09-2423 | S | BUILDING | Bruner Ave | SY | 23863.34 | 39.8368 | 0% | 39.8368 | 950639.2965 |  | Pricing from Bruner contract.
Stucco - Pump House | 09-2423S | A | PUMPHOUSE | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Stucco - Walls | 09-2424 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Area | 09-2428 | A | POOL AREA | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Stucco - Cabana | 09-2429 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Equipment | 09-2430 | S | POOL EQUIP | Pebble | LS | 1 | 5000 | 0% | 5000 | 5000
Stucco - Repairs | 09-2423A | RR | BUILDING | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Drywall | 09-2905 | S | BUILDING | West H. | SF | 362571 | 7.65 | 0% | 7.65 | 2773668.15 |  | WH Classic proposal.
Drywall - Repairs | 09-2905A | RR | BUILDING | Allowance | Unit | 363 | 85 | 0% | 85 | 30855
Drywall - Pump House | 09-2905S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Tile Tubs and Showers | 09-3001 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Common Tile | 09-3002 | S | COMMON AREA | Torrey Pines | Unit | 363 | 468.71 | 0% | 468.71 | 170141.73 |  | Based on Torrey Pines awarded proposal
Kitchen Backsplash | 09-3003 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Tile | 09-3008 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Flooring - Units | 09-6001 | S | BUILDING | Bruner | SY | 31493.6667 | 16.2966 | 0% | 16.2966 | 513238.1887 |  | Sheet Vinyl - Seamless
Common Wood | 09-6401 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common Vinyl | 09-6517 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Hall Flooring | 09-6520 | S | COMMON AREA | Torrey Pines | SF | 362571 | 0.75 | 0% | 0.75 | 271928.25 |  | Torrey Pines approved proposal
Hall Flooring - Elevators | 09-6520A | A | COMMON AREA | Allowance | Count | 6 | 750 | 0% | 750 | 4500
Common - Plank | 09-6521 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common - VCT | 09-6522 | S | COMMON AREA | N/A | SF | 0 | 0 | 0% | 0 | 0
Common - Rubber Floor (Ecore) | 09-6566 | S | COMMON AREA | Bruner | SF | 1901.9 | 19.54 | 0% | 19.54 | 37163.126 |  | Bruner proposal
Common - Carpet Stairs | 09-6802 | S | COMMON AREA | Pebble | Count | 19 | 1848.1429 | 0% | 1848.1429 | 35114.7143 |  | Pebble contracted Price (RMI) plus an additional $300)
Hall Runner Install | 09-6803 | S | COMMON AREA | Pebble | SF | 362571 | 0 | 0% | 0 | 0 |  | Based on Torrey Pines, assumption is that we are not doing hall runners (if so, $0.05 per SF)
Hall Runner Materials | 09-6804 | S | COMMON AREA | Pebble | SF | 362571 | 0 | 0% | 0 | 0 |  | Based on Torrey Pines, assumption is that we are not doing hall runners (if so, $0.30 per SF)
Painting - Repairs | 09-9101A | RR | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Painting | 09-9101 | S | BUILDING | West H. | SF | 362571 | 1.98 | 0% | 1.98 | 717890.58 |  | Classic Proposal
Painting - Pump House | 09-9101S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Painting - Walls | 09-9102 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Painting - Pool Area | 09-9106 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Wall Covering |  | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Walls - Specialty | 09-9110 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Finishes | 09 | JASON | [8 empty] | 5963501.3854
Entry Directory | 10-1300 | S | ON-SITE | N/A |  |  | 5478 | 0% | 5478 | 0
Unit Carport Signs | 10-1401 | S | CARPORT | Pebble | Unit | 363 | 212 | 0% | 212 | 76956 |  | Per Pebble budget
Site Signage | 10-1404 | S | ON-SITE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Entry Sign Letters | 10-1419 | S | ON-SITE | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Offsite Street Signs | 10-1454 | S | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Bath Accessories | 10-2816 | S | BUILDING | Pebble | Per Bathroom | 363 | 41 | 0% | 41 | 14883 |  | Per Pebble Budget
Shower Doors | 10-2919 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places | 10-3000 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places - Pool Area | 10-3200 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
BBQ Units | 10-3355 | S | POOL AREA | Arzano | LS | 4 | 3360 | 0% | 3360 | 13440
Lock Boxes | 10-4116 | S | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fire Extinguishers | 10-4416 | S | BUILDING | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 |  | Is this not included in the sprinkler contract? Yes but seperate cost code.
Mail Boxes | 10-5523 | S | BUILDING | Pebble | Unit | 363 | 230 | 0% | 230 | 83490 |  | Per Pebble Budget
Closet Shelving | 10-5723 | S | BUILDING | Bruner | Unit | 363 | 332 | 0% | 332 | 120516
Window Awnings Small | 10-7313 | S | BUILDING | Torrey Pines | Count | 30 | 2500 | 0% | 2500 | 75000
Window Awnings Large | 10-7313 | S | BUILDING | Torrey Pines | Count | 10 | 8500 | 0% | 8500 | 85000
Specialties | 10 | JASON | [8 empty] | 525785
Appliances | 11-3013 | S | BUILDING | Bruner | Unit | 363 | 3169.7043 | 5% | 3328.1895 | 1208132.8053
Appliances - Laundry Room | 11-3013 | S | BUILDING | Torrey Pines | Units | 363 | 343.7053 | 0% | 343.7053 | 124765.0105 |  | Based on Torret Pines ($65k) Laundry room appliance cost per unit.
Appliances - Common | 11-3013 | S | BUILDING | Allowance | LS | 1 | 35000 | 0% | 35000 | 35000 |  | Kithcen and laundry rooms
Equipment | 11 | JASON | [8 empty] | 1367897.8159
Dumpsters | 12-0131 | S | DUMPSTERS | N/A | 0 | 0 | 0 | 0% | 0 | 0 |  | Included in Construction Cleaning Contract | [7 empty] | W.H Units | Box Count | Robin. Units | # of Units | Total Counts
Blinds | 12-2100 | S | BUILDING | Torrey Pines | Per Unit | 363 | 443 | 0% | 443 | 160809 |  | Incudes New Requirement for Cordless Blinds. | [7 empty] | A1A | 16 | 1A | 168 | 2688
Cabinets Units | 12-3531 | S | BUILDING | West H. | Boxes | 6830 | 137.8 | 0% | 137.8 | 941174 |  | Based on Thermafoil White, W.H. units (A1A, B1B, B3A, and B2C) to approximate counts. Add $150,260 if upgrading to Morning Dew ($159.80 / SF) |  |  |  |  | Counts to the side |  |  | B1B | 14 | 1B | 52 | 728
Cabinet Common Areas | 12-3535 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000 | [9 empty] | B3A | 24 | 2A | 125 | 3000
Counter Tops Units | 12-3601 | S | BUILDING | Bruner | Unit | 363 | 1868.4433 | 0% | 1868.4433 | 678244.9175 |  | Based on Arctic White SF cost from Bruner and Takeoffs. Add $79,844 if upgrading to Carrera Trigato ($28.40 / SF) |  |  |  |  | Counts to the side |  |  | B2C | 23 | 2B | 18 | 414
Counter Tops Common Areas | 12-3605 | A | BUILDING | Allowance | LS | 1 | 65000 | 0% | 65000 | 65000 | [13 empty] | 6830
Counter Tops Pool Area | 12-3608 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Top | 12-3609 | S | POOL AREA | Allowance | LS | 4 | 6000 | 0% | 6000 | 24000
Furnishings | 12 | JASON | [8 empty] | 1944227.9175 | [8 empty] | Units | Countertop SF | # of Units | Total Counts
Pools and Spas | 13-1113 | S | POOL AREA | W. Henderson | LS | 1 | 290932.3333 | 0% | 290932.3333 | 290932.3333 |  | WH plus $37k for a 2nd spa. | [7 empty] | 1A | 55.2 | 168 | 9273.6
Carports | 13-3401 | S | CARPORT | Torrey Pines | Count | 286 | 2292 | 0% | 2292 | 655512 |  | Proposal | [7 empty] | 1B | 77.08 | 52 | 4008.16
Pool Equipment Cover | 13-3402 | S | POOL EQUIP | Decatur | Count | 1 | 7049 | 0% | 7049 | 7049 | [9 empty] | 2A | 64.88 | 125 | 8110
Special Construction | 13 | JASON | [8 empty] | 953493.3333 | [8 empty] | 2B | 64.6 | 18 | 1162.8
Trash Chute | 13-G | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Trash Chute | 13-G | [9 empty] | 0 | [11 empty] | 22554.56
Elevator | 14-2400 | S | BUILDING | West H. | Elevator | 6 | 80632.8333 | 0% | 80632.8333 | 483797 |  | West Henderson (Otis) Proposal - $10k per Bradley Roska at Otis | [5 empty] | 40316.4167
Pool and Spa Lifts | 14-4101 | S | POOL AREA | Allowance | Count | 2 | 6500 | 0% | 6500 | 13000 | [7 empty] | 80632.8333
Conveying Equipment | 14 | JASON | [8 empty] | 496797
Sprinkler Design & Permit | 21-0600 | S | BUILDING | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Sprinkler System | 21-1313 | S | BUILDING | Bruner | SF | 362571 | 2.65 | 0% | 2.65 | 960813.15 |  | SNF Proposal at Bruner.
Fire Pump | 21-3000 | S | PUMPHOUSE | Bruner | Count | 1 | 125000 | 0% | 125000 | 125000 |  | Focus Bruner proposal (2nd lowest) | [5 empty] | 0.081633
Fire Suppression | 21 | JASON | [8 empty] | 1110813.15
1 Bathroom Unit | 22-1001 | S | BUILDING | Bruner | Count | 363 | 10069 | 0% | 10069 | 3655047 |  | Bruner pricing by Focus with comventional DWV.
2 Bathroom Unit | 22-1001 | S | BUILDING | N/A | 0 | 0 | 0 | 0% | 0 | 0
Plumbing - Pump House | 22-1001S | S | PUMPHOUSE | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pool Area | 22-1003 | S | POOL AREA | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Pool Equipment | 22-1007 | S | POOL EQUIP | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Plumbing | 22 | JASON | [8 empty] | 3688547
HVAC Standard | 23-3001 | S | BUILDING | Bruner | Unit | 363 | 9845.3608 | 0% | 9845.3608 | 3573865.9794 |  | Allstate signed off proposal
HVAC - Pump House | 23-3001S | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
HVAC | 23 | JASON | [8 empty] | 3588865.9794
Electrical | 26-1001 | S | BUILDING | West H. | SF | 362571 | 10.61 | 0% | 10.61 | 3846878.31 |  | Sigma proposal.
Electrical - Pump House | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Electrical Fixtures | 26-5001 | S | BUILDING | Allowance | Unit | 363 | 700 | 0% | 700 | 254100
Building Electrical Fixtures | 26-5002 | S | BUILDING | West H. | Unit | 363 | 120 | 0% | 120 | 43560 |  | Per Unit allowance from West Henderson
Hall Lighting Fixtures | 26-5003 | S | BUILDING | West H. | Unit | 363 | 115 | 0% | 115 | 41745 |  | Per unit allowance from West Henderson
Carports Electrical | 26-1001 | S | CARPORT | West H. | Space | 286 | 200 | 0% | 200 | 57200 |  | Per unit allowance from West Henderson
Carport Fixtures | 26-5001 | S | CARPORT | Allowance | Space | 286 | 50 | 0% | 50 | 14300
Cabana Electrical | 26-1001 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Cabana Fixtures | 26-5004 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Street Lights | 26-5613 | S | Offsite | Budget | Count | 4 | 15000 | 0% | 15000 | 60000
Site Lighting Electrical | 26-1005 | S | ON-SITE | Allowance | Acre | 17.35 | 2500 | 0% | 2500 | 43375
Site Lighting Fixtures | 26-5602 | S | ON-SITE | Allowance | Acre | 17.35 | 1750 | 0% | 1750 | 30362.5
Pool Lighting Electrical | 26-1004 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Lighting Fixtures | 26-5603 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Equipment Electrical | 26-1007 | S | POOL EQUIP | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pump House Electrical | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Pump House Fixtures | 26-5001 | S | PUMPHOUSE | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Electrical | 26 | [9 empty] | 4455520.81
TV and Media | 27-2201 | A | BUILDING | Allowance | LS | 3 | 1000 | 0% | 1000 | 3000 |  | Per Building
DAS System | 27-3010 | S | BUILDING | Torrey Pines | SF | 362571 | 0.45 | 0% | 0.45 | 163156.95
Pool ADA Phone | 27-3201 | S | POOL AREA | Allowance | LS | 1 | 800 | 0% | 800 | 800 |  | Per Pool
Communications | 27 | [9 empty] | 166956.95
Security System | 28-1001 | S | BUILDING | Bruner | Unit | 363 | 551.2887 | 0% | 551.2887 | 200117.7835
Site Security System | 28-2001 | S | ON-SITE | Pebble | Mo | 24 | 5642.8571 | 0% | 5642.8571 | 135428.5714 |  | Pebble monthly cost to date.
Fire Alarm / Two Way Comm AOR | 28-4601 | S | BUILDING | Decatur | SF | 361641 | 1.94 | 0% | 1.94 | 701583.54 |  | Used Decatur because the new low frequency code expected to be adopted by Clark County as well.
Fire Alarm - Pump House | 28-4601S | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Electronic Safety & Security | 28 | [9 empty] | 1047129.8949
Construction Water | 31-0121 | S | ON-SITE | Allowance | Acre | 17.35 | 6500 | 0% | 6500 | 112775
Dust Control | 31-0122 | S | ON-SITE | Allowance | Acre | 17.35 | 3500 | 0% | 3500 | 60725
Track Out Pad / DEMO | 31-0505 | S | ON-SITE | Budget | LS | 1 | 100000 | 0% | 100000 | 100000
Rock Dirt Haul Off | 31-1492 | S | ON-SITE | Budget | LS | 1 | 50000 | 0% | 50000 | 50000
Mass Grading | 31-2201 | S | ON-SITE | Budget | LS | 1 | 1257581.3634 | 0% | 1257581.3634 | 1257581.3634
Fine Grade | 31-2216 | S | ON-SITE | Budget | LS | 1 | 52966.135 | 0% | 52966.135 | 52966.135
Hard Dig | 31-2319 | S | ON-SITE | Budget | LS | 1 | 100000 | 0% | 100000 | 100000
Dewatering | 31-2322 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Storm Water Prevention | 31-2501 | S | ON-SITE | Allowance | Acre | 17.35 | 2500 | 0% | 2500 | 43375
Earthwork | 31 | [9 empty] | 1777422.4984
Bond Repair | 32-0100 | RR | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Street Cleaning | 32-0111 | S | OTHER SITE | Allowance | LS | 2 | 2500 | 0% | 2500 | 5000
Asphalt Sawcut and Removal | 32-0506 | S | ON-SITE | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000 |  | See Budget File
Paving | 32-1216 | S | ON-SITE | Budget | LS | 1 | 601630.93 | 0% | 601630.93 | 601630.93 |  | See Budget File
Seal Coat | 32-1236 | S | ON-SITE | Allowance | SF | 215053 | 0.25 | 0% | 0.25 | 53763.25
Pavers | 32-1401 | S | OTHER SITE | Pebble | SF | 3000 | 8.5 | 0% | 8.5 | 25500 |  | Allowance
Pool Decks | 32-1402 | S | POOL AREA | Pebble | SF | 8023 | 8.5 | 0% | 8.5 | 68195.5 |  | Pool Deck
Curbs and Gutters | 32-1613 | S | ON-SITE | West H. | LS | 1 | 114991.74 | 0% | 114991.74 | 114991.74 |  | See Budget File
Tack On Curb | 32-1614 | S | ON-SITE | West H. | LS | 1 | 134729.4 | 0% | 134729.4 | 134729.4 |  | See Budget File
Concrete Flatwork | 32-1623 | S | ON-SITE | West H. | LS | 1 | 338206.8875 | 0% | 338206.8875 | 338206.8875 |  | Preliminary Plans has 5' sidewalk versus 3.5' previous budget.
Bus Pad | 32-1625 | S | OTHER SITE | N/A |  |  |  | 0% | 0 | 0
Pool Hardscape | 32-1626 | S | POOL AREA | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Street Signs / Striping | 32-1700 | S | ON-SITE | Allowance | Acre | 17.35 | 3000 | 0% | 3000 | 52050
Walls Iron | 32-3101 | S | ON-SITE | Torrey Pines | LS | 1 | 164035.4 | 0% | 164035.4 | 164035.4 |  | See Budget File
Trash Enclosure Iron Gates | 32-3103 | S | OTHER SITE | Torrey Pines | Count | 14 | 2485 | 0% | 2485 | 34790
Site Railings | 32-3104 | A | OTHER SITE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Dog Run Fence | 32-3105 | S | ON-SITE | Allowance | LF | 300 | 55 | 0% | 55 | 16500
Pool Fence | 32-3106 | S | POOL AREA | Torrey Pines | LF | 300 | 70 | 0% | 70 | 21000
Pool Fence Gates | 32-3106 | S | POOL AREA | Torrey Pines | Count | 2 | 1950 | 0% | 1950 | 3900
Entry Security Gates | 32-3111 | S | ON-SITE | Torrey Pines | LS | 1 | 6000 | 0% | 6000 | 6000 |  | Crash Gate
Entry Security Gates Electrical | 32-3112 | S | ON-SITE | N/A |  |  | 3555 | 0% | 3555 | 0
Entry Gate Transmitters | 32-3113 | S | ON-SITE | N/A |  |  | 44 | 0% | 44 | 0
Entry Gates | 32-3114 | S | ON-SITE | Budget | LS | 0 | 1950 | 0% | 1950 | 0
Temp Fencing | 32-3120 | S | ON-SITE | Allowance | LS | 17.35 | 5000 | 0% | 5000 | 86750
Walls Masonry | 32-3201 | S | ON-SITE | West H. | LS | 1 | 493481.675 | 0% | 493481.675 | 493481.675 |  | Preliminary Civil Plans
Walls Pilaster Caps | 32-3202 | S | ON-SITE | West H. | LS | 1 | 31250 | 0% | 31250 | 31250 |  | Preliminary Civil Plans
Retaining Walls | 32-3204 | S | ON-SITE | West H. | LS | 1 | 303105.8 | 0% | 303105.8 | 303105.8 |  | Preliminary Civil Plans
Pool Walls | 32-3208 | A | POOL AREA | Allowance | LS | 2 | 7500 | 0% | 7500 | 15000
Site Furniture Permanent | 32-3343 | A | BUILDING | Allowance | LS | 1 | 7000 | 0% | 7000 | 7000
Site Landscaping | 32-9001 | S | ON-SITE | West H. | SF | 316370.92 | 9 | 0% | 9 | 2847338.28 |  | West Henderson proposal with 304k lanscaping sf is under $8.50 /sf
Site Landscaping Lighting | 32-9001 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Site Landscaping Planter Pots | 32-9433 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Offsite Asphalt Sawcut and Removal | 32-0506 | S | Offsite | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Offsite Paving | 32-1216 | S | Offsite | Budget | LS | 1 | 341251.0625 | 0% | 341251.0625 | 341251.0625 |  | See Budget File.
Offsite Curbs and Gutters | 32-1613 | S | Offsite | West H. | LS | 1 | 45316 | 0% | 45316 | 45316 |  | See Budget File
Offsite Concrete Flatwork | 32-1623 | S | Offsite | West H. | LS | 1 | 25863 | 0% | 25863 | 25863 |  | See Budget File
Offsite Parvin Realignment | 32-5500 | S | Offsite | Budget | LS | 1 | 0 | 0% | 0 | 0
Exterior Improvements | 32 | [9 empty] | 5896648.925
Temp Power | 33-0501 | A |  | Allowance | Unit | 363 | 375 | 0% | 375 | 136125
Traffic Control, AC Removal and Patch | 33-1001 | A | Offsite | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Water | 33-1001 | S | ON-SITE | Budget | LS | 1 | 1292500.98 | 0% | 1292500.98 | 1292500.98
Sewer | 33-3001 | S | ON-SITE | Budget | LS | 1 | 516087 | 0% | 516087 | 516087
Storm Drain | 33-4001 | S | ON-SITE | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Sub Drains | 33-4116 | A |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Gas | 33-5001 | S | Offsite | Budget | LS | 1 | 0 | 15% | 0 | 0
Electric | 33-7101 | S |  | Budget | LS | 1 | 350575.2 | 0% | 350575.2 | 350575.2
Secondary Conduit | 33-7102 | A |  | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Bollards | 33-7103 | S |  | Allowance | LS | 1 | 15600 | 0% | 15600 | 15600
Cable TV | 33-8201 | S |  | N/A |  |  |  | 0% | 0 | 0
Phone | 33-8202 | S |  | N/A |  |  |  | 0% | 0 | 0
Off Site Water | 33-1001 | S | Offsite | Budget | LS | 1 | 387993.65 | 0% | 387993.65 | 387993.65 |  | POC on Robindale water lines.
Off Site Sewer | 33-3001 | S | Offsite | Alowance | LS | 1 | 91720 | 0% | 91720 | 91720 |  | Allowance. Per Pete POC are onsite.
Off Site Storm Drain | 33-4001 | S | Offsite | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Off Site Electric | 33-7101 | S | Offsite | Budget | LS | 1 | 61000 | 0% | 61000 | 61000
Utilities | 33 | [9 empty] | 2941601.83
Bridge |  |  | ON-SITE | Allowance | LS | 2 | 594250 | 0% | 594250 | 1188500 |  | UNchanged
Other |  |  | ON-SITE | Allowance | LS | 1 | 300000 | 0% | 300000 | 300000 |  | Current prelim plan calls for 47,604 Sf 6" concrete with 18" on center rebard. Estimated cost $600k but chosed with $300k allowance since this may change.
Brigde Over Duct Creek Wash | 33 | [9 empty] | 1488500
Traffic Control | 34-4116 | A | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Transportation | 34 | [9 empty] | 7500
Solar PV System | 48-1413 | S |  | Allowance | LS | 1 | 977434 | 0% | 977434 | 977434 |  | Unchanged
Solar PV Conduit | 48-1414 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Unchanged
Car Charging Stations | 48-1913 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Unchanged
Electrical Power Generation | 48 | [9 empty] | 1077434
Staking | 49-0601 | S |  | Pebble | LS | 17.35 | 9000 | 0% | 9000 | 156150 |  | Using Pebble Cost to Date as Benchmark.
Re Staking | 49-0602 | S |  | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Using Pebble Cost to Date as Benchmark.
Certs and Verifications | 49-0603 | S |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000 |  | Using Pebble Cost to Date as Benchmark.
Slab Testing | 49-0801 | S |  | Allowance | EAH | 3 | 15000 | 0% | 15000 | 45000 |  | Using Pebble Cost to Date as Benchmark.
Grading Testing | 49-0802 | S |  | Pebble | LS | 17.35 | 5000 | 0% | 5000 | 86750 |  | Using Pebble Cost to Date as Benchmark.
Other Testing | 49-0803 | S |  | Pebble | LS | 17.35 | 5000 | 0% | 5000 | 86750 |  | Using Pebble Cost to Date as Benchmark.
Masonry Testing | 49-0807 | S |  | Allowance | LS | 17.35 | 2500 | 0% | 2500 | 43375 |  | Using Pebble Cost to Date as Benchmark.
Pavement Testing | 49-0808 | S |  | Allowance | LS | 17.35 | 1500 | 0% | 1500 | 26025 |  | Using Pebble Cost to Date as Benchmark.
Third Party Inspections | 49-0950 | S |  | Pebble | LS | 17.35 | 2500 | 0% | 2500 | 43375 |  | Using Pebble Cost to Date as Benchmark.
Field Surveys, Staking | 49 | [9 empty] | 502425
BABA | [5 empty] | 0% |  |  |  | 0
Bid Risk | [5 empty] | 2% |  |  |  | 1097466.1021
Bid Risk & BABA | Bid Risk | [9 empty] | 1097466.1021
Golf Carts | 11-1001 | S |  | Allowance | LS | 2 | 10000 | 0% | 10000 | 20000
Convenience Store Equipment | 11-2101 | S |  | N/A |  |  |  | 0% | 0 | 0
Pet Wash | 11-2102 | S |  | N/A | LS | 0 | 21000 | 0% | 21000 | 0
Office Equipment | 11-2801 | S |  | Allowance | LS | 1 | 20000 | 0% | 20000 | 20000
Gym Exercise Equipment | 11-6613 | S |  | Decatur | SF | 1901.9 | 47.98 | 0% | 47.98 | 91253.162
Playground / Basketball Hoop | 11-6813 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 3720000
Maintenance Shop Equipment | 11-8101 | S |  | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Maintenance Shop Start Up Supplies | 11-8102 | S |  | Alowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fixed Asset Misc. | 11-8105 | S |  | N/A |  |  |  | 0% | 0 | 0
Interior Furniture | 12-5000 | S |  | Allowance | LS | 1 | 700000 | 0% | 700000 | 700000 |  | Per Armen Email with an old proposal on Robindale interior and exteior furniture
Exterior Furniture | 12-5483 | S |  | Allowance | LS | 3 | 100000 | 0% | 100000 | 300000 |  | Per Armen Email with an old proposal on Robindale interior and exteior furniture
Rec Building TV Media Computer | 27-2201 | S |  | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Rec Building Telephone System | 27-3202 | S |  | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Maintenance Radios | 27-3243 | S |  | Allowance | LS | 2 | 1500 | 0% | 1500 | 3000
FFE | FFE Extra | [9 empty] | 1181753.162
Construction Contingency | 55-9800 |  |  |  |  | 5% |  |  |  | 2743665.2552
Construction Contingency | 55 | [9 empty] | 2743665.2552
Sub Bonds | 50-9950 | B |  |  |  | 1.7% |  |  |  | 932846.1868
Sub Bonds | 50 | [9 empty] | 932846.1868
GL Insurance | 50-0001 |  |  |  | 3.03 per $1,000 | 5 |  |  |  | 306866.5255
Misc. | 50-0001 |  |  |  | 5% of GL Ins. | 5% |  |  |  | 15343.3263
Umbrella | 50-0001 |  |  |  | 95% of GL Ins. | 0.95 |  |  |  | 291523.1992
GL Insurance | 50 | [9 empty] | 613733.051
Overhead | 56 |  |  |  |  | 2% |  |  |  | 1112938.67
Contractor Fee | 56 |  |  |  |  | 6% |  |  |  | 3338816.01
OH & Contractor Fee | 56 | [9 empty] | 4451754.68
Total Hard Costs | [10 empty] | 68005168.6858
0
General Requirements | 01 |  |  | 3292398.3063 | [8 empty] | 6% General Conditions
Existing Conditions | 02 |  |  | 16000 | [8 empty] | 54873305.1044
Concrete | 03 |  |  | 2775836.1715 | [8 empty] | 3292398.3063 | 2743665.2552
Parking Garage | 03-G |  |  | #N/A | [8 empty] | 137183.2628
Masonry | 04 |  |  | 128000
Metals | 05 |  |  | 474487.5
Wood, Plastics, & Composites | 06 |  |  | 8286913.771
Thermal & Moisture Protection | 07 |  |  | 2366346.01
Openings | 08 |  |  | 642900
Finishes | 09 |  |  | 5963501.3854
Specialties | 10 |  |  | 525785
Equipment | 11 |  |  | 1367897.8159
Furnishings | 12 |  |  | 1944227.9175
Special Construction | 13 |  |  | 953493.3333
Trash Chute | 13-G |  |  | 0
Conveying Equipment | 14 |  |  | 496797
Fire Suppression | 21 |  |  | 1110813.15
Plumbing | 22 |  |  | 3688547
HVAC | 23 |  |  | 3588865.9794
Electrical | 26 |  |  | 4455520.81
Communications | 27 |  |  | 166956.95
Electronic Safety & Security | 28 |  |  | 1047129.8949
Earthwork | 31 |  |  | 1777422.4984
Exterior Improvements | 32 |  |  | 5896648.925
Utilities | 33 |  |  | 2941601.83
Transportation | 34 |  |  | 7500
Electrical Power Generation | 48 |  |  | 1077434
Field Surveys, Staking | 49 |  |  | 502425
5th Story Factor |  |  |  | #N/A
Bid Risk |  |  |  | 0
FFE |  |  |  | 1181753.162
Construction Contingency | 55 |  |  | 0
Sub Bonds | 50 |  |  | 0
GL Insurance | 50 |  |  | 613733.051
Contractor Fee | 56 |  |  | 0
Total Hard Costs |  |  |  | 68005168.6858
#N/A
Cost Code
Total
01 - General Requirements | 01 |  |  |  | 3292398.3063
02 - Existing Conditions | 02 |  |  |  | 16000
03 - Concrete | 03 |  |  |  | 2775836.1715
04 - Masonry | 04 |  |  |  | 128000
05 - Metals | 05 |  |  |  | 474487.5
06 - Wood, Plastics, & Composites | 06 |  |  |  | 8286913.771
07 - Thermal & Moisture Protection | 07 |  |  |  | 2366346.01
08 - Openings | 08 |  |  |  | 642900
09 - Finishes | 09 |  |  |  | 5963501.3854
10 - Specialties | 10 |  |  |  | 525785
11 - Equipment | 11 |  |  |  | 1367897.8159
12 - Furnishings | 12 |  |  |  | 1944227.9175
13 - Special Construction | 13 |  |  |  | 953493.3333
14 - Conveying Equipment | 14 |  |  |  | 496797
21 - Fire Suppression | 21 |  |  |  | 1110813.15
22 - Plumbing | 22 |  |  |  | 3688547
23 - HVAC | 23 |  |  |  | 3588865.9794
26 - Electrical | 26 |  |  |  | 4455520.81
27 - Communications | 27 |  |  |  | 166956.95
28 - Electronic Safety & Security | 28 |  |  |  | 1047129.8949
31 - Earthwork | 31 |  |  |  | 1777422.4984
32 - Exterior Improvements | 32 |  |  |  | 5896648.925
33 - Utilities | 33 |  |  |  | 4430101.83
34 - Transportation | 34 |  |  |  | 7500
48 - Electrical Power Generation | 48 |  |  |  | 1077434
49 - Field Surveys, Staking | 49 |  |  |  | 502425
Bid Risk | Bid Risk |  |  |  | 1097466.1021
FFE Extra | FFE Extra |  |  |  | 1181753.162
50 - Sub Bonds | 50 |  |  |  | 1546579.2378
55 - Construction Contingency | 55 |  |  |  | 2743665.2552
56 - Contractor Fee | 56 |  |  |  | 4451754.68
Total |  |  |  |  | 68005168.6858
check |  |  |  |  | 0
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units | 09-6001 |  |  |  | 513238.1887 | 09
Common Wood | 09-6401 |  |  |  | 0 | 09
Common Vinyl | 09-6517 |  |  |  | 0 | 09
Hall Flooring | 09-6520 |  |  |  | 271928.25 | 09
Hall Flooring - Elevators | 09-6520A |  |  |  | 4500 | 09
Common - Plank | 09-6521 |  |  |  | 0 | 09
Common - VCT | 09-6522 |  |  |  | 0 | 09
Common - Rubber Floor | 09-6566 |  |  |  | 37163.126 | 09
Common - Carpet | 09-6802 |  |  |  | 35114.7143 | 09
Appliances | 11-3013 |  |  |  | 1367897.8159 | 11
Blinds | 12-2100 |  |  |  | 160809 | 12
Total Appliances, Flooring & Blinds |  |  |  |  | 2390651.0948
Site Work
Major Categories
Existing Conditions | 2 |  |  |  | 16000
Earthwork | 31 |  |  |  | 1777422.4984
Exterior Improvements | 32 |  |  |  | 5896648.925
Utilities | 33 |  |  |  | 4430101.83
Transportation | 34 |  |  |  | 7500
Electrical Power Generation | 48 |  |  |  | 1077434
Minor Categories
Carports | 13-3401 |  |  |  | 655512
Dumpsters | 06-0111 |  |  |  | 0
Gazebo |  |  |  |  | 0
Other Site |  |  |  |  | 0
Pools and Spas | 13-1113 |  |  |  | 290932.3333
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Pump House Concrete | 03-3101 |  |  |  | 2141443.32
Total Site Work |  |  |  |  | 16292994.9067
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  | already included in 32
Offsite Paving | 32-1216OFFSITE |  |  | already included in 32
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  | already included in 32
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  | already included in 32
Storm Drain | 33-4001OFFSITE |  |  | already included in 33
Off Site Water | 33-1001OFFSITE |  |  | already included in 33
Off Site Sewer | 33-3001OFFSITE |  |  | already included in 33
Off Site Electric | 33-7101OFFSITE |  |  | already included in 33
Traffic Control | 34-4116OFFSITE |  |  | already included in 34
Pump House Concrete | 03-3101
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  |  | 0
Offsite Paving | 32-1216OFFSITE |  |  |  | 0
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  |  | 0
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  |  | 0
Off Site Water | 33-1001OFFSITE |  |  |  | 0
Off Site Sewer | 33-3001OFFSITE |  |  |  | 0
Storm Drain | 33-4001OFFSITE |  |  |  | 0
Off Site Electric | 33-7101OFFSITE |  |  |  | 0
Traffic Control | 34-4116OFFSITE |  |  |  | 0
Other Ineligible Costs
Major Categories
Parking Garage | 03-G |  |  |  | 0
Minor Categories
Pump House Concrete | 03-3101 |  |  |  | 2141443.32
Pool Area Shower Concrete | 03-3105 |  |  |  | 23959
Cabana Concrete | 03-3107 |  |  |  | 6500
Pool Equipment Foundation | 03-3108 |  |  |  | 6500
Deck Concrete | 03-5001 |  |  |  | 45894.0515
Masonry Veneer Pool Area | 04-4305 |  |  |  | 15000
Pool Equipment Shower Stone | 04-4306 |  |  |  | 15000
Cabana Iron | 05-7004 |  |  |  | 0
Pool Equipment Gate | 05-7005 |  |  |  | 1950
Cabana Framing | 06-1109 |  |  |  | 0
BBQ Framing | 06-1110 |  |  |  | 10000
Fireplace Framing | 06-1111 |  |  |  | 0
Trellis | 06-1114 |  |  |  | 0
BBQ Trim | 06-2006 |  |  |  | 5000
Cabana Roofing | 07-3002 |  |  |  | 7500
Pump House Roofing | 07-3002 |  |  |  | 7500
Pool Equipment Windows | 08-5303 |  |  |  | 0
Pool Glass Walls | 08-8001 |  |  |  | 0
Stucco - Pump House | 09-2423 |  |  |  | 950639.2965
Stucco - Cabana | 09-2423 |  |  |  | 950639.2965
Stucco - Pool Wall | 09-2423 |  |  |  | 950639.2965
Unit Carport Signs | 10-1401 |  |  |  | 76956
Fire Places - Pool Area | 10-3200 |  |  |  | 0
BBQ Units | 10-3355 |  |  |  | 13440
BBQ Top | 12-3609 |  |  |  | 24000
Pools and Spas | 13-1113 |  |  |  | 290932.3333
Carports | 13-3401 |  |  |  | 655512
Pool Equipment Cover | 13-3402 |  |  |  | 7049
Pool and Spa Lifts | 14-4101 |  |  |  | 13000
Pool Area | 22-1003 |  |  |  | 25000
Pool Equipment | 22-1007 |  |  |  | 6000
Carports Electrical | 26-1001 |  |  |  | 3934078.31
Carport Fixtures | 26-5001 |  |  |  | 269900
Cabana Electrical | 26-1001 |  |  |  | 3934078.31
Cabana Fixtures | 26-5004 |  |  |  | 5000
Pool Lighting Electrical | 26-1004 |  |  |  | 12500
Pool Lighting Fixtures | 26-5603 |  |  |  | 12500
Pool Equipment Electrical | 26-1007 |  |  |  | 2500
Pump House Electrical | 26-1001 |  |  |  | 3934078.31
Pump House Fixtures | 26-5001 |  |  |  | 269900
Pool Decks | 32-1402 |  |  |  | 68195.5
Pool Hardscape | 32-1626 |  |  |  | 10000
Pool Fence | 32-3106 |  |  |  | 24900
Pool Walls | 32-3208 |  |  |  | 15000
Pet Wash | 11-2102 |  |  |  | 0
Office Equipment | 11-2801 |  |  |  | 20000
Gym Exercise Equipment | 11-6613 |  |  |  | 91253.162
Playground / Basketball Hoop | 11-6813 |  |  |  | 0
Rec Building TV Media Computer | 27-2201 |  |  |  | 28000
Rec Building Telephone System | 27-3202 |  |  |  | 2500

## Assumptions & Takeoffs
Unit Matrix |  |  |  |  | Reports Available
Unit Type | Number | % | SF |  | SER (GCW)
1A | 170 | 46.83% | 676 |  | Soils Report
1B | 48 | 13.22% | 764 |  | Alta Survey
2A | 127 | 34.99% | 901 |  | Plans |  |  |  | 10
2B | 18 | 4.959% | 968 | [5 empty] | 160
Totals | 363 | 100% | 283443
600
List of Take offs |  |  | List of Take offs |  |  | List of Take offs |  |  | 490 | Slabs |  | Patios |  | Lightweight
Slab SF | 177268 | GSF | Counter tops | 29662.32 | SF | Fitness Center | 0 | SF |  | Building 1 | 48298.63 | 500 |  | 135 | 48163.63
Elevators | 6 | Count | Blinds | 0 |  | Unit Appliances |  |  |  | Building 2 | 66583.37 | 625 |  | 195 | 66388.37
Elevators Stops | 12 | Count | Landscaping | 316370.92 | SF | Kitchens |  |  |  | Building 3 | 62776.41 | 500 |  | 180 | 62596.41
Trash Encl. | 14 | Site Plan | Lighweight | 171978.5 |  | Laundries |  |  |  | Pump House | 600 |  | Assumption
Stairs | 19 | Count | 1x1 Decks | 3072 | SF | Patio | 1223.57 | SF |  | Pool Equipment | 307
Pool | 1 |  | 2x1 Decks | 0 | SF | Deck | 2236 | SF
Gym | 1901.9 | SF | Lightweight | 0 | SF
Iron Rail | 2595 | LF | Pavers | 0 | SF | Corridors | 35218.83
Roofing | 2143.43 | Square | Pool Deck | 0 | SF | Other Common Areas | 5741.77
Stucco | 23863.34 | Square Yard | Pool Fence | 0 | LF | Laundry | 1103.55 |  |  | Stucco |  | Returns
Livable Area | 269691 | SF | Dog Park Fence | 0 | LF | Great Room (c | 4961.54 |  |  | Building 1 | 48784 | 1800
Carports | 286 | Count | Common Bldg. 1 | 0 | SF | Fitness Center | 1956.73 |  |  | Building 2 | 64771 | 2200
Stairs Landings | 0 | Landings | Asphalt | 0 |  | Leasing | 674.75 |  |  | Building 3 | 66016 | 2254
Pump House | 1 | EA | Pavers | 0 | [6 empty] | 179571 | 6254 | 185825
Lock Boxes | 0 | EA | Pavers Pool | 0 |  |  |  |  | 86 | Squares | 19952.3333 | 694.8889 | 20647.2222
Awning Small | 30 | EA | [6 empty] | 8
Awning Large | 10 | EA | [6 empty] | 10
|  |  | Stucco | [5 empty] | 8 | 1 | 94262 | 98509 | 4247
|  |  | Building A | 6633.44 | SY |  |  |  | 2236 | 2 | 113176 | 136604 | 23428
|  |  | Building B | 8701.64 | SY |  |  |  |  | 3 | 121766 | 127458 | 5692
|  |  | Building C | 8528.26 | SY | [5 empty] | 329204 | 362571 | 33367
|  |  | Total | 23863.34
[10 empty] | Unit |  | SF
[10 empty] | 1A | 166
[10 empty] | 1B | 52
[10 empty] | 2A | 127
[10 empty] | 2B | 18
363

## LEVEL 2
Project Details
Project | Robindale & 215 | [7 empty] | Total Cost | 68767993.9666 |  | Unit Breakdown |  |  | Parking
Budget Level | Level 2 | [10 empty] | Unit Type | Number | % | Cover Parking | 286 | [8 empty] | Railing Estimate |  |  | Building 3 | 147 | Stucco |  |  | Building 3 | 61455
Product | Senior | [7 empty] | Cost Per Unit | 189443.5095 |  | Studios | 0 | 0% | Cover Accesible Parking | [9 empty] | Building 1 |  |  |  | 98 | Building 1
Start Date | [11 empty] | 1 Br - 1 Ba | 218 | 60.06% | Open Parking | 157 | [8 empty] | Northwest | 190 |  |  | 176 | Northwest | 19256
Timeline | 24 | [7 empty] | Cost Per SF | 189.6677 |  | 2 Br - 1 Ba | 145 | 39.94% | Accessible Parking | 14 | [8 empty] | Southwest | 146 |  |  | 70 | Southwest | 8980
Floors | 2 | [10 empty] | 2 Br - 2 Ba | 0 | 0% | Waiver | 0 | [8 empty] | Northeast | 118 |  |  | 491 | Northeast | 8850
Bldg. SF | 362571 | [7 empty] | Efficiency | 78.18% |  | 3 Br - 2 Ba | 0 | 0% | Total Parking Provided | 457 | [8 empty] | Southeast | 306 |  |  |  | Southeast | 19965
Acres | 17.35 | [10 empty] | Totals | 363 | 100% | Parking Ratio | 1.259 | [8 empty] | More | 132 | 892 |  |  | More | 24325 | 81376
Site SF | 755766
Buildings | 3 | [23 empty] | Building 2 & 5 |  |  | Building 4 | 112 | Building 2 & 5 |  |  | Building 4 | 29517
[25 empty] | Northwest |  |  |  | 160 | Northwest
Description | Cost Code | Cost Category | Sub job | Source | UMO | Quantity | U.P. | Escal % | Total U.P. | Sub Total | Total | Description / Details
General Requirement | 01 | S |  |  | Mo | 24 | 138831.5456 | 0% | 138831.5456 | 3331957.0935
General Requirements | 01 | [9 empty] | 3331957.0935
Potholing | 02-3213 | S | ON-SITE | Allowance |  | 1 | 16000 | 0% | 16000 | 16000
Existing Conditions | 02 | [9 empty] | 16000
Slabs | 03-3101 | S | BUILDING | Torrey Pines | SF | 177268 | 11.99 | 0% | 11.99 | 2125443.32 |  | 4" over 4" slab profile. WH that has a proposal at $9.16 by NRC but all other competitors are over $12/sf.
Deepened Footings | 03-3101 | S | BUILDING | N/A |  |  |  |  | 0 | 0
Concrete Slab Repairs | 03-3101 | RR | BUILDING | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Pump House Concrete | 03-3101 | S | PUMPHOUSE | Allowance | LS | 1 | 8500 |  | 8500 | 8500
Trash Enclosure Concrete | 03-3102 | S | OTHER SITE | Allowance | EA | 14 | 5000 | 0% | 5000 | 70000
Pool Area Shower Concrete | 03-3105 | S | POOL AREA | Allowance | LS | 1 | 23959 | 0% | 23959 | 23959
Cabana Concrete | 03-3107 | S | POOL AREA | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Pool Equipment Foundation | 03-3108 | S | POOL EQUIP | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Lightweight Concrete | 03-3116 | S | BUILDING | Bruner | SF | 171978.5 | 2.8 | 0% | 2.8 | 481539.8 |  | Nevada Gypsum 1" with Mat.
Deck Concrete | 03-5001 | S | BUILDING | Bruner | SF | 2236 | 20.5251 | 0% | 20.5251 | 45894.0515
Concrete | 03 | [9 empty] | 2775836.1715
Elevator Shaft | 04-2201 | S | BUILDING | N/A | Stop | 0 | 11500 | 0% | 11500 | 0 |  | Wood framed.
Trash Enclosure | 04-2202 | S | OTHER SITE | West H. | Count | 14 | 7000 | 0% | 7000 | 98000
Masonry Veneer | 04-4301 | S | ON-SITE | N/A |  |  | 0 |  | 0 | 0
Masonry Veneer Pool Area | 04-4305 | S | POOL AREA | Allowance | LS | 3 | 5000 | 0% | 5000 | 15000
Pool Eq. Shower | 04-4306 | A | POOL EQUIP | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Masonry | 04 | [9 empty] | 128000
Structural Steel | 05-1201 | S | BUILDING | Allowance | LS | 1 | 150000 | 0% | 150000 | 150000 |  | Place holder. No Plans
Elevator Shaft Iron | 05-1202 | S | BUILDING | Allowance | Count | 6 | 4250 | 0% | 4250 | 25500
Stair Handrails | 05-5201 | S | BUILDING | West H. | Flight | 19 | 3000 | 0% | 3000 | 57000
Garage Stair Railings | 05-5201 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Cabana Iron | 05-7004 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
Pool Equipment Gate | 05-7005 | S | POOL EQUIP | Torrey Pines | Count | 1 | 1950 | 0% | 1950 | 1950
Iron Railings | 05-7300 | S | BUILDING | West H. | LF | 2595 | 92.5 | 0% | 92.5 | 240037.5
Cable Railings | 05-7316 | S | COMMON AREA | N/A |  |  | 0 | 0% | 0 | 0
Metals | 05 | [9 empty] | 474487.5
Framing | 06-1100 | S | BUILDING | Bruner | SF | 362571 | 18.68 | 0% | 18.68 | 6772826.28 |  | Unchanged
Framing Pump House | 06-1100 | S | PUMPHOUSE | Bruner | SF | 600 | 18.68 | 0% | 18.68 | 11208
Framing - Crane | 06-1100 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Framing | 06-1109 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Framing | 06-1110 | S | COMMON AREA | Allowance | LS | 4 | 2500 | 0% | 2500 | 10000
Fireplace Framing | 06-1111 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Trellis | 06-1114 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Pool Equipment Framing | 06-1114 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Finish Carpentry - Units | 06-2001 | S | BUILDING | Torrey Pines | Unit | 363 | 3210.0359 | 10% | 3531.0395 | 1281767.3538 |  | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies.
Finish Carpentry - Common | 06-2001 | S | COMMON AREA | Bruner | SF | 362571 | 1.08 | 10% | 1.188 | 430736.136 |  | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies.
Finish Carpentry - Pump House | 06-2001S | S | PUMPHOUSE | Allowance | LS | 1 | 4000 | 0% | 4000 | 4000
BBQ Trim | 06-2006 | S | COMMON AREA | Allowance | LS | 4 | 1250 | 0% | 1250 | 5000
Shutters | 06-4919 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Wood, Plastics, & Composites | 06 | [9 empty] | 8515537.7698
Insulation | 07-2101 | S | BUILDING | Bruner Ave | SF | 362571 | 2.5 | 0% | 2.5 | 906427.5 |  | Red Rock proposal.
Insulation - PH | 07-2101 | S | PUMPHOUSE | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Roofing | 07-3001 | S | BUILDING | Bruner | Squares | 2143.43 | 596 | 0% | 596 | 1277484.28
Roofing - PH | 07-3001 | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Cabana Roofing | 07-3002 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Pump House Roofing | 07-3002 | S | PUMPHOUSE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Pool Equipment Roofing | 07-3003 | S | POOL EQUIP | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Trash Enclosure Cover | 07-6101 | S | OTHER SITE | Bruner | Count | 14 | 6000 | 0% | 6000 | 84000
Pigeon Proofing | 07-7001 | S | BUILDING | Allowance | SF | 362571 | 0.08 | 0% | 0.08 | 29005.68
Gutters and Downspouts | 07-7124 | S | BUILDING | Allowance | SF | 362571 | 0.05 | 0% | 0.05 | 18128.55
Roof Ladders | 07-7210 | S | BUILDING | Allowance | Count | 6 | 1550 | 0% | 1550 | 9300 |  | 2 Per building
Roof Access Doors | 07-7233 | S | BUILDING | Allowance | Count | 6 | 2500 | 0% | 2500 | 15000 |  | 2 Per building
Roof Winch | 07-7250 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Thermal & Moisture Protection | 07 | JASON | [8 empty] | 2366346.01
Entry Doors | 08-1001 | S | COMMON AREA | Allowance | Count | 3 | 8000 | 0% | 8000 | 24000
Common Doors | 08-1002 | S | COMMON AREA | Included |  |  |  | 0% | 0 | 0
Pocket Doors - 3 Panel | 08-1002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Garage Doors | 08-3619 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Windows and Sliding Glass Doors | 08-5301 | S | BUILDING | West H. | Per Unit | 363 | 1550 | 0% | 1550 | 562650 |  | Contempo unit windows Proposal plus $100 per unit for frontage windows.
Windows Repair and Replacement | 08-5301 | RR | BUILDING | Allowance | Per Unit | 363 | 75 | 0% | 75 | 27225
Pool Equipment Windows | 08-5303 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Pool Glass Walls | 08-8001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Fixed Glass | 08-8002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED Install | 08-8302 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Framed | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Polished Edges (Units) | 08-8301 | S | BUILDING | Bruner | Bathroom | 363 | 175 | 0% | 175 | 63525 |  | Updated based on Bruner budget
Mirrors - Polished Edges (Restrooms) | 08-8301 | S | BUILDING | Allowance | Count | 6 | 300 | 0% | 300 | 1800
Openings | 08 | JASON | [8 empty] | 679200
Cost Prep Labor | 09-0101 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cost Prep Mat - Home Depot | 09-0102 | S | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Clean Up - Final | 09-0103 | S | BUILDING | Bruner | SF | 362571 | 0.85 | 0% | 0.85 | 308185.35 |  | Includes Dumpters
Clean Up - During Construction - Labor | 09-0104 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000
Dumpsters | 09-0113 | S | DUMPSTERS | Allowance | Unit | 363 | 79 | 0% | 79 | 28677
Clean Up - Hauling Exterior | 09-0121 | S | ON-SITE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Included in Construction Cleaning Contract.
Stucco | 09-2423 | S | BUILDING | Bruner Ave | SY | 23863.34 | 39.8368 | 0% | 39.8368 | 950639.2965 |  | Pricing from Bruner contract.
Stucco - Pump House | 09-2423S | A | PUMPHOUSE | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Stucco - Walls | 09-2424 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Area | 09-2428 | A | POOL AREA | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Stucco - Cabana | 09-2429 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Equipment | 09-2430 | S | POOL EQUIP | Pebble | LS | 1 | 5000 | 0% | 5000 | 5000
Stucco - Repairs | 09-2423A | RR | BUILDING | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Drywall | 09-2905 | S | BUILDING | West H. | SF | 362571 | 7.65 | 0% | 7.65 | 2773668.15 |  | WH Classic proposal.
Drywall - Repairs | 09-2905A | RR | BUILDING | Allowance | Unit | 363 | 85 | 0% | 85 | 30855
Drywall - Pump House | 09-2905S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Tile Tubs and Showers | 09-3001 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Common Tile | 09-3002 | S | COMMON AREA | Torrey Pines | Unit | 363 | 468.71 | 0% | 468.71 | 170141.73 |  | Based on Torrey Pines awarded proposal
Kitchen Backsplash | 09-3003 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Tile | 09-3008 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Flooring - Units | 09-6001 | S | BUILDING | Bruner | SY | 31493.6667 | 16.2966 | 0% | 16.2966 | 513238.1887 |  | Sheet Vinyl - Seamless
Common Wood | 09-6401 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common Vinyl | 09-6517 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Hall Flooring | 09-6520 | S | COMMON AREA | Torrey Pines | SF | 362571 | 0.75 | 0% | 0.75 | 271928.25 |  | Torrey Pines approved proposal
Hall Flooring - Elevators | 09-6520A | A | COMMON AREA | Allowance | Count | 6 | 750 | 0% | 750 | 4500
Common - Plank | 09-6521 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common - VCT | 09-6522 | S | COMMON AREA | N/A | SF | 0 | 0 | 0% | 0 | 0
Common - Rubber Floor (Ecore) | 09-6566 | S | COMMON AREA | Bruner | SF | 1901.9 | 19.54 | 0% | 19.54 | 37163.126 |  | Bruner proposal
Common - Carpet Stairs | 09-6802 | S | COMMON AREA | Pebble | Count | 19 | 1848.1429 | 0% | 1848.1429 | 35114.7143 |  | Pebble contracted Price (RMI) plus an additional $300)
Hall Runner Install | 09-6803 | S | COMMON AREA | Pebble | SF | 362571 | 0 | 0% | 0 | 0 |  | Based on Torrey Pines, assumption is that we are not doing hall runners (if so, $0.05 per SF)
Hall Runner Materials | 09-6804 | S | COMMON AREA | Pebble | SF | 362571 | 0 | 0% | 0 | 0 |  | Based on Torrey Pines, assumption is that we are not doing hall runners (if so, $0.30 per SF)
Painting - Repairs | 09-9101A | RR | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Painting | 09-9101 | S | BUILDING | West H. | SF | 362571 | 1.98 | 0% | 1.98 | 717890.58 |  | Classic Proposal
Painting - Pump House | 09-9101S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Painting - Walls | 09-9102 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Painting - Pool Area | 09-9106 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Wall Covering |  | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Walls - Specialty | 09-9110 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Finishes | 09 | JASON | [8 empty] | 5963501.3854
Entry Directory | 10-1300 | S | ON-SITE | N/A |  |  | 5478 | 0% | 5478 | 0
Unit Carport Signs | 10-1401 | S | CARPORT | Pebble | Unit | 363 | 212 | 0% | 212 | 76956 |  | Per Pebble budget
Site Signage | 10-1404 | S | ON-SITE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Entry Sign Letters | 10-1419 | S | ON-SITE | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Offsite Street Signs | 10-1454 | S | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Bath Accessories | 10-2816 | S | BUILDING | Pebble | Per Bathroom | 363 | 41 | 0% | 41 | 14883 |  | Per Pebble Budget
Shower Doors | 10-2919 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places | 10-3000 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places - Pool Area | 10-3200 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
BBQ Units | 10-3355 | S | POOL AREA | Arzano | LS | 4 | 3360 | 0% | 3360 | 13440
Lock Boxes | 10-4116 | S | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fire Extinguishers | 10-4416 | S | BUILDING | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 |  | Is this not included in the sprinkler contract? Yes but seperate cost code.
Mail Boxes | 10-5523 | S | BUILDING | Pebble | Unit | 363 | 230 | 0% | 230 | 83490 |  | Per Pebble Budget
Closet Shelving | 10-5723 | S | BUILDING | Bruner | Unit | 363 | 332 | 0% | 332 | 120516
Window Awnings Small | 10-7313 | S | BUILDING | Torrey Pines | Count | 30 | 2500 | 0% | 2500 | 75000
Window Awnings Large | 10-7313 | S | BUILDING | Torrey Pines | Count | 10 | 8500 | 0% | 8500 | 85000
Specialties | 10 | JASON | [8 empty] | 525785
Appliances | 11-3013 | S | BUILDING | Bruner | Unit | 363 | 3201 | 5% | 3361.05 | 1220061.15
Appliances - Laundry Room | 11-3013 | S | BUILDING | Torrey Pines | Units | 363 | 343.7053 | 0% | 343.7053 | 124765.0105 |  | Based on Torret Pines ($65k) Laundry room appliance cost per unit.
Appliances - Common | 11-3013 | S | BUILDING | Allowance | LS | 1 | 35000 | 0% | 35000 | 35000 |  | Kithcen and laundry rooms
Equipment | 11 | JASON | [8 empty] | 1379826.1605
Dumpsters | 12-0131 | S | DUMPSTERS | N/A | 0 | 0 | 0 | 0% | 0 | 0 |  | Included in Construction Cleaning Contract | [7 empty] | W.H Units | Box Count | Robin. Units | # of Units | Total Counts
Blinds | 12-2100 | S | BUILDING | Torrey Pines | Per Unit | 363 | 443 | 0% | 443 | 160809 |  | Incudes New Requirement for Cordless Blinds. | [7 empty] | A1A | 16 | 1A | 168 | 2688
Cabinets Units | 12-3531 | S | BUILDING | West H. | Boxes | 6830 | 137.8 | 0% | 137.8 | 941174 |  | Based on Thermafoil White, W.H. units (A1A, B1B, B3A, and B2C) to approximate counts. Add $150,260 if upgrading to Morning Dew ($159.80 / SF) |  |  |  |  | Counts to the side |  |  | B1B | 14 | 1B | 52 | 728
Cabinet Common Areas | 12-3535 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000 | [9 empty] | B3A | 24 | 2A | 125 | 3000
Counter Tops Units | 12-3601 | S | BUILDING | West H. | SF | 22554.56 | 24.86 | 0% | 24.86 | 560706.3616 |  | Based on Arctic White SF cost from Bruner and Takeoffs. Add $79,844 if upgrading to Carrera Trigato ($28.40 / SF) |  |  |  |  | Counts to the side |  |  | B2C | 23 | 2B | 18 | 414
Counter Tops Common Areas | 12-3605 | A | BUILDING | Allowance | LS | 1 | 65000 | 0% | 65000 | 65000 | [13 empty] | 6830
Counter Tops Pool Area | 12-3608 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Top | 12-3609 | S | POOL AREA | Allowance | LS | 4 | 6000 | 0% | 6000 | 24000
Furnishings | 12 | JASON | [8 empty] | 1826689.3616 | [8 empty] | Units | Countertop SF | # of Units | Total Counts
Pools and Spas | 13-1113 | S | POOL AREA | Bruner Proposal | LS | 1 | 290931.6667 | 0% | 290931.6667 | 290931.6667 |  | Average cost from three proposals from Bruner (California, Paragon, and Anthony & Sylvan) | [7 empty] | 1A | 55.2 | 168 | 9273.6
Carports | 13-3401 | S | CARPORT | Torrey Pines | Count | 286 | 2292 | 0% | 2292 | 655512 |  | Proposal | [7 empty] | 1B | 77.08 | 52 | 4008.16
Pool Equipment Cover | 13-3402 | S | POOL EQUIP | Decatur | Count | 1 | 7049 | 0% | 7049 | 7049 | [9 empty] | 2A | 64.88 | 125 | 8110
Special Construction | 13 | JASON | [8 empty] | 953492.6667 | [8 empty] | 2B | 64.6 | 18 | 1162.8
Trash Chute | 13-G | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Trash Chute | 13-G | [9 empty] | 0 | [11 empty] | 22554.56
Elevator | 14-2400 | S | BUILDING | West H. | Elevator | 6 | 80632.8333 | 0% | 80632.8333 | 483797 |  | West Henderson (Otis) Proposal - $10k per Bradley Roska at Otis | [5 empty] | 40316.4167
Pool and Spa Lifts | 14-4101 | S | POOL AREA | Allowance | Count | 2 | 6500 | 0% | 6500 | 13000 | [7 empty] | 80632.8333
Conveying Equipment | 14 | JASON | [8 empty] | 496797
Sprinkler Design & Permit | 21-0600 | S | BUILDING | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Sprinkler System | 21-1313 | S | BUILDING | Bruner | SF | 362571 | 2.65 | 0% | 2.65 | 960813.15 |  | SNF Proposal at Bruner.
Fire Pump | 21-3000 | S | PUMPHOUSE | Bruner | Count | 1 | 125000 | 0% | 125000 | 125000 |  | Focus Bruner proposal (2nd lowest) | [5 empty] | 0.081633
Fire Suppression | 21 | JASON | [8 empty] | 1110813.15
1 Bathroom Unit | 22-1001 | S | BUILDING | Bruner | Count | 363 | 10069 | 0% | 10069 | 3655047 |  | Bruner pricing by Focus with comventional DWV.
2 Bathroom Unit | 22-1001 | S | BUILDING | N/A | 0 | 0 | 0 | 0% | 0 | 0
Plumbing - Pump House | 22-1001S | S | PUMPHOUSE | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pool Area | 22-1003 | S | POOL AREA | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Pool Equipment | 22-1007 | S | POOL EQUIP | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Plumbing | 22 | JASON | [8 empty] | 3688547
HVAC Standard | 23-3001 | S | BUILDING | Bruner | Unit | 363 | 9845.3608 | 0% | 9845.3608 | 3573865.9794 |  | Allstate signed off proposal
HVAC - Pump House | 23-3001S | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
HVAC | 23 | JASON | [8 empty] | 3588865.9794
Electrical | 26-1001 | S | BUILDING | West H. | SF | 362571 | 10.61 | 0% | 10.61 | 3846878.31 |  | Sigma proposal.
Electrical - Pump House | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Electrical Fixtures | 26-5001 | S | BUILDING | Allowance | Unit | 363 | 700 | 0% | 700 | 254100
Building Electrical Fixtures | 26-5002 | S | BUILDING | West H. | Unit | 363 | 120 | 0% | 120 | 43560 |  | Per Unit allowance from West Henderson
Hall Lighting Fixtures | 26-5003 | S | BUILDING | West H. | Unit | 363 | 115 | 0% | 115 | 41745 |  | Per unit allowance from West Henderson
Carports Electrical | 26-1001 | S | CARPORT | West H. | Space | 286 | 200 | 0% | 200 | 57200 |  | Per unit allowance from West Henderson
Carport Fixtures | 26-5001 | S | CARPORT | Allowance | Space | 286 | 50 | 0% | 50 | 14300
Cabana Electrical | 26-1001 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Cabana Fixtures | 26-5004 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Street Lights | 26-5613 | S | Offsite | Budget | Count | 4 | 15000 | 0% | 15000 | 60000
Site Lighting Electrical | 26-1005 | S | ON-SITE | Allowance | Acre | 17.35 | 2500 | 0% | 2500 | 43375
Site Lighting Fixtures | 26-5602 | S | ON-SITE | Allowance | Acre | 17.35 | 1750 | 0% | 1750 | 30362.5
Pool Lighting Electrical | 26-1004 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Lighting Fixtures | 26-5603 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Equipment Electrical | 26-1007 | S | POOL EQUIP | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pump House Electrical | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Pump House Fixtures | 26-5001 | S | PUMPHOUSE | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Electrical | 26 | [9 empty] | 4455520.81
TV and Media | 27-2201 | A | BUILDING | Allowance | LS | 3 | 1000 | 0% | 1000 | 3000 |  | Per Building
DAS System | 27-3010 | S | BUILDING | Torrey Pines | SF | 362571 | 0.45 | 0% | 0.45 | 163156.95
Pool ADA Phone | 27-3201 | S | POOL AREA | Allowance | LS | 1 | 800 | 0% | 800 | 800 |  | Per Pool
Communications | 27 | [9 empty] | 166956.95
Security System | 28-1001 | S | BUILDING | Bruner | Unit | 363 | 551.2887 | 0% | 551.2887 | 200117.7835
Site Security System | 28-2001 | S | ON-SITE | Pebble | Mo | 24 | 5642.8571 | 0% | 5642.8571 | 135428.5714 |  | Pebble monthly cost to date.
Fire Alarm / Two Way Comm AOR | 28-4601 | S | BUILDING | Decatur | SF | 361641 | 1.94 | 0% | 1.94 | 701583.54 |  | Used Decatur because the new low frequency code expected to be adopted by Clark County as well.
Fire Alarm - Pump House | 28-4601S | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Electronic Safety & Security | 28 | [9 empty] | 1047129.8949
Construction Water | 31-0121 | S | ON-SITE | Allowance | Acre | 17.35 | 6500 | 0% | 6500 | 112775
Dust Control | 31-0122 | S | ON-SITE | Allowance | Acre | 17.35 | 3500 | 0% | 3500 | 60725
Track Out Pad / DEMO | 31-0505 | S | ON-SITE | Budget | LS | 1 | 100000 | 0% | 100000 | 100000
Rock Dirt Haul Off | 31-1492 | S | ON-SITE | Budget | LS | 1 | 50000 | 0% | 50000 | 50000
Mass Grading | 31-2201 | S | ON-SITE | Budget | LS | 1 | 1257581.3634 | 0% | 1257581.3634 | 1257581.3634
Fine Grade | 31-2216 | S | ON-SITE | Budget | LS | 1 | 52966.135 | 0% | 52966.135 | 52966.135
Hard Dig | 31-2319 | S | ON-SITE | Budget | LS | 1 | 100000 | 0% | 100000 | 100000
Dewatering | 31-2322 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Storm Water Prevention | 31-2501 | S | ON-SITE | Allowance | Acre | 17.35 | 2500 | 0% | 2500 | 43375
Earthwork | 31 | [9 empty] | 1777422.4984
Bond Repair | 32-0100 | RR | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Street Cleaning | 32-0111 | S | OTHER SITE | Allowance | LS | 2 | 2500 | 0% | 2500 | 5000
Asphalt Sawcut and Removal | 32-0506 | S | ON-SITE | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000 |  | See Budget File
Paving | 32-1216 | S | ON-SITE | Budget | LS | 1 | 601630.93 | 0% | 601630.93 | 601630.93 |  | See Budget File
Seal Coat | 32-1236 | S | ON-SITE | Allowance | SF | 215053 | 0.25 | 0% | 0.25 | 53763.25
Pavers | 32-1401 | S | OTHER SITE | Pebble | SF | 3000 | 8.5 | 0% | 8.5 | 25500 |  | Allowance
Pool Decks | 32-1402 | S | POOL AREA | Pebble | SF | 8023 | 8.5 | 0% | 8.5 | 68195.5 |  | Pool Deck
Curbs and Gutters | 32-1613 | S | ON-SITE | West H. | LS | 1 | 114991.74 | 0% | 114991.74 | 114991.74 |  | See Budget File
Tack On Curb | 32-1614 | S | ON-SITE | West H. | LS | 1 | 134729.4 | 0% | 134729.4 | 134729.4 |  | See Budget File
Concrete Flatwork | 32-1623 | S | ON-SITE | West H. | LS | 1 | 338206.8875 | 0% | 338206.8875 | 338206.8875 |  | Preliminary Plans has 5' sidewalk versus 3.5' previous budget.
Bus Pad | 32-1625 | S | OTHER SITE | N/A |  |  |  | 0% | 0 | 0
Pool Hardscape | 32-1626 | S | POOL AREA | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Street Signs / Striping | 32-1700 | S | ON-SITE | Allowance | Acre | 17.35 | 3000 | 0% | 3000 | 52050
Walls Iron | 32-3101 | S | ON-SITE | Torrey Pines | LS | 1 | 164035.4 | 0% | 164035.4 | 164035.4 |  | See Budget File
Trash Enclosure Iron Gates | 32-3103 | S | OTHER SITE | Torrey Pines | Count | 14 | 2485 | 0% | 2485 | 34790
Site Railings | 32-3104 | A | OTHER SITE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Dog Run Fence | 32-3105 | S | ON-SITE | Allowance | LF | 300 | 55 | 0% | 55 | 16500
Pool Fence | 32-3106 | S | POOL AREA | Torrey Pines | LF | 300 | 70 | 0% | 70 | 21000
Pool Fence Gates | 32-3106 | S | POOL AREA | Torrey Pines | Count | 2 | 1950 | 0% | 1950 | 3900
Entry Security Gates | 32-3111 | S | ON-SITE | Torrey Pines | LS | 1 | 6000 | 0% | 6000 | 6000 |  | Crash Gate
Entry Security Gates Electrical | 32-3112 | S | ON-SITE | N/A |  |  | 3555 | 0% | 3555 | 0
Entry Gate Transmitters | 32-3113 | S | ON-SITE | N/A |  |  | 44 | 0% | 44 | 0
Entry Gates | 32-3114 | S | ON-SITE | Budget | LS | 0 | 1950 | 0% | 1950 | 0
Temp Fencing | 32-3120 | S | ON-SITE | Allowance | LS | 17.35 | 5000 | 0% | 5000 | 86750
Walls Masonry | 32-3201 | S | ON-SITE | West H. | LS | 1 | 493481.675 | 0% | 493481.675 | 493481.675 |  | Preliminary Civil Plans
Walls Pilaster Caps | 32-3202 | S | ON-SITE | West H. | LS | 1 | 31250 | 0% | 31250 | 31250 |  | Preliminary Civil Plans
Retaining Walls | 32-3204 | S | ON-SITE | West H. | LS | 1 | 303105.8 | 0% | 303105.8 | 303105.8 |  | Preliminary Civil Plans
Pool Walls | 32-3208 | A | POOL AREA | Allowance | LS | 2 | 7500 | 0% | 7500 | 15000
Site Furniture Permanent | 32-3343 | A | BUILDING | Allowance | LS | 1 | 7000 | 0% | 7000 | 7000
Site Landscaping | 32-9001 | S | ON-SITE | West H. | SF | 316370.92 | 9 | 0% | 9 | 2847338.28 |  | West Henderson proposal with 304k lanscaping sf is under $8.50 /sf
Site Landscaping Lighting | 32-9001 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Site Landscaping Planter Pots | 32-9433 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Offsite Asphalt Sawcut and Removal | 32-0506 | S | Offsite | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Offsite Paving | 32-1216 | S | Offsite | Budget | LS | 1 | 341251.0625 | 0% | 341251.0625 | 341251.0625 |  | See Budget File.
Offsite Curbs and Gutters | 32-1613 | S | Offsite | West H. | LS | 1 | 45316 | 0% | 45316 | 45316 |  | See Budget File
Offsite Concrete Flatwork | 32-1623 | S | Offsite | West H. | LS | 1 | 25863 | 0% | 25863 | 25863 |  | See Budget File
Offsite Parvin Realignment | 32-5500 | S | Offsite | Budget | LS | 1 | 0 | 0% | 0 | 0
Exterior Improvements | 32 | [9 empty] | 5896648.925
Temp Power | 33-0501 | A |  | Allowance | Unit | 363 | 375 | 0% | 375 | 136125
Traffic Control, AC Removal and Patch | 33-1001 | A | Offsite | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Water | 33-1001 | S | ON-SITE | Budget | LS | 1 | 1292500.98 | 0% | 1292500.98 | 1292500.98
Sewer | 33-3001 | S | ON-SITE | Budget | LS | 1 | 516087 | 0% | 516087 | 516087
Storm Drain | 33-4001 | S | ON-SITE | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Sub Drains | 33-4116 | A |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Gas | 33-5001 | S | Offsite | Budget | LS | 1 | 0 | 15% | 0 | 0
Electric | 33-7101 | S |  | Budget | LS | 1 | 350575.2 | 0% | 350575.2 | 350575.2
Secondary Conduit | 33-7102 | A |  | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Bollards | 33-7103 | S |  | Allowance | LS | 1 | 15600 | 0% | 15600 | 15600
Cable TV | 33-8201 | S |  | N/A |  |  |  | 0% | 0 | 0
Phone | 33-8202 | S |  | N/A |  |  |  | 0% | 0 | 0
Off Site Water | 33-1001 | S | Offsite | Budget | LS | 1 | 387993.65 | 0% | 387993.65 | 387993.65 |  | POC on Robindale water lines.
Off Site Sewer | 33-3001 | S | Offsite | Alowance | LS | 1 | 91720 | 0% | 91720 | 91720 |  | Allowance. Per Pete POC are onsite.
Off Site Storm Drain | 33-4001 | S | Offsite | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Off Site Electric | 33-7101 | S | Offsite | Budget | LS | 1 | 61000 | 0% | 61000 | 61000
Utilities | 33 | [9 empty] | 2941601.83
Bridge |  |  | ON-SITE | Allowance | LS | 2 | 594250 | 0% | 594250 | 1188500 |  | UNchanged
Other |  |  | ON-SITE | Allowance | LS | 1 | 300000 | 0% | 300000 | 300000 |  | Current prelim plan calls for 47,604 Sf 6" concrete with 18" on center rebard. Estimated cost $600k but chosed with $300k allowance since this may change.
Brigde Over Duct Creek Wash | 33 | [9 empty] | 1488500
Traffic Control | 34-4116 | A | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Transportation | 34 | [9 empty] | 7500
Solar PV System | 48-1413 | S |  | Allowance | LS | 1 | 977434 | 0% | 977434 | 977434 |  | Unchanged
Solar PV Conduit | 48-1414 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Unchanged
Car Charging Stations | 48-1913 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Unchanged
Electrical Power Generation | 48 | [9 empty] | 1077434
Staking | 49-0601 | S |  | Pebble | LS | 17.35 | 9000 | 0% | 9000 | 156150 |  | Using Pebble Cost to Date as Benchmark.
Re Staking | 49-0602 | S |  | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Using Pebble Cost to Date as Benchmark.
Certs and Verifications | 49-0603 | S |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000 |  | Using Pebble Cost to Date as Benchmark.
Slab Testing | 49-0801 | S |  | Allowance | EAH | 3 | 15000 | 0% | 15000 | 45000 |  | Using Pebble Cost to Date as Benchmark.
Grading Testing | 49-0802 | S |  | Pebble | LS | 17.35 | 5000 | 0% | 5000 | 86750 |  | Using Pebble Cost to Date as Benchmark.
Other Testing | 49-0803 | S |  | Pebble | LS | 17.35 | 5000 | 0% | 5000 | 86750 |  | Using Pebble Cost to Date as Benchmark.
Masonry Testing | 49-0807 | S |  | Allowance | LS | 17.35 | 2500 | 0% | 2500 | 43375 |  | Using Pebble Cost to Date as Benchmark.
Pavement Testing | 49-0808 | S |  | Allowance | LS | 17.35 | 1500 | 0% | 1500 | 26025 |  | Using Pebble Cost to Date as Benchmark.
Third Party Inspections | 49-0950 | S |  | Pebble | LS | 17.35 | 2500 | 0% | 2500 | 43375 |  | Using Pebble Cost to Date as Benchmark.
Field Surveys, Staking | 49 | [9 empty] | 502425
BABA | [5 empty] | 0% |  |  |  | 0
Bid Risk | [5 empty] | 2% |  |  |  | 1110652.3645
Bid Risk & BABA | Bid Risk | [9 empty] | 1110652.3645
Golf Carts | 11-1001 | S |  | Allowance | LS | 2 | 10000 | 0% | 10000 | 20000
Convenience Store Equipment | 11-2101 | S |  | N/A |  |  |  | 0% | 0 | 0
Pet Wash | 11-2102 | S |  | N/A | LS | 0 | 21000 | 0% | 21000 | 0
Office Equipment | 11-2801 | S |  | Allowance | LS | 1 | 20000 | 0% | 20000 | 20000
Gym Exercise Equipment | 11-6613 | S |  | Decatur | SF | 1901.9 | 47.98 | 0% | 47.98 | 91253.162
Playground / Basketball Hoop | 11-6813 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 3720000
Maintenance Shop Equipment | 11-8101 | S |  | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Maintenance Shop Start Up Supplies | 11-8102 | S |  | Alowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fixed Asset Misc. | 11-8105 | S |  | N/A |  |  |  | 0% | 0 | 0
Interior Furniture | 12-5000 | S |  | Allowance | LS | 3 | 400000 | 0% | 400000 | 1200000
Exterior Furniture | 12-5483 | S |  | Allowance | LS | 3 | 100000 | 0% | 100000 | 300000
Rec Building TV Media Computer | 27-2201 | S |  | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Rec Building Telephone System | 27-3202 | S |  | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Maintenance Radios | 27-3243 | S |  | Allowance | LS | 2 | 1500 | 0% | 1500 | 3000
FFE | FFE Extra | [9 empty] | 1681753.162
Construction Contingency | 55-9800 |  |  |  |  | 5% |  |  |  | 2776630.9113
Construction Contingency | 55 | [9 empty] | 2776630.9113
Sub Bonds | 50-9950 | B |  |  |  | 1.7% |  |  |  | 944054.5098
Sub Bonds | 50 | [9 empty] | 944054.5098
GL Insurance | 50-0001 |  |  |  | 3.03 per $1,000 | 5 |  |  |  | 310163.0911
Misc. | 50-0001 |  |  |  | 5% of GL Ins. | 5% |  |  |  | 15508.1546
Umbrella | 50-0001 |  |  |  | 95% of GL Ins. | 0.95 |  |  |  | 294654.9366
GL Insurance | 50 | [9 empty] | 620326.1823
Overhead | 56 |  |  |  |  | 2% |  |  |  | 1112938.67
Contractor Fee | 56 |  |  |  |  | 6% |  |  |  | 3338816.01
OH & Contractor Fee | 56 | [9 empty] | 4451754.68
Total Hard Costs | [10 empty] | 68767993.9666
0
General Requirements | 01 |  |  | 3331957.0935 | [8 empty] | 6% General Conditions
Existing Conditions | 02 |  |  | 16000 | [8 empty] | 55532618.2252
Concrete | 03 |  |  | 2775836.1715 | [8 empty] | 3331957.0935 | 2776630.9113
Parking Garage | 03-G |  |  | #N/A | [8 empty] | 138831.5456
Masonry | 04 |  |  | 128000
Metals | 05 |  |  | 474487.5
Wood, Plastics, & Composites | 06 |  |  | 8515537.7698
Thermal & Moisture Protection | 07 |  |  | 2366346.01
Openings | 08 |  |  | 679200
Finishes | 09 |  |  | 5963501.3854
Specialties | 10 |  |  | 525785
Equipment | 11 |  |  | 1379826.1605
Furnishings | 12 |  |  | 1826689.3616
Special Construction | 13 |  |  | 953492.6667
Trash Chute | 13-G |  |  | 0
Conveying Equipment | 14 |  |  | 496797
Fire Suppression | 21 |  |  | 1110813.15
Plumbing | 22 |  |  | 3688547
HVAC | 23 |  |  | 3588865.9794
Electrical | 26 |  |  | 4455520.81
Communications | 27 |  |  | 166956.95
Electronic Safety & Security | 28 |  |  | 1047129.8949
Earthwork | 31 |  |  | 1777422.4984
Exterior Improvements | 32 |  |  | 5896648.925
Utilities | 33 |  |  | 2941601.83
Transportation | 34 |  |  | 7500
Electrical Power Generation | 48 |  |  | 1077434
Field Surveys, Staking | 49 |  |  | 502425
5th Story Factor |  |  |  | #N/A
Bid Risk |  |  |  | 0
FFE |  |  |  | 1681753.162
Construction Contingency | 55 |  |  | 0
Sub Bonds | 50 |  |  | 0
GL Insurance | 50 |  |  | 620326.1823
Contractor Fee | 56 |  |  | 0
Total Hard Costs |  |  |  | 68767993.9666
#N/A
Cost Code
Total
01 - General Requirements | 01 |  |  |  | 3331957.0935
02 - Existing Conditions | 02 |  |  |  | 16000
03 - Concrete | 03 |  |  |  | 2775836.1715
04 - Masonry | 04 |  |  |  | 128000
05 - Metals | 05 |  |  |  | 474487.5
06 - Wood, Plastics, & Composites | 06 |  |  |  | 8515537.7698
07 - Thermal & Moisture Protection | 07 |  |  |  | 2366346.01
08 - Openings | 08 |  |  |  | 679200
09 - Finishes | 09 |  |  |  | 5963501.3854
10 - Specialties | 10 |  |  |  | 525785
11 - Equipment | 11 |  |  |  | 1379826.1605
12 - Furnishings | 12 |  |  |  | 1826689.3616
13 - Special Construction | 13 |  |  |  | 953492.6667
14 - Conveying Equipment | 14 |  |  |  | 496797
21 - Fire Suppression | 21 |  |  |  | 1110813.15
22 - Plumbing | 22 |  |  |  | 3688547
23 - HVAC | 23 |  |  |  | 3588865.9794
26 - Electrical | 26 |  |  |  | 4455520.81
27 - Communications | 27 |  |  |  | 166956.95
28 - Electronic Safety & Security | 28 |  |  |  | 1047129.8949
31 - Earthwork | 31 |  |  |  | 1777422.4984
32 - Exterior Improvements | 32 |  |  |  | 5896648.925
33 - Utilities | 33 |  |  |  | 4430101.83
34 - Transportation | 34 |  |  |  | 7500
48 - Electrical Power Generation | 48 |  |  |  | 1077434
49 - Field Surveys, Staking | 49 |  |  |  | 502425
Bid Risk | Bid Risk |  |  |  | 1110652.3645
FFE Extra | FFE Extra |  |  |  | 1681753.162
50 - Sub Bonds | 50 |  |  |  | 1564380.6921
55 - Construction Contingency | 55 |  |  |  | 2776630.9113
56 - Contractor Fee | 56 |  |  |  | 4451754.68
Total |  |  |  |  | 68767993.9666
check |  |  |  |  | 0
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units | 09-6001 |  |  |  | 513238.1887 | 09
Common Wood | 09-6401 |  |  |  | 0 | 09
Common Vinyl | 09-6517 |  |  |  | 0 | 09
Hall Flooring | 09-6520 |  |  |  | 271928.25 | 09
Hall Flooring - Elevators | 09-6520A |  |  |  | 4500 | 09
Common - Plank | 09-6521 |  |  |  | 0 | 09
Common - VCT | 09-6522 |  |  |  | 0 | 09
Common - Rubber Floor | 09-6566 |  |  |  | 37163.126 | 09
Common - Carpet | 09-6802 |  |  |  | 35114.7143 | 09
Appliances | 11-3013 |  |  |  | 1379826.1605 | 11
Blinds | 12-2100 |  |  |  | 160809 | 12
Total Appliances, Flooring & Blinds |  |  |  |  | 2402579.4395
Site Work
Major Categories
Existing Conditions | 2 |  |  |  | 16000
Earthwork | 31 |  |  |  | 1777422.4984
Exterior Improvements | 32 |  |  |  | 5896648.925
Utilities | 33 |  |  |  | 4430101.83
Transportation | 34 |  |  |  | 7500
Electrical Power Generation | 48 |  |  |  | 1077434
Minor Categories
Carports | 13-3401 |  |  |  | 655512
Dumpsters | 06-0111 |  |  |  | 0
Gazebo |  |  |  |  | 0
Other Site |  |  |  |  | 0
Pools and Spas | 13-1113 |  |  |  | 290931.6667
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Pump House Concrete | 03-3101 |  |  |  | 2141443.32
Total Site Work |  |  |  |  | 16292994.2401
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  | already included in 32
Offsite Paving | 32-1216OFFSITE |  |  | already included in 32
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  | already included in 32
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  | already included in 32
Storm Drain | 33-4001OFFSITE |  |  | already included in 33
Off Site Water | 33-1001OFFSITE |  |  | already included in 33
Off Site Sewer | 33-3001OFFSITE |  |  | already included in 33
Off Site Electric | 33-7101OFFSITE |  |  | already included in 33
Traffic Control | 34-4116OFFSITE |  |  | already included in 34
Pump House Concrete | 03-3101
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  |  | 0
Offsite Paving | 32-1216OFFSITE |  |  |  | 0
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  |  | 0
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  |  | 0
Off Site Water | 33-1001OFFSITE |  |  |  | 0
Off Site Sewer | 33-3001OFFSITE |  |  |  | 0
Storm Drain | 33-4001OFFSITE |  |  |  | 0
Off Site Electric | 33-7101OFFSITE |  |  |  | 0
Traffic Control | 34-4116OFFSITE |  |  |  | 0
Other Ineligible Costs
Major Categories
Parking Garage | 03-G |  |  |  | 0
Minor Categories
Pump House Concrete | 03-3101 |  |  |  | 2141443.32
Pool Area Shower Concrete | 03-3105 |  |  |  | 23959
Cabana Concrete | 03-3107 |  |  |  | 6500
Pool Equipment Foundation | 03-3108 |  |  |  | 6500
Deck Concrete | 03-5001 |  |  |  | 45894.0515
Masonry Veneer Pool Area | 04-4305 |  |  |  | 15000
Pool Equipment Shower Stone | 04-4306 |  |  |  | 15000
Cabana Iron | 05-7004 |  |  |  | 0
Pool Equipment Gate | 05-7005 |  |  |  | 1950
Cabana Framing | 06-1109 |  |  |  | 0
BBQ Framing | 06-1110 |  |  |  | 10000
Fireplace Framing | 06-1111 |  |  |  | 0
Trellis | 06-1114 |  |  |  | 0
BBQ Trim | 06-2006 |  |  |  | 5000
Cabana Roofing | 07-3002 |  |  |  | 7500
Pump House Roofing | 07-3002 |  |  |  | 7500
Pool Equipment Windows | 08-5303 |  |  |  | 0
Pool Glass Walls | 08-8001 |  |  |  | 0
Stucco - Pump House | 09-2423 |  |  |  | 950639.2965
Stucco - Cabana | 09-2423 |  |  |  | 950639.2965
Stucco - Pool Wall | 09-2423 |  |  |  | 950639.2965
Unit Carport Signs | 10-1401 |  |  |  | 76956
Fire Places - Pool Area | 10-3200 |  |  |  | 0
BBQ Units | 10-3355 |  |  |  | 13440
BBQ Top | 12-3609 |  |  |  | 24000
Pools and Spas | 13-1113 |  |  |  | 290931.6667
Carports | 13-3401 |  |  |  | 655512
Pool Equipment Cover | 13-3402 |  |  |  | 7049
Pool and Spa Lifts | 14-4101 |  |  |  | 13000
Pool Area | 22-1003 |  |  |  | 25000
Pool Equipment | 22-1007 |  |  |  | 6000
Carports Electrical | 26-1001 |  |  |  | 3934078.31
Carport Fixtures | 26-5001 |  |  |  | 269900
Cabana Electrical | 26-1001 |  |  |  | 3934078.31
Cabana Fixtures | 26-5004 |  |  |  | 5000
Pool Lighting Electrical | 26-1004 |  |  |  | 12500
Pool Lighting Fixtures | 26-5603 |  |  |  | 12500
Pool Equipment Electrical | 26-1007 |  |  |  | 2500
Pump House Electrical | 26-1001 |  |  |  | 3934078.31
Pump House Fixtures | 26-5001 |  |  |  | 269900
Pool Decks | 32-1402 |  |  |  | 68195.5
Pool Hardscape | 32-1626 |  |  |  | 10000
Pool Fence | 32-3106 |  |  |  | 24900
Pool Walls | 32-3208 |  |  |  | 15000
Pet Wash | 11-2102 |  |  |  | 0
Office Equipment | 11-2801 |  |  |  | 20000
Gym Exercise Equipment | 11-6613 |  |  |  | 91253.162
Playground / Basketball Hoop | 11-6813 |  |  |  | 0
Rec Building TV Media Computer | 27-2201 |  |  |  | 28000
Rec Building Telephone System | 27-3202 |  |  |  | 2500

## Comparison
| Level 1.2 |  | Level 2 |  | Variance
Units |  | 363 |  | 363 |  | 0
Building Gross Square Feet |  | 329194 |  | 362571 |  | 33377
Total Cost |  | 68871987.7394 |  | 68767993.9666 |  | 103993.7728 |  |  |  |  | Studios | 0 | 0% | Southeast | 306 |  |  |  | Southeast | 19965
Cost Per Unit |  | 189729.9938 |  | 189443.5095 |  | 286.4842 |  |  |  |  | 1 Br - 1 Ba | 218 | 60.06% | More | 132 | 438 |  |  | More | 24325 | 44290
Cost Per SF |  | 189.9545 |  | 189.6677 |  | 0.28682 |  |  |  |  | 2 Br - 1 Ba | 145 | 39.94%
[11 empty] | 2 Br - 2 Ba | 0 | 0% | Building 2 & 5 |  |  | Building 4 | 112 | Building 2 & 5 |  |  | Building 4 | 29517
Description | Sub Total | Total | Sub Total | Total | Variance | % Change | Description / Details |  |  |  | Totals | 363 | 100%
General Requirement | 3338816.01 |  | 3331957.0935 |  | 6858.9165 | 0.2054%
General Requirements |  | 3338816.01 |  | 3331957.0935 | 6858.9165 | 0.2054%
Potholing | 16000 |  | 16000 |  | 0 | 0%
Existing Conditions |  | 16000 |  | 16000 | 0 | 0%
Slabs | 2130124.3359 |  | 2125443.32 |  | 4681.0159 | 0.2198%
Concrete Slab Repairs | 7500 |  | 7500 |  | 0 | 0% |  |  |  |  | Project Details
Pump House Concrete | 8500 |  | 8500 |  | 0 | 0% |  |  |  |  | Project | Robindale &215
Trash Enclosure Concrete | 70000 |  | 70000 |  | 0 | 0% |  |  |  |  | Budget Level | Level 1
Pool Area Shower Concrete | 20200 |  | 23959 |  | -3759 | -18.61% |  |  |  |  | Product | Senior
Cabana Concrete | 0 |  | 6500 |  | -6500 | 0%
Pool Equipment Foundation | 10000 |  | 6500 |  | 3500 | 35% |  |  |  |  | Timeline | 30
Lightweight Concrete | 496015.548 |  | 481539.8 |  | 14475.748 | 2.918% | Updated take off |  |  |  | Floors | 2
Deck Concrete | 43318 |  | 45894.0515 |  | -2576.0515 | -5.947% |  |  |  |  | Bldg. SF | 362571
Concrete |  | 2785657.8839 |  | 2775836.1715 | 9821.7124 | 0.3526% |  |  |  |  | Acres | 17.35
Elevator Shaft | 138000 |  | 0 |  | 138000 | 100% | Eliminated CMU shaft for framing. |  |  |  | Site SF | 755766
Trash Enclosure | 102200 |  | 98000 |  | 4200 | 4.11% |  |  |  |  | Buildings | 3
Masonry Veneer Pool Area | 5000 |  | 15000 |  | -10000 | -200%
Pool Eq. Shower | 10000 |  | 15000 |  | -5000 | -50%
Masonry |  | 255200 |  | 128000 | 127200 | 49.84%
Structural Steel | 150000 |  | 150000 |  | 0 | 0%
Elevator Shaft Iron | 24540 |  | 25500 |  | -960 | -3.912%
Stair Handrails | 45000 |  | 57000 |  | -12000 | -26.67%
Pool Equipment Gate | 1950 |  | 1950 |  | 0 | 0%
Iron Railings | 238464 |  | 240037.5 |  | -1573.5 | -0.6598%
Cable Railings | 0 |  | 0 |  | 0 | n/a
Metals |  | 459954 |  | 474487.5 | -14533.5 | -3.16%
Framing | 6772826.28 |  | 6772826.28 |  | 0 | 0%
Framing Pump House | 11208 |  | 11208 |  | 0 | 0%
Framing - Crane | 0 |  | 0 |  | 0 | n/a
Cabana Framing | 0 |  | 0 |  | 0 | n/a
BBQ Framing | 10000 |  | 10000 |  | 0 | 0%
Fireplace Framing | 0 |  | 0 |  | 0 | n/a
Trellis | 0 |  | 0 |  | 0 | n/a
Pool Equipment Framing | 0 |  | 0 |  | 0 | n/a
Finish Carpentry - Units | 1125300 |  | 1281767.3538 |  | -156467.3538 | -13.9% | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies.
Finish Carpentry - Common | 398828.1 |  | 430736.136 |  | -31908.036 | -8% | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies. |  |  | 920930.34
Finish Carpentry - Pump House | 4000 |  | 4000 |  | 0 | 0% |  |  |  | 906427.5
BBQ Trim | 5000 |  | 5000 |  | 0 | 0% |  |  |  | -14502.84
Shutters | 0 |  | 0 |  | 0 | n/a
Wood, Plastics, & Composites |  | 8327162.38 |  | 8515537.7698 | -188375.3898 | -2.262% |  |  |  | 2.33
Insulation | 906427.5 |  | 906427.5 |  | 0 | 0% |  |  |  | 2.59
Insulation - PH | 2000 |  | 2000 |  | 0 | 0% |  |  |  | 2.7
Roofing | 1071280.2123 |  | 1277484.28 |  | -206204.0677 | -19.25% | New takeoff based on 50% DD yielded 366 more squares (added parapet walls to take off).
Roofing - PH | 10000 |  | 10000 |  | 0 | 0%
Cabana Roofing | 0 |  | 0 |  | 0 | n/a
Pump House Roofing | 7500 |  | 7500 |  | 0 | 0%
Pool Equipment Roofing | 7500 |  | 7500 |  | 0 | 0%
Trash Enclosure Cover | 81200 |  | 84000 |  | -2800 | -3.448%
Pigeon Proofing | 29005.68 |  | 29005.68 |  | 0 | 0%
Gutters and Downspouts | 18128.55 |  | 18128.55 |  | 0 | 0%
Roof Ladders | 9300 |  | 9300 |  | 0 | 0%
Roof Access Doors | 15000 |  | 15000 |  | 0 | 0%
Roof Winch | 0 |  | 0 |  | 0 | n/a
Thermal & Moisture Protection |  | 2157341.9423 |  | 2366346.01 | -209004.0677 | -9.688%
Entry Doors | 8000 |  | 24000 |  | -16000 | -200%
Common Doors | 0 |  | 0 |  | 0 | n/a
Pocket Doors - 3 Panel | 0 |  | 0 |  | 0 | n/a
Garage Doors | 0 |  | 0 |  | 0 | n/a
Windows and Sliding Glass Doors | 501303 |  | 562650 |  | -61347 | -12.24% | Contempo W. Henderson proposal plus $100 /unit for frontage windows.
Windows Repair and Replacement | 27225 |  | 27225 |  | 0 | 0%
Pool Equipment Windows | 0 |  | 0 |  | 0 | n/a
Pool Glass Walls | 0 |  | 0 |  | 0 | n/a
Fixed Glass | 0 |  | 0 |  | 0 | n/a
Mirrors - LED | 0 |  | 0 |  | 0 | n/a
Mirrors - LED Install | 0 |  | 0 |  | 0 | n/a
Mirrors - Framed | 0 |  | 0 |  | 0 | n/a
Mirrors - Polished Edges (Units) | 59895 |  | 63525 |  | -3630 | -6.061%
Mirrors - Polished Edges (Restrooms) | 1500 |  | 1800 |  | -300 | -20%
Openings |  | 597923 |  | 679200 | -81277 | -13.59%
Cost Prep Labor | 0 |  | 0 |  | 0 | #DIV/0!
Cost Prep Mat - Home Depot | 10000 |  | 10000 |  | 0 | 0%
Clean Up - Final | 308185.35 |  | 308185.35 |  | 0 | 0%
Clean Up - During Construction - Labor | 75000 |  | 75000 |  | 0 | 0%
Dumpsters | 28677 |  | 28677 |  | 0 | 0%
Clean Up - Hauling Exterior | 10000 |  | 10000 |  | 0 | 0%
Stucco | 842819.6111 |  | 950639.2965 |  | -107819.6853 | -12.79% | New take off based on 50% DD tielded 3k SY more than previous.
Stucco - Pump House | 6000 |  | 6000 |  | 0 | 0%
Stucco - Walls | 0 |  | 0 |  | 0 | n/a
Stucco - Pool Area | 2000 |  | 2000 |  | 0 | 0%
Stucco - Cabana | 0 |  | 0 |  | 0 | n/a
Stucco - Pool Equipment | 5000 |  | 5000 |  | 0 | 0% |  |  |  | 2875188.03
Stucco - Repairs | 1500 |  | 1500 |  | 0 | 0% |  |  |  | 2773668.15
Drywall | 2791796.7 |  | 2773668.15 |  | 18128.55 | 0.6494% |  |  |  | -101519.88
Drywall - Repairs | 30855 |  | 30855 |  | 0 | 0%
Drywall - Pump House | 1000 |  | 1000 |  | 0 | 0%
Tile Tubs and Showers | 0 |  | 0 |  | 0 | n/a
Common Tile | 75000 |  | 170141.73 |  | -95141.73 | -126.9% | Increase as an allowance per building.
Kitchen Backsplash | 0 |  | 0 |  | 0 | n/a
Cabana Tile | 0 |  | 0 |  | 0 | n/a
Flooring - Units | 538541.7 |  | 513238.1887 |  | 25303.5113 | 4.699%
Common Wood | 0 |  | 0 |  | 0 | 0%
Common Vinyl | 0 |  | 0 |  | 0 | 0%
Hall Flooring | 170408.37 |  | 271928.25 |  | -101519.88 | -59.57% | Updated pricing to Torrey Pines contract versus previous budget using Pebble.
Hall Flooring - Elevators | 4500 |  | 4500 |  | 0 | 0%
Common - Plank | 0 |  | 0 |  | 0 | 0%
Common - VCT | 0 |  | 0 |  | 0 | 0%
Common - Rubber Floor (Ecore) | 0 |  | 37163.126 |  | -37163.126 | 0%
Common - Carpet Stairs | 33266.5714 |  | 35114.7143 |  | -1848.1429 | -5.556%
Hall Runner Install | 18566.9248 |  | 0 |  | 18566.9248 | 100% | Deleted hallway runners in latest plans.
Hall Runner Materials | 107683.4373 |  | 0 |  | 107683.4373 | 100% | Deleted hallway runners in latest plans.
Painting - Repairs | 10000 |  | 10000 |  | 0 | 0%
Painting | 572862.18 |  | 717890.58 |  | -145028.4 | -25.32% | Based on West Henderson Paint proposal by Classic.
Painting - Pump House | 1000 |  | 1000 |  | 0 | 0%
Painting - Walls | 0 |  | 0 |  | 0 | n/a
Painting - Pool Area | 0 |  | 0 |  | 0 | n/a
Wall Covering | 0 |  | 0 |  | 0 | n/a
Walls - Specialty | 0 |  | 0 |  | 0 | n/a
Finishes |  | 5644662.8447 |  | 5963501.3854 | -318838.5408 | -5.648%
Entry Directory | 0 |  | 0 |  | 0 | n/a
Unit Carport Signs | 56265 |  | 76956 |  | -20691 | -36.77%
Site Signage | 7500 |  | 7500 |  | 0 | 0%
Entry Sign Letters | 6500 |  | 6500 |  | 0 | 0%
Offsite Street Signs | 7500 |  | 7500 |  | 0 | 0%
Bath Accessories | 6171 |  | 14883 |  | -8712 | -141.2%
Shower Doors | 0 |  | 0 |  | 0 | n/a
Fire Places | 0 |  | 0 |  | 0 | n/a
Fire Places - Pool Area | 0 |  | 0 |  | 0 | n/a
BBQ Units | 13440 |  | 13440 |  | 0 | 0%
Lock Boxes | 5000 |  | 5000 |  | 0 | 0%
Fire Extinguishers | 30000 |  | 30000 |  | 0 | 0%
Mail Boxes | 55539 |  | 83490 |  | -27951 | -50.33%
Closet Shelving | 120516 |  | 120516 |  | 0 | 0%
Window Awnings Small | 75000 |  | 75000 |  | 0 | 0%
Window Awnings Large | 85000 |  | 85000 |  | 0 | 0%
Specialties |  | 468431 |  | 525785 | -57354 | -12.24%
Appliances | 1009140 |  | 1220061.15 |  | -210921.15 | -20.9% | Updated to Torrrey Pines cost / unit verus Decatur.
Appliances - Laundry Room | 124765.0105 |  | 124765.0105 |  | 0 | 0%
Appliances - Common | 35000 |  | 35000 |  | 0 | 0%
Equipment |  | 1168905.0105 |  | 1379826.1605 | -210921.15 | -18.04%
Dumpsters | 0 |  | 0 |  | 0 | 0%
Blinds | 160809 |  | 160809 |  | 0 | 0%
Cabinets Units | 1143813 |  | 941174 |  | 202639 | 17.72% | Using Thermafoil White, W.H. units. Add $150,260 if upgrading to Morning Dew ($159.80 / SF)
Cabinet Common Areas | 75000 |  | 75000 |  | 0 | 0%
Counter Tops Units | 591327 |  | 560706.3616 |  | 30620.6384 | 5.178%
Counter Tops Common Areas | 65000 |  | 65000 |  | 0 | 0%
Counter Tops Pool Area | 0 |  | 0 |  | 0 | n/a
BBQ Top | 24000 |  | 24000 |  | 0 | 0%
Furnishings |  | 2059949 |  | 1826689.3616 | 233259.6384 | 11.32%
Pools and Spas | 245000 |  | 290931.6667 |  | -45931.6667 | -18.75%
Carports | 655512 |  | 655512 |  | 0 | 0%
Pool Equipment Cover | 7049 |  | 7049 |  | 0 | 0%
Special Construction |  | 907561 |  | 953492.6667 | -45931.6667 | -5.061%
Trash Chute | 0 |  | 0 |  | 0 | n/a
Trash Chute |  | 0 |  | 0 | 0 | 0
Elevator | 426560 |  | 483797 |  | -57237 | -13.42% | Based on Otis discussion on estimated cost per 2-stop elevator
Pool and Spa Lifts | 13000 |  | 13000 |  | 0 | 0%
Conveying Equipment |  | 439560 |  | 496797 | -57237 | -13.02%
Sprinkler Design & Permit | 25000 |  | 25000 |  | 0 | 0%
Sprinkler System | 960813.15 |  | 960813.15 |  | 0 | 0%
Fire Pump | 125000 |  | 125000 |  | 0 | 0%
Fire Suppression |  | 1110813.15 |  | 1110813.15 | 0 | 0%
1 Bathroom Unit | 3655047 |  | 3655047 |  | 0 | 0%
2 Bathroom Unit | 0 |  | 0 |  | 0 | n/a
Plumbing - Pump House | 2500 |  | 2500 |  | 0 | 0%
Pool Area | 25000 |  | 25000 |  | 0 | 0%
Pool Equipment | 6000 |  | 6000 |  | 0 | 0%
Plumbing |  | 3688547 |  | 3688547 | 0 | 0%
HVAC Standard | 3573865.9794 |  | 3573865.9794 |  | 0 | 0%
HVAC - Pump House | 15000 |  | 15000 |  | 0 | 0%
HVAC |  | 3588865.9794 |  | 3588865.9794 | 0 | 0%
Electrical | 3651772.9827 |  | 3846878.31 |  | -195105.3273 | -5.343% | Updated to West Henderson proposal by Sigma (cost/SF).
Electrical - Pump House | 0 |  | 10000
Electrical Fixtures | 217800 |  | 254100 |  | -36300 | -16.67%
Building Electrical Fixtures | 43197 |  | 43560 |  | -363 | -0.8403%
Hall Lighting Fixtures | 40656 |  | 41745 |  | -1089 | -2.679%
Carports Electrical | 39468 |  | 57200 |  | -17732 | -44.93%
Carport Fixtures | 7150 |  | 14300 |  | -7150 | -100%
Cabana Electrical | 0 |  | 5000 |  | -5000 | n/a
Cabana Fixtures | 0 |  | 5000 |  | -5000 | n/a
Street Lights | 100000 |  | 60000 |  | 40000 | 40%
Site Lighting Electrical | 20820 |  | 43375 |  | -22555 | -108.3%
Site Lighting Fixtures | 20820 |  | 30362.5 |  | -9542.5 | -45.83%
Pool Lighting Electrical | 20000 |  | 12500 |  | 7500 | 37.5%
Pool Lighting Fixtures | 12500 |  | 12500 |  | 0 | 0%
Pool Equipment Electrical | 2500 |  | 2500 |  | 0 | 0%
Pump House Electrical | 17500 |  | 15000 |  | 2500 | 14.29%
Pump House Fixtures | 750 |  | 1500 |  | -750 | -100%
Electrical |  | 4194933.9827 |  | 4455520.81 | -260586.8273 | -6.212%
TV and Media | 3000 |  | 3000 |  | 0 | 0%
DAS System | 163156.95 |  | 163156.95 |  | 0 | 0%
Pool ADA Phone | 800 |  | 800 |  | 0 | 0%
Communications |  | 166956.95 |  | 166956.95 | 0 | 0%
Security System | 162624 |  | 200117.7835 |  | -37493.7835 | -23.06%
Site Security System | 169285.7143 |  | 135428.5714 |  | 33857.1429 | 20%
Fire Alarm / Two Way Comm AOR | 506841.6422 |  | 701583.54 |  | -194741.8978 | -38.42% | Used Decatur due to expectation that all Jurisdictions would implement new code.
Fire Alarm - Pump House | 10000 |  | 10000 |  | 0 | 0%
Electronic Safety & Security |  | 848751.3565 |  | 1047129.8949 | -198378.5385 | -23.37%
Construction Water | 112775 |  | 112775 |  | 0 | 0%
Dust Control | 60725 |  | 60725 |  | 0 | 0%
Track Out Pad / DEMO | 25000 |  | 100000 |  | -75000 | -300%
Rock Dirt Haul Off | 50000 |  | 50000 |  | 0 | 0%
Mass Grading | 1067126 |  | 1257581.3634 |  | -190455.3634 | -17.85% | Updated based on new take off and West Henderson prices. Preliminary Civils provided.
Fine Grade | 37727 |  | 52966.135 |  | -15239.135 | -40.39%
Hard Dig | 150000 |  | 100000 |  | 50000 | 33.33%
Dewatering | 0 |  | 0 |  | 0 | n/a
Storm Water Prevention | 43375 |  | 43375 |  | 0 | 0%
Earthwork |  | 1546728 |  | 1777422.4984 | -230694.4984 | -14.92%
Bond Repair | 5000 |  | 5000 |  | 0 | 0%
Street Cleaning | 5000 |  | 5000 |  | 0 | 0%
Asphalt Sawcut and Removal | 30000 |  | 25000 |  | 5000 | 16.67%
Paving | 670743 |  | 601630.93 |  | 69112.07 | 10.3%
Seal Coat | 53763.25 |  | 53763.25 |  | 0 | 0%
Pavers | 25500 |  | 25500 |  | 0 | 0%
Pool Decks | 68195.5 |  | 68195.5 |  | 0 | 0%
Curbs and Gutters | 112240 |  | 114991.74 |  | -2751.74 | -2.452%
Tack On Curb | 140670 |  | 134729.4 |  | 5940.6 | 4.223%
Concrete Flatwork | 273468 |  | 338206.8875 |  | -64738.8875 | -23.67% | Updated take off based on preliminary site plan by Engeneer. Preliminary Civils provided.
Bus Pad | 0 |  | 0 |  | 0 | n/a
Pool Hardscape | 10000 |  | 10000 |  | 0 | 0%
Street Signs / Striping | 52050 |  | 52050 |  | 0 | 0%
Walls Iron | 91085 |  | 164035.4 |  | -72950.4 | -80.09% | Updated take off based on preliminary site plan by Engeneer. Preliminary Civils provided.
Trash Enclosure Iron Gates | 34790 |  | 34790 |  | 0 | 0%
Site Railings | 15000 |  | 15000 |  | 0 | 0%
Dog Run Fence | 22500 |  | 16500 |  | 6000 | 26.67%
Pool Fence | 27900 |  | 21000 |  | 6900 | 24.73%
Pool Fence Gates | 3900 |  | 3900 |  | 0 | 0%
Entry Security Gates | 6000 |  | 6000 |  | 0 | 0%
Entry Security Gates Electrical | 0 |  | 0 |  | 0 | n/a
Entry Gate Transmitters | 0 |  | 0 |  | 0 | n/a
Entry Gates | 3900 |  | 0 |  | 3900 | 100%
Temp Fencing | 30000 |  | 86750 |  | -56750 | -189.2%
Walls Masonry | 376743 |  | 493481.675 |  | -116738.675 | -30.99% | Updated take off based on preliminary site plan by Engeneer. Preliminary Civils provided.
Walls Pilaster Caps | 31250 |  | 31250 |  | 0 | 0%
Retaining Walls | 331457 |  | 303105.8 |  | 28351.2 | 8.554%
Pool Walls | 15000 |  | 15000 |  | 0 | 0%
Site Furniture Permanent | 7000 |  | 7000 |  | 0 | 0%
Site Landscaping | 3976294.82 |  | 2847338.28 |  | 1128956.54 | 28.39% | Updated pricing at West Henderson increased by $0.50 / sf. Robindale assimilates WH based on project size and large open spaces.
Site Landscaping Lighting | 0 |  | 0 |  | 0 | n/a
Site Landscaping Planter Pots | 0 |  | 0 |  | 0 | n/a
Offsite Asphalt Sawcut and Removal | 5000 |  | 5000 |  | 0 | 0%
Offsite Paving | 413660 |  | 341251.0625 |  | 72408.9375 | 17.5% | Civil plans shows minimal but this budget assumes the entire Robindale frontage to be paved due to poor currect conditions.
Offsite Curbs and Gutters | 32717 |  | 45316 |  | -12599 | -38.51%
Offsite Concrete Flatwork | 37000 |  | 25863 |  | 11137 | 30.1%
Offsite Parvin Realignment | 0 |  | 0 |  | 0 | n/a
Exterior Improvements |  | 6907826.57 |  | 5896648.925 | 1011177.645 | 14.64%
Temp Power | 136125 |  | 136125 |  | 0 | 0% |  |  | 136125 | 0
Traffic Control, AC Removal and Patch | 10000 |  | 10000 |  | 0 | 0% |  |  | 10000 | 0
Water | 1306636 |  | 1292500.98 |  | 14135.02 | 1.082% |  |  | 1306636 | 0
Sewer | 823398 |  | 516087 |  | 307311 | 37.32% | Updated based on preliminary civil plans and WH pricing. |  | 823398 | 0
Storm Drain | 50000 |  | 25000 |  | 25000 | 50% |  |  | 50000 | 0
Sub Drains | 5000 |  | 5000 |  | 0 | 0% |  |  | 5000 | 0
Gas | 0 |  | 0 |  | 0 | n/a |  |  | 0 | 0
Electric | 452076 |  | 350575.2 |  | 101500.8 | 22.45% | Updated designed prepared by estimating team. |  | 452076 | 0
Secondary Conduit | 0 |  | 25000 |  | -25000 | n/a |  |  | 0 | 0
Bollards | 15600 |  | 15600 |  | 0 | 0% |  |  | 15600 | 0
Cable TV | 0 |  | 0 |  | 0 | n/a |  |  | 0 | 0
Phone | 0 |  | 0 |  | 0 | n/a |  |  | 0 | 0
Off Site Water | 345550 |  | 387993.65 |  | -42443.65 | -12.28% | Updated based on preliminary civil plans and WH pricing. |  | 345550 | 0
Off Site Sewer | 75000 |  | 91720 |  | -16720 | -22.29% | Updated based on preliminary civil plans and WH pricing. |  | 75000 | 0
Off Site Storm Drain | 25000 |  | 25000 |  | 0 | 0% |  |  | 25000 | 0
Off Site Electric | 61000 |  | 61000 |  | 0 | 0% |  |  | 61000 | 0
Utilities |  | 3305385 |  | 2941601.83 | 363783.17 | 11.01%
Bridge | 1188500 |  | 1188500 |  | 0 | 0%
Other | 100000 |  | 300000 |  | -200000 | -200%
Brigde Over Duct Creek Wash |  | 1288500 |  | 1488500 | -200000 | -15.52%
Traffic Control | 7500 |  | 7500 |  | 0 | 0%
Transportation |  | 7500 |  | 7500 | 0 | 0%
Solar PV System | 977434 |  | 977434 |  | 0 | 0%
Solar PV Conduit | 50000 |  | 50000 |  | 0 | 0%
Car Charging Stations | 50000 |  | 50000 |  | 0 | 0%
Electrical Power Generation |  | 1077434 |  | 1077434 | 0 | 0%
Staking | 173014.2 |  | 156150 |  | 16864.2 | 9.747%
Re Staking | 10000 |  | 10000 |  | 0 | 0%
Certs and Verifications | 5000 |  | 5000 |  | 0 | 0%
Slab Testing | 100196.25 |  | 45000 |  | 55196.25 | 55.09% | Updated allowances
Grading Testing | 130125 |  | 86750 |  | 43375 | 33.33% | Updated allowances
Other Testing | 130125 |  | 86750 |  | 43375 | 33.33% | Updated allowances
Masonry Testing | 17350 |  | 43375 |  | -26025 | -150% | Updated allowances
Pavement Testing | 17350 |  | 26025 |  | -8675 | -50% | Updated allowances
Third Party Inspections | 43375 |  | 43375 |  | 0 | 0%
Field Surveys, Staking |  | 626535.45 |  | 502425 | 124110.45 | 19.81%
BABA | 0 |  | 0 |  | 0 | n/a
Bid Risk | 1112398.67 |  | 1110652.3645 |  | 1746.3055 | 0.157%
Bid Risk & BABA |  | 1112398.67 |  | 1110652.3645 | 1746.3055 | 0.157%
Golf Carts | 10000 |  | 20000 |  | -10000 | -100%
Convenience Store Equipment | 0 |  | 0 |  | 0 | n/a
Pet Wash | 0 |  | 0 |  | 0 | 0%
Office Equipment | 25000 |  | 20000 |  | 5000 | 20%
Gym Exercise Equipment | 94648 |  | 91253.162 |  | 3394.838 | 3.587%
Playground / Basketball Hoop | 0 |  | 0 |  | 0 | n/a |  |  |  | 3720000
Maintenance Shop Equipment | 15000 |  | 15000 |  | 0 | 0%
Maintenance Shop Start Up Supplies | 5000 |  | 5000 |  | 0 | 0%
Fixed Asset Misc. | 0 |  | 0 |  | 0 | n/a
Interior Furniture | 1500000 |  | 1200000 |  | 300000 | 20% | Updated allowance.
Exterior Furniture | 300000 |  | 300000 |  | 0 | 0%
Rec Building TV Media Computer | 20000 |  | 25000 |  | -5000 | -25%
Rec Building Telephone System | 2000 |  | 2500 |  | -500 | -25%
Maintenance Radios | 1200 |  | 3000 |  | -1800 | -150%
FFE |  | 1972848 |  | 1681753.162 | 291094.838 | 14.76%
Construction Contingency | 2782346.675 |  | 2776630.9113 |  | 5715.7637 | 0.2054%
Construction Contingency |  | 2782346.675 |  | 2776630.9113 | 5715.7637 | 0.2054%
Sub Bonds | 945538.8695 |  | 944054.5098 |  | 1484.3597 | 0.157%
Sub Bonds |  | 945538.8695 |  | 944054.5098 | 1484.3597 | 0.157%
GL Insurance | 310599.6675 |  | 310163.0911 |  | 436.5764 | 0.1406%
Misc. | 15529.9834 |  | 15508.1546 |  | 21.8288 | 0.1406%
Umbrella | 295069.6841 |  | 294654.9366 |  | 414.7476 | 0.1406%
GL Insurance |  | 621199.335 |  | 620326.1823 | 873.1527 | 0.1406%
Overhead | 1112938.67 |  | 1112938.67 |  | 0 | 0%
Contractor Fee | 3338816.01 |  | 3338816.01 |  | 0 | 0%
Contractor Fee |  | 4451754.68 |  | 4451754.68 | 0 | 0%
Total Hard Costs |  | 68871987.7394 |  | 68767993.9666 | 103993.7728 | 0.151%
|  | 0 |  | 0
General Requirements | [7 empty] | 6% General Conditions
Existing Conditions | [7 empty] | 55532618.2252
Concrete | [7 empty] | 3331957.0935
Parking Garage | [7 empty] | 111065.2365
Masonry
Metals
Wood, Plastics, & Composites
Thermal & Moisture Protection
Openings
Finishes
Specialties
Equipment
Furnishings
Special Construction
Trash Chute
Conveying Equipment
Fire Suppression
Plumbing
HVAC
Electrical
Communications
Electronic Safety & Security
Earthwork
Exterior Improvements
Utilities
Transportation
Electrical Power Generation
Field Surveys, Staking
5th Story Factor
Bid Risk
FFE
Construction Contingency
Sub Bonds
GL Insurance
Contractor Fee
Total Hard Costs
01 - General Requirements
02 - Existing Conditions
03 - Concrete
04 - Masonry
05 - Metals
06 - Wood, Plastics, & Composites
07 - Thermal & Moisture Protection
08 - Openings
09 - Finishes
10 - Specialties
11 - Equipment
12 - Furnishings
13 - Special Construction
14 - Conveying Equipment
21 - Fire Suppression
22 - Plumbing
23 - HVAC
26 - Electrical
27 - Communications
28 - Electronic Safety & Security
31 - Earthwork
32 - Exterior Improvements
33 - Utilities
34 - Transportation
48 - Electrical Power Generation
49 - Field Surveys, Staking
Bid Risk
FFE Extra
50 - Sub Bonds
55 - Construction Contingency
56 - Contractor Fee
Total
check
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units
Common Wood
Common Vinyl
Hall Flooring
Hall Flooring - Elevators
Common - Plank
Common - VCT
Common - Rubber Floor
Common - Carpet
Appliances
Blinds
Total Appliances, Flooring & Blinds
Site Work
Major Categories
Existing Conditions
Earthwork
Exterior Improvements
Utilities
Transportation
Electrical Power Generation
Minor Categories
Carports
Dumpsters
Gazebo
Other Site
Pools and Spas
Offsite Street Signs
Street Lights
Pump House Concrete
Total Site Work
Offsite Asphalt Sawcut and Removal
Offsite Paving
Offsite Curbs and Gutters
Offsite Concrete Flatwork
Storm Drain
Off Site Water
Off Site Sewer
Off Site Electric
Traffic Control
Pump House Concrete
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs
Street Lights
Offsite Asphalt Sawcut and Removal
Offsite Paving
Offsite Curbs and Gutters
Offsite Concrete Flatwork
Off Site Water
Off Site Sewer
Storm Drain
Off Site Electric
Traffic Control
Other Ineligible Costs
Major Categories
Parking Garage
Minor Categories
Pump House Concrete
Pool Area Shower Concrete
Cabana Concrete
Pool Equipment Foundation
Deck Concrete
Masonry Veneer Pool Area
Pool Equipment Shower Stone
Cabana Iron
Pool Equipment Gate
Cabana Framing
BBQ Framing
Fireplace Framing
Trellis
BBQ Trim
Cabana Roofing
Pump House Roofing
Pool Equipment Windows
Pool Glass Walls
Stucco - Pump House
Stucco - Cabana
Stucco - Pool Wall
Unit Carport Signs
Fire Places - Pool Area
BBQ Units
BBQ Top
Pools and Spas
Carports
Pool Equipment Cover
Pool and Spa Lifts
Pool Area
Pool Equipment
Carports Electrical
Carport Fixtures
Cabana Electrical
Cabana Fixtures
Pool Lighting Electrical
Pool Lighting Fixtures
Pool Equipment Electrical
Pump House Electrical
Pump House Fixtures
Pool Decks
Pool Hardscape
Pool Fence
Pool Walls
Pet Wash
Office Equipment
Gym Exercise Equipment
Playground / Basketball Hoop
Rec Building TV Media Computer
Rec Building Telephone System

## What Changed
ROBINDALE AND 215 - DETAILS OF BUDGET CHANGE
| Budget 1.2 |  | Budget 2 |  | Variance |  | Reason for Change
Elevator Shaft | 138000 |  | 0 |  | 138000 | 0% | Elevator Shaft to be framed, not CMU.
Masonry |  | 255200 |  | 128000 | 127200 | 49.84%
Finish Carpentry - Units | 1125300 |  | 1281767.3538 |  | -156467.3538 | 0% | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies.
Finish Carpentry - Common | 398828.1 |  | 430736.136 |  | -31908.036 | 0% | Added 10% as we have indication BFS has purchased Rystin and Doors and Millwork companies.
Wood, Plastics, & Composites |  | 8327162.38 |  | 8515537.7698 | -188375.3898 | -2.262%
Roofing | 1071280.2123 |  | 1277484.28 |  | -206204.0677 | -19.25% | New takeoff based on 50% DD yielded 366 more squares (added parapet walls to take off).
Thermal & Moisture Protection |  | 2157341.9423 |  | 2366346.01 | -209004.0677 | -9.688%
Stucco | 842819.6111 |  | 950639.2965 |  | -107819.6853 | -12.24% | New take off based on 50% DD tielded 3k SY more than previous.
Common Tile | 75000 |  | 170141.73 |  | -95141.73 | -12.24% | Increase as an allowance per building.
Hall Flooring | 170408.37 |  | 271928.25 |  | -101519.88 | -12.24% | Updated pricing to Torrey Pines contract versus previous budget using Pebble.
Hall Runner Materials | 107683.4373 |  | 0 |  | 107683.4373 | 0% | Deleted hallway runners in latest plans.
Painting | 572862.18 |  | 717890.58 |  | -145028.4 | 5.178% | Based on West Henderson Paint proposal by Classic.
Finishes |  | 2059949 |  | 1826689.3616 | 233259.6384 | 11.32%
Appliances | 1009140 |  | 1220061.15 |  | -210921.15 | 0% | Updated to Bruner and 5% for annual increase in appliance cost.
Equipment |  | 907561 |  | 953492.6667 | -45931.6667 | -5.061%
Cabinets Units | 1143813 |  | 941174 |  | 202639 | 0% | Using Thermafoil White, W.H. units. Add $150,260 if upgrading to Morning Dew ($159.80 / SF)
Furnishings |  | 2059949 |  | 1826689.3616 | 233259.6384 | -5.061%
Elevator | 426560 |  | 483797 |  | -57237 | -13.42% | Based on Otis discussion on estimated cost per 2-stop elevator
Conveying Equipment |  | 439560 |  | 496797 | -57237 | -13.02%
Electrical | 3651772.9827 |  | 3846878.31 |  | -195105.3273 | -5.343% | Updated to West Henderson proposal by Sigma (cost/SF).
Electrical |  | 4194933.9827 |  | 4455520.81 | -260586.8273 | -6.212%
Fire Alarm / Two Way | 506841.6422 |  | 701583.54 |  | -194741.8978 | -38.42% | Used Decatur due to expectation that all Jurisdictions would implement new code.
Electronic Safety & Security |  | 848751.3565 |  | 1047129.8949 | -198378.5385 | -23.37%
Mass Grading | 1067126 |  | 1257581.3634 |  | -190455.3634 | -17.85% | Preliminary civil shows an 50k CY export site. Increase export while decreasing hard dig and excavation based on take off.
Earthwork |  | 1546728 |  | 1777422.4984 | -230694.4984 | -14.92%
Paving | 670743 |  | 601630.93 |  | 69112.07 | 10.3% | Updated takeoff based on preliminary civil plans.
Walls Iron | 91085 |  | 164035.4 |  | -72950.4 | -80.09% | Updated takeoff based on preliminary civil plans.
Walls Masonry | 376743 |  | 493481.675 |  | -116738.675 | -30.99% | Updated takeoff based on preliminary civil plans.
Retaining Walls | 331457 |  | 303105.8 |  | 28351.2 | 8.554% | Updated takeoff based on preliminary civil plans.
Site Landscaping | 3976294.82 |  | 2847338.28 |  | 1128956.54 | 28.39% | Updated pricing at West Henderson increased by $0.50 / sf. Robindale assimilates WH based on project size and large open spaces.
Offsite Paving | 413660 |  | 341251.0625 |  | 72408.9375 | 17.5% | Civil plans shows minimal but this budget assumes the entire Robindale frontage to be paved due to poor currect conditions.
Exterior Improvements |  | 6907826.57 |  | 5896648.925 | 1011177.645 | 14.64%
Sewer | 823398 |  | 516087 |  | 307311 | 37.32% | Preliminary Civils show no lift station ($200k) and hard dig decreased by $50k. Soils show limited hard dig.
Electric | 452076 |  | 350575.2 |  | 101500.8 | 22.45% | Updated with a internal power design based on previous projects. Lowered Hard dig to $50k from $100k.
Off Site Water | 345550 |  | 387993.65 |  | -42443.65 | -12.28% | Based on preliminary civils take offs.
Off Site Sewer | 75000 |  | 91720 |  | -16720 | -22.29% | Based on preliminary civils take offs.
Utilities |  | 3305385 |  | 2941601.83 | 363783.17 | 11.01%
Interior Furniture | 1500000 |  | 1200000 |  | 300000 | 20% | Assuming Main Building approximatly $500k and $350k for each of the 2 other buidlings.
FFE |  | 1972848 |  | 1681753.162 | 291094.838 | 14.76%
Total Hard Costs |  | 68871987.7394 |  | 68767993.9666 | 103993.7728 | 0.151%

## Unit Pricing Comparison
SENIOR / AFFORABLE PROJECTS
|  | Robindale & 215 (Level 2) |  |  |  | West Henderson Level 3 | Bruner | South Nellis | Torrey Pines | Decatur | Pebble
Budget |  |  |  | Units | 363 | 380 | 194 | 50 | 190 | 276 | 195
Proposal |  |  |  | GSF | 362571 | 422635 | 196289 | 34388 | 188825 | 258464 | 184108
Contract |  |  |  | Acres | 17.35 | 15.83 | 4.9 | 1.3 | 5 | 9.45 | 5
|  |  |  | Site SF | 755766 | 689554.8 | 213444 | 56628 | 217800 | 411642 | 217800
Description | % | Cost | UOM | U | PU | PU | PU | PU | PU | PU | PU | COMMENTS ROBINDALE VS WEST HENDERSON | Recommendation for Robindale
Framing | 9.849% | 6772826.28 | SF | 362571 | 18.68 | 17.7166 | 18.68 | 20.0754 | 19.9215 | 22.8885 | 19.011 | WH is ave between the 3 current proposal. | Leave as budgeted
Electrical | 5.594% | 3846878.31 | SF (Bldg) | 362571 | 10.61 | 11.33 | 10.06 | 12.5044 | 9.27 | 10.176 | 12.1343 | WH is ave between the 3 current proposal. | Increase to WH
HVAC Standard | 5.197% | 3573865.9794 | Unit | 363 | 9845.3608 | 10558.3064 | 9845.36 | 10148.68 | 9739.2737 | 10104.6739 | 9218.2513 | WH ave of 2 best proposal. 3rd is an outlier. Larger units at WH. | Increase to WH
Drywall | 4.033% | 2773668.15 | SF (Bldg) | 362571 | 7.65 | 7.6967 | 7.2941 | 7.7385 | 8.0157 | 7.3585 | 8.0768 | WH is ave between the 3 current proposal. | Leave as budgeted
1 Bathroom Unit | 5.315% | 3655047 | 1 Bath Unit | 363 | 10069 | 10250 | 10069 | 10196.24 | 10526.3105 | 11042.5145 | 10050.2103 | WH is tied to JMAC proposal. | Increase to WH
Appliances | 1.774% | 1220061.15 | Unit | 363 | 3361.05 | 3328.1895 | 3169.7043 | 3064.485 | 3144.7947 | 3454.4783 | 3201.4974 |  | Decrease to Bruner
Sprinkler System | 1.397% | 960813.15 | SF (Bldg) | 362571 | 2.65 | 2.65 | 2.65 | 3.2148 | 2.4531 | 2.94 | 2.448 |  | Leave as budgeted
Cabinets Units | 1.369% | 941174 | Unit | 363 | 2592.7658 | 3072.4615 | 4150.2474 | 1985.2 | 3778.0053 | 3705.4275 | 3113.7333 | WH has more cabinet boxes due to extra bathrooms (increase/unit) | Leave as budgeted
Windows and Sliding Glass Doors | 0.8182% | 562650 | Unit | 363 | 1550 | 1400 | 1335.866 | 1300.6084 | 1157.8947 | 1408.8261 | 739.2714 |  | Leave as budgeted
Finish Carpentry - Units | 1.864% | 1281767.3538 | Unit | 363 | 3531.0395 | 3002.6901 | 2607.1546 | 2710.9005 | 3210.0359 | 2983.3587 | 3081.2324 | Budgeted basd on WH proposal per liavable SF | Decrese to WH $/SF
Slabs | 3.091% | 2125443.32 | SF (Slab) | 177268 | 11.99 | 9.5 | 11.11 | 16.7788 | 11.99 | 15.8829 | 16.0609 | WH has low outlier proposal. | Leave as budgeted
Insulation | 1.318% | 906427.5 | SF (Bldg) | 362571 | 2.5 | 2.3795 | 2.5 | 2.5423 | 2.6984 | 2.2715 | 2.5011 |  | Leave as budgeted
Fire Alarm / Two Way Comm AOR | 1.02% | 701583.54 | SF (Bldg) | 362571 | 1.935 | 2.25 | 1.335 | 1.9774 | 1.6733 | 1.94 | 1.5534 | Henderson has signicant higher permit fees | Leave as budgeted
Site Landscaping | 4.14% | 2847338.28 | Site SF | 316370.92 | 9 | 7.5062 | 13.6814 | 10.5 | 12.0076 | 13.4837 | 21.389 | Selected a budget cost/SF in between WH and Bruner. | Leave as budgeted
Stucco | 1.382% | 950639.2965 | SY (Bldg) | 23863.34 | 39.8368 | 39.3114 | 39.8368 | 39.371 | 40.8187 | 42.2347 | 46.6884 |  | Leave as budgeted
Counter Tops Units | 0.8154% | 560706.3616 | Unit | 363 | 1544.6456 | 2157.06 | 1868.4433 | 1100 | 1724 | 1551.7283 | 1600.2513 | WH has more countertops with secondary bathrooms. | Increase to Bruner
Lightweight Concrete | 0.7002% | 481539.8 | LW SF | 171978.5 | 2.8 | 2.6 | 2.8 | 2.9324 | 2.9421 | 1.2966 | 1.1 |  | Leave as budgeted
Pools and Spas | 0.4231% | 290931.6667 | LS | 1 | 290931.6667 | 253813.3333 | 249085 | N/A | 245000 | 228710 | 208310 | Budgeted in the event a second spa is designed. | Leave as budgeted
Painting | 1.044% | 717890.58 | SF (Bldg) | 362571 | 1.98 | 1.92 | 1.58 | 2.0534 | 1.8371 | 2.0979 | 1.932 |  | Leave as budgeted
Roofing | 1.858% | 1277484.28 | Square | 2143.43 | 596 | 573 | 596 | 491.3969 | 603.3984 | 598.3865 | 535.7424 |  | Leave as budgeted
Fire Pump | 0.1818% | 125000 | LS | 1 | 125000 | 160560 | 103700 | N/A | 133300 | 160560 | 120800 |  | Leave as budgeted
Total Hard Costs (Level 2) |  | 68767993.9666 | GSF | 362571 | 189.6677
Total Hard Costs (Level 2.1) |  | 68005168.6858
Variance |  | 762825.2808

## Division Comparison
Project Details | Level 1.2 | Level 2 | Variance
No Units | 363 | 363 | 0
1 Br - 1 Ba | 218 | 218 | 0
2 Br - 1 Ba | 145 | 145 | 0
Parking Spaces | 457 | 457 | 0
Building SF | 362571 | 362571 | 0 | 0%
Building Efficiency | 78.18% | 78.18% | 0%
Total Cost | 68871987.7394 | 68767993.9666 | 103993.7728
Cost Per SF | 189.9545 | 189.6677 | 0
Cost Per Unit | 189729.9938 | 189443.5095 | 0
5%
Description | Level 1.2 | Level 2 | Variance | % Change | Description / Details
General Requirements | 3338816.01 | 3331957.0935 | 6858.9165 | 0.2054%
Existing Conditions | 16000 | 16000 | 0 | 0%
Concrete | 2785657.8839 | 2775836.1715 | 9821.7124 | 0.3526%
Masonry | 255200 | 128000 | 127200 | 49.84%
Metals | 459954 | 474487.5 | -14533.5 | -3.16%
Wood, Plastics, & Composites | 8327162.38 | 8515537.7698 | -188375.3898 | -2.262%
Thermal & Moisture Protection | 2157341.9423 | 2366346.01 | -209004.0677 | -9.688%
Openings | 597923 | 679200 | -81277 | -13.59%
Finishes | 5644662.8447 | 5963501.3854 | -318838.5408 | -5.648%
Specialties | 468431 | 525785 | -57354 | -12.24%
Equipment | 1168905.0105 | 1379826.1605 | -210921.15 | -18.04%
Furnishings | 2059949 | 1826689.3616 | 233259.6384 | 11.32%
Special Construction | 907561 | 953492.6667 | -45931.6667 | -5.061%
Trash Chute | 0 | 0 | 0 | 0%
Conveying Equipment | 439560 | 496797 | -57237 | -13.02%
Fire Suppression | 1110813.15 | 1110813.15 | 0 | 0%
Plumbing | 3688547 | 3688547 | 0 | 0%
HVAC | 3588865.9794 | 3588865.9794 | 0 | 0%
Electrical | 4194933.9827 | 4455520.81 | -260586.8273 | -6.212%
Communications | 166956.95 | 166956.95 | 0 | 0%
Electronic Safety & Security | 848751.3565 | 1047129.8949 | -198378.5385 | -23.37%
Earthwork | 1546728 | 1777422.4984 | -230694.4984 | -14.92%
Exterior Improvements | 6907826.57 | 5896648.925 | 1011177.645 | 14.64%
Utilities | 3305385 | 2941601.83 | 363783.17 | 11.01%
Bridge | 1288500 | 1488500 | -200000 | -15.52%
Transportation | 7500 | 7500 | 0 | 0%
Electrical Power Generation | 1077434 | 1077434 | 0 | 0%
Field Surveys, Staking | 626535.45 | 502425 | 124110.45 | 19.81%
Bid Risk | 1112398.67 | 1110652.3645 | 1746.3055 | 0.157%
FFE | 1972848 | 1681753.162 | 291094.838 | 14.76%
Construction Contingency | 2782346.675 | 2776630.9113 | 5715.7637 | 0.2054%
Sub Bonds | 945538.8695 | 944054.5098 | 1484.3597 | 0.157%
GL Insurance | 621199.335 | 620326.1823 | 873.1527 | 0.1406%
OH & Contractor Fee | 4451754.68 | 4451754.68 | 0 | 0%
Total Hard Cost | 68871987.7394 | 68767993.9666 | 103993.7728

## Comparison to Projects
| TOTAL BUDGET |  |  |  |  | TOTAL BUDGET PER UNIT | [6 empty] | Variance Per Unit
[6 empty] | 363 | 190 | 276 | 208 | 195 |  |  | 190 | 276 | 208 | 195
Hard Cost Divisions | Robindale | Torrey Pines | Decatur | Russell IV | Pebble | Robindale | Torrey Pines | Decatur | Russell IV | Pebble | AVE | Var to Comp | Torrey Pines | Decatur | Russell IV | Pebble
Existing Conditions | 16000 | 3500 | 3500 | 1625 | 4640 | 44.0771 | 18.4211 | 12.6812 | 7.8125 | 23.7949 | 15.6774 | -28.3997 | 25.6561 | 31.396 | 36.2646 | 20.2823
Concrete | 2775836.1715 | 855751.3 | 2000752.3424 | 872411 | 923880.71 | 7646.9316 | 4503.9542 | 7249.1027 | 4194.2837 | 4737.8498 | 5171.2976 | -2475.634 | 3142.9774 | 397.8289 | 3452.6479 | 2909.0818
Masonry | 128000 | 154110 | 177000 | 172404.61 | 113987.04 | 352.6171 | 811.1053 | 641.3043 | 828.8683 | 584.5489 | 716.4567 | 363.8396 | -458.4882 | -288.6873 | -476.2512 | -231.9318
Metals | 474487.5 | 288724 | 318241 | 282542 | 293620 | 1307.1281 | 1519.6 | 1153.0471 | 1358.375 | 1505.7436 | 1384.1914 | 77.0633 | -212.4719 | 154.081 | -51.2469 | -198.6155
Wood, Plastics, & Composites | 8515537.7698 | 4782473.5 | 7142611.9221 | 5373532.57 | 4318539.14 | 23458.7817 | 25170.9132 | 25879.0287 | 25834.2912 | 22146.3546 | 24757.6469 | 1298.8652 | -1712.1314 | -2420.247 | -2375.5095 | 1312.4272
Thermal & Moisture Protection | 2366346.01 | 886843.75 | 1514404.5 | 925801 | 815319.47 | 6518.8595 | 4667.5987 | 5486.9728 | 4450.9663 | 4181.1255 | 4696.6658 | -1822.1937 | 1851.2608 | 1031.8867 | 2067.8932 | 2337.734
Openings | 679200 | 462292.91 | 695411 | 448928.79 | 404995.16 | 1871.0744 | 2433.1206 | 2519.6051 | 2158.3115 | 2076.8983 | 2296.9838 | 425.9095 | -562.0462 | -648.5307 | -287.2371 | -205.8239
Finishes | 5963501.3854 | 3275902.94 | 4733364.5184 | 3225416.68 | 2994978.87 | 16428.3785 | 17241.5944 | 17149.8714 | 15506.811 | 15358.866 | 16314.2857 | -114.0928 | -813.2159 | -721.493 | 921.5675 | 1069.5125
Specialties | 525785 | 207648 | 271520.3513 | 177129.21 | 183305.17 | 1448.4435 | 1092.8842 | 983.7694 | 851.5827 | 940.0265 | 967.0657 | -481.3778 | 355.5593 | 464.6741 | 596.8608 | 508.417
Equipment | 1379826.1605 | 555940 | 838575.4 | 586774 | 619814 | 3801.174 | 2926 | 3038.3167 | 2821.0288 | 3178.5333 | 2990.9697 | -810.2043 | 875.174 | 762.8573 | 980.1451 | 622.6407
Furnishings | 1826689.3616 | 1126769 | 1462590.07 | 1141152.82 | 1036514.13 | 5032.2021 | 5930.3632 | 5299.2394 | 5486.3116 | 5315.4571 | 5507.8428 | 475.6407 | -898.1611 | -267.0373 | -454.1095 | -283.255
Special Construction | 953492.6667 | 514455.07 | 731169 | 488086 | 456527 | 2626.7016 | 2707.6583 | 2649.163 | 2346.5673 | 2341.1641 | 2511.1382 | -115.5634 | -80.9567 | -22.4615 | 280.1343 | 285.5375
Conveying Equipment | 496797 | 337555 | 501480 | 572503 | 321100 | 1368.5868 | 1776.6053 | 1816.9565 | 2752.4183 | 1646.6667 | 1998.1617 | 629.5749 | -408.0185 | -448.3697 | -1383.8315 | -278.0799
Fire Suppression | 1110813.15 | 661214.75 | 877427.94 | 565239 | 729173.6 | 3060.0913 | 3480.0776 | 3179.0867 | 2717.4952 | 3739.3518 | 3279.0028 | 218.9115 | -419.9863 | -118.9954 | 342.5961 | -679.2605
Plumbing | 3688547 | 2166278.5 | 2970301.9 | 2502732 | 1962617 | 10161.2865 | 11401.4658 | 10761.9634 | 12032.3654 | 10064.7026 | 11065.1243 | 903.8378 | -1240.1793 | -600.6769 | -1871.0789 | 96.5839
HVAC | 3588865.9794 | 1751619.5 | 2852260.2 | 2193825 | 1799105 | 9886.6831 | 9219.05 | 10334.2761 | 10547.2356 | 9226.1795 | 9831.6853 | -54.9979 | 667.6331 | -447.5929 | -660.5524 | 660.5037
Electrical | 4455520.81 | 2257308 | 3362672.25 | 2387312.5 | 2151632.7 | 12274.162 | 11880.5684 | 12183.5951 | 11477.4639 | 11034.0138 | 11643.9103 | -630.2517 | 393.5936 | 90.5669 | 796.6981 | 1240.1482
Communications | 166956.95 | 900 | 1000 | 0 | 0 | 459.9365 | 4.7368 | 3.6232 | 0 | 0 | 2.09 | -457.8465 | 455.1997 | 456.3133 | 459.9365 | 459.9365
Electronic Safety & Security | 1047129.8949 | 464996.5 | 574065.07 | 697535 | 437564.8 | 2884.6554 | 2447.35 | 2079.9459 | 3353.5337 | 2243.9221 | 2531.1879 | -353.4675 | 437.3054 | 804.7095 | -468.8783 | 640.7333
Earthwork | 1777422.4984 | 609629.75 | 854419.7619 | 326803 | 361123.31 | 4896.4807 | 3208.5776 | 3095.7238 | 1571.1683 | 1851.9144 | 2431.846 | -2464.6347 | 1687.9031 | 1800.7569 | 3325.3124 | 3044.5663
Exterior Improvements | 5896648.925 | 2186782.45 | 3890600.4978 | 1626346.92 | 1854247.86 | 16244.2119 | 11509.3813 | 14096.3786 | 7818.9756 | 9508.9634 | 10733.4247 | -5510.7872 | 4734.8306 | 2147.8333 | 8425.2363 | 6735.2485
Utilities | 2941601.83 | 1788881 | 2288417.64 | 1316600.5 | 1167559.78 | 8103.5863 | 9415.1632 | 8291.3683 | 6329.8101 | 5987.4861 | 7505.9569 | -597.6294 | -1311.5768 | -187.782 | 1773.7762 | 2116.1003
Brigde Over Duct Creek Wash | 1488500 | 0 | 0 | 0 | 0 | 4100.551 | 0 | 0 | 0 | 0 | 0 | -4100.551 | 4100.551 | 4100.551 | 4100.551 | 4100.551
Transportation | 7500 | 7500 | 15000 | 0 | 15000 | 20.6612 | 39.4737 | 54.3478 | 0 | 76.9231 | 42.6861 | 22.025 | -18.8125 | -33.6867 | 20.6612 | -56.2619
Electrical Power Generation | 1077434 | 707152.38 | 178738.2 | 444320.52 | 202992.5 | 2968.1377 | 3721.8546 | 647.6022 | 2136.1563 | 1040.9872 | 1886.6501 | -1081.4877 | -753.7169 | 2320.5356 | 831.9814 | 1927.1506
Field Surveys, Staking | 502425 | 149353.1 | 440850 | 148310 | 217223.1 | 1384.0909 | 786.0689 | 1597.2826 | 713.0288 | 1113.9646 | 1052.5863 | -331.5047 | 598.022 | -213.1917 | 671.0621 | 270.1263
FFE | 1681753.162 | 1161406.5315 | 939893.043 | 926137.36 | 960082.51 | 4632.9288 | 6112.666 | 3405.4096 | 4452.5835 | 4923.5001 | 4723.5398 | 90.6109 | -1479.7371 | 1227.5192 | 180.3454 | -290.5712
Subtotal | 55532618.2252 | 27364987.9315 | 39636266.6068 | 27403468.48 | 24345542.85 | 152982.4194 | 144026.2523 | 143609.6616 | 131747.4446 | 124848.9377 | 136058.074 | -16924.3453 | 8956.1671 | 9372.7577 | 21234.9747 | 28133.4817
General Requirements | 3331957.0935
Bid Risk | 1110652.3645 |  |  |  | Slab | 177268 | 46943
Construction Contingency | 2776630.9113 |  |  |  | Slab Per Unit | 488.3416 | 247.0684
Sub Bonds | 944054.5098 | [5 empty] | 49.41%
GL Insurance | 620326.1823
Contractor Fee & OH | 4451754.68 |  |  |  | Roof | 2143.43 | 539
Total Hard Cost Budget | 68767993.9666 |  |  |  | Roof SQ Per Unit | 5.9048 | 2.8368
51.96%
[5 empty] | Acres | 17.35 | 5
[5 empty] | Unit / Acre | 20.9222 | 38

## LEVEL 1.2 BUDGET
Project Details
Project | Robindale & 215 | [7 empty] | Total Cost | 68871987.7394 |  | Unit Breakdown |  |  | Parking
Budget Level | Level 1 | [10 empty] | Unit Type | Number | % | Cover Parking | 286 |  |  |  | Railing Estimate |  |  | Building 3 | 147 | Stucco |  |  | Building 3 | 61455
Product | Senior | [7 empty] | Cost Per Unit | 189729.9938 |  | Studios | 0 | 0% | Cover Accesible Parking |  |  |  |  | Building 1 |  |  |  | 98 | Building 1
Start Date | [11 empty] | 1 Br - 1 Ba | 218 | 60.06% | Open Parking | 157 |  |  |  | Northwest | 190 |  |  | 176 | Northwest | 19256
Timeline | 30 | [7 empty] | Cost Per SF | 189.9545 |  | 2 Br - 1 Ba | 145 | 39.94% | Accessible Parking | 14 |  |  |  | Southwest | 146 |  |  | 70 | Southwest | 8980
Floors | 2 | [10 empty] | 2 Br - 2 Ba | 0 | 0% | Waiver | 0 |  |  |  | Northeast | 118 |  |  | 491 | Northeast | 8850
Bldg. SF | 362571 | [7 empty] | Efficiency | 78.18% |  | 3 Br - 2 Ba | 0 | 0% | Total Parking Provided | 457 |  |  |  | Southeast | 306 |  |  |  | Southeast | 19965
Acres | 17.35 | [10 empty] | Totals | 363 | 100% | Parking Ratio | 1.259 |  |  |  | More | 132 | 892 |  |  | More | 24325 | 81376
Site SF | 755766
Buildings | 3 | [18 empty] | Building 2 & 5 |  |  | Building 4 | 112 | Building 2 & 5 |  |  | Building 4 | 29517
[20 empty] | Northwest |  |  |  | 160 | Northwest
Description | Cost Code | Cost Category | Sub job | Source | UMO | Quantity | U.P. | Escal % | Total U.P. | Sub Total | Total | Description / Details
General Requirement | 01 | S |  |  | Mo | 30 | 111293.867 | 0% | 111293.867 | 3338816.01
General Requirements | 01 | [9 empty] | 3338816.01
Potholing | 02-3213 | S | ON-SITE | Allowance |  | 1 | 16000 | 0% | 16000 | 16000
Existing Conditions | 02 | [9 empty] | 16000
Slabs | 03-3101 | S | BUILDING | Torrey Pines | SF | 177658.41 | 11.99 | 0% | 11.99 | 2130124.3359 |  | 4" over 4" slab profile.
Deepened Footings | 03-3101 | S | BUILDING | N/A |  |  |  |  | 0 | 0
Concrete Slab Repairs | 03-3101 | RR | BUILDING | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Pump House Concrete | 03-3101 | S | PUMPHOUSE | Bruner | LS | 1 | 8500 |  | 8500 | 8500
Trash Enclosure Concrete | 03-3102 | S | OTHER SITE | Bruner | EA | 14 | 5000 | 0% | 5000 | 70000
Pool Area Shower Concrete | 03-3105 | S | POOL AREA | Bruner | LS | 1 | 20200 | 0% | 20200 | 20200
Cabana Concrete | 03-3107 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Pool Equipment Foundation | 03-3108 | S | POOL EQUIP | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Lightweight Concrete | 03-3116 | S | BUILDING | Bruner | SF | 177148.41 | 2.8 | 0% | 2.8 | 496015.548 |  | Nevada Gypsum 1" with Mat.
Deck Concrete | 03-5001 | S | BUILDING | Bruner | SF | 2200 | 19.69 | 0% | 19.69 | 43318 |  | Ave between NV Gyp and Sound-Crete
Concrete | 03 | [9 empty] | 2785657.8839
Elevator Shaft | 04-2201 | S | BUILDING | Bruner | Stop | 12 | 11500 | 0% | 11500 | 138000 |  | Integrity proposal at Bruner (Desert is at $10k per stop)
Trash Enclosure | 04-2202 | S | OTHER SITE | Bruner | Count | 14 | 7300 | 0% | 7300 | 102200 |  | Integrity proposal at Bruner (Desert is at $5,600 per enclosure)
Masonry Veneer | 04-4301 | S | ON-SITE | N/A |  |  | 0 |  | 0 | 0
Masonry Veneer Pool Area | 04-4305 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Pool Eq. Shower | 04-4306 | A | POOL EQUIP | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Masonry | 04 | [9 empty] | 255200
Structural Steel | 05-1201 | S | BUILDING | Allowance | LS | 1 | 150000 | 0% | 150000 | 150000
Elevator Shaft Iron | 05-1202 | S | BUILDING | Bruner | Count | 6 | 4090 | 0% | 4090 | 24540
Stair Handrails | 05-5201 | S | BUILDING | Bruner | Flight | 18 | 2500 | 0% | 2500 | 45000
Garage Stair Railings | 05-5201 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Cabana Iron | 05-7004 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
Pool Equipment Gate | 05-7005 | S | POOL EQUIP | Torrey Pines | Count | 1 | 1950 | 0% | 1950 | 1950
Iron Railings | 05-7300 | S | BUILDING | Bruner | LF | 1648 | 92 | 0% | 92 | 238464
Cable Railings | 05-7316 | S | COMMON AREA | N/A |  |  | 0 | 0% | 0 | 0
Metals | 05 | [9 empty] | 459954
Framing | 06-1100 | S | BUILDING | Bruner | SF | 362571 | 18.68 | 0% | 18.68 | 6772826.28 |  | Focus Framing signed off proposal at Bruner.
Framing Pump House | 06-1100 | S | PUMPHOUSE | Moving Ave | SF | 600 | 18.68 | 0% | 18.68 | 11208
Framing - Crane | 06-1100 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Framing | 06-1109 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Framing | 06-1110 | S | COMMON AREA | Allowance | LS | 4 | 2500 | 0% | 2500 | 10000
Fireplace Framing | 06-1111 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Trellis | 06-1114 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Pool Equipment Framing | 06-1114 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Finish Carpentry - Units | 06-2001 | S | BUILDING | Bruner | Unit | 363 | 3100 | 0% | 3100 | 1125300 |  | Average of 3 proposals at Bruner.
Finish Carpentry - Common | 06-2001 | S | COMMON AREA | Bruner | SF | 362571 | 1.1 | 0% | 1.1 | 398828.1 |  | Comparable cost at Bruner.
Finish Carpentry - Pump House | 06-2001S | S | PUMPHOUSE | Allowance | LS | 1 | 4000 | 0% | 4000 | 4000
BBQ Trim | 06-2006 | S | COMMON AREA | Allowance | LS | 4 | 1250 | 0% | 1250 | 5000
Shutters | 06-4919 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Wood, Plastics, & Composites | 06 | [9 empty] | 8327162.38
Insulation | 07-2101 | S | BUILDING | Bruner Ave | SF | 362571 | 2.5 | 0% | 2.5 | 906427.5 |  | Red Rock proposal.
Insulation - PH | 07-2101 | S | PUMPHOUSE | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Roofing | 07-3001 | S | BUILDING | Torrey Pines | Squares | 1776.5841 | 603 | 0% | 603 | 1071280.2123
Roofing - PH | 07-3001 | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Cabana Roofing | 07-3002 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Pump House Roofing | 07-3002 | S | PUMPHOUSE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Pool Equipment Roofing | 07-3003 | S | POOL EQUIP | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Trash Enclosure Cover | 07-6101 | S | OTHER SITE | Decatur | Count | 14 | 5800 | 0% | 5800 | 81200
Pigeon Proofing | 07-7001 | S | BUILDING | Torrey Pines | SF | 362571 | 0.08 | 0% | 0.08 | 29005.68
Gutters and Downspouts | 07-7124 | S | BUILDING | Torrey Pines | SF | 362571 | 0.05 | 0% | 0.05 | 18128.55
Roof Ladders | 07-7210 | S | BUILDING | Torrey Pines | Count | 6 | 1550 | 0% | 1550 | 9300 |  | 2 Per building
Roof Access Doors | 07-7233 | S | BUILDING | Torrey Pines | Count | 6 | 2500 | 0% | 2500 | 15000 |  | 2 Per building
Roof Winch | 07-7250 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Thermal & Moisture Protection | 07 | [9 empty] | 2157341.9423
Entry Doors | 08-1001 | S | COMMON AREA | Allowance | Count | 1 | 8000 | 0% | 8000 | 8000
Common Doors | 08-1002 | S | COMMON AREA | Included |  |  |  | 0% | 0 | 0
Pocket Doors - 3 Panel | 08-1002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Garage Doors | 08-3619 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Windows and Sliding Glass Doors | 08-5301 | S | BUILDING | Bruner | Per Unit | 363 | 1381 | 0% | 1381 | 501303
Windows Repair and Replacement | 08-5301 | RR | BUILDING | Allowance | Per Unit | 363 | 75 | 0% | 75 | 27225
Pool Equipment Windows | 08-5303 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Pool Glass Walls | 08-8001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Fixed Glass | 08-8002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED Install | 08-8302 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Framed | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Polished Edges (Units) | 08-8301 | S | BUILDING | Pebble | Unit | 363 | 165 | 0% | 165 | 59895
Mirrors - Polished Edges (Restrooms) | 08-8301 | S | BUILDING | Allowance | Count | 6 | 250 | 0% | 250 | 1500
Openings | 08 | [9 empty] | 597923
Cost Prep Labor | 09-0101 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cost Prep Mat - Home Depot | 09-0102 | S | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Clean Up - Final | 09-0103 | S | BUILDING | Torrey Pines | SF | 362571 | 0.85 | 0% | 0.85 | 308185.35 |  | Includes Dumpters
Clean Up - During Construction - Labor | 09-0104 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000
Dumpsters | 09-0113 | S | DUMPSTERS | Allowance | Unit | 363 | 79 | 0% | 79 | 28677
Clean Up - Hauling Exterior | 09-0121 | S | ON-SITE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Included in Construction Cleaning Contract.
Stucco | 09-2423 | S | BUILDING | Bruner Ave | SY | 20647.2222 | 40.82 | 0% | 40.82 | 842819.6111 |  | Bruner proposal.
Stucco - Pump House | 09-2423S | A | PUMPHOUSE | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Stucco - Walls | 09-2424 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Area | 09-2428 | A | POOL AREA | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Stucco - Cabana | 09-2429 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Equipment | 09-2430 | S | POOL EQUIP | Pebble | LS | 1 | 5000 | 0% | 5000 | 5000
Stucco - Repairs | 09-2423A | RR | BUILDING | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Drywall | 09-2905 | S | BUILDING | Bruner | SF | 362571 | 7.7 | 0% | 7.7 | 2791796.7 |  | Wall Constructors proposal.
Drywall - Repairs | 09-2905A | RR | BUILDING | Allowance | Unit | 363 | 85 | 0% | 85 | 30855
Drywall - Pump House | 09-2905S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Tile Tubs and Showers | 09-3001 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Common Tile | 09-3002 | S | COMMON AREA | Pebble | LS | 1 | 75000 | 0% | 75000 | 75000
Kitchen Backsplash | 09-3003 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Tile | 09-3008 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Flooring - Units | 09-6001 | S | BUILDING | Decatur | SY | 31493.6667 | 17.1 | 0% | 17.1 | 538541.7 |  | Sheet Vinyl - Seamless
Common Wood | 09-6401 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common Vinyl | 09-6517 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Hall Flooring | 09-6520 | S | COMMON AREA | Pebble | SF | 362571 | 0.47 | 0% | 0.47 | 170408.37
Hall Flooring - Elevators | 09-6520A | A | COMMON AREA | Allowance | Count | 6 | 750 | 0% | 750 | 4500
Common - Plank | 09-6521 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common - VCT | 09-6522 | S | COMMON AREA | N/A | SF | 0 | 0 | 0% | 0 | 0
Common - Rubber Floor (Ecore) | 09-6566 | S | COMMON AREA | Pebble | SF | 0 | 16.5334 | 0% | 16.5334 | 0
Common - Carpet Stairs | 09-6802 | S | COMMON AREA | Pebble | Count | 18 | 1848.1429 | 0% | 1848.1429 | 33266.5714
Hall Runner Install | 09-6803 | S | COMMON AREA | Pebble | SF | 362571 | 0.051209 | 0% | 0.051209 | 18566.9248 |  | Assumption of 25% of corridor SF.
Hall Runner Materials | 09-6804 | S | COMMON AREA | Pebble | SF | 362571 | 0.297 | 0% | 0.297 | 107683.4373 |  | Assumption of 25% of corridor SF.
Painting - Repairs | 09-9101A | RR | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Painting | 09-9101 | S | BUILDING | Bruner | SF | 362571 | 1.58 | 0% | 1.58 | 572862.18 |  | Latest proposal by Wall Contractors
Painting - Pump House | 09-9101S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Painting - Walls | 09-9102 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Painting - Pool Area | 09-9106 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Wall Covering |  | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Walls - Specialty | 09-9110 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Finishes | 09 | [9 empty] | 5644662.8447
Entry Directory | 10-1300 | S | ON-SITE | N/A |  |  | 5478 | 0% | 5478 | 0
Unit Carport Signs | 10-1401 | S | CARPORT | Russell IV | Unit | 363 | 155 | 0% | 155 | 56265
Site Signage | 10-1404 | S | ON-SITE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Entry Sign Letters | 10-1419 | S | ON-SITE | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Offsite Street Signs | 10-1454 | S | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Bath Accessories | 10-2816 | S | BUILDING | Russell IV | Unit | 363 | 17 | 0% | 17 | 6171
Shower Doors | 10-2919 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places | 10-3000 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places - Pool Area | 10-3200 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
BBQ Units | 10-3355 | S | POOL AREA | Arzano | LS | 4 | 3360 | 0% | 3360 | 13440
Lock Boxes | 10-4116 | S | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fire Extinguishers | 10-4416 | S | BUILDING | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 |  | Is this not included in the sprinkler contract? Yes but seperate cost code.
Mail Boxes | 10-5523 | S | BUILDING | Rainbow | Unit | 363 | 153 | 0% | 153 | 55539
Closet Shelving | 10-5723 | S | BUILDING | Bruner | Unit | 363 | 332 | 0% | 332 | 120516
Window Awnings Small | 10-7313 | S | BUILDING | Torrey Pines | Count | 30 | 2500 | 0% | 2500 | 75000
Window Awnings Large | 10-7313 | S | BUILDING | Torrey Pines | Count | 10 | 8500 | 0% | 8500 | 85000
Specialties | 10 | [9 empty] | 468431
Appliances | 11-3013 | S | BUILDING | Decatur | Unit | 363 | 2780 | 0% | 2780 | 1009140
Appliances - Laundry Room | 11-3013 | S | BUILDING | Allowance | Units | 363 | 343.7053 | 0% | 343.7053 | 124765.0105 |  | Based on Torret Pines ($65k) Laundry room appliance cost per unit.
Appliances - Common | 11-3013 | S | BUILDING | Allowance | LS | 1 | 35000 | 0% | 35000 | 35000 |  | Kithcen and laundry rooms
Equipment | 11 | [9 empty] | 1168905.0105
Dumpsters | 12-0131 | S | DUMPSTERS | N/A | 0 | 0 | 0 | 0% | 0 | 0 |  | Included in Construction Cleaning Contract
Blinds | 12-2100 | S | BUILDING | Torrey Pines | Per Unit | 363 | 443 | 0% | 443 | 160809 |  | Incudes New Requirement for Cordless Blinds.
Cabinets Units | 12-3531 | S | BUILDING | Torrey Pines | Unit | 363 | 3151 | 0% | 3151 | 1143813 |  | Decatur Option 2 - Corona Elmwood Thurmofoil
Cabinet Common Areas | 12-3535 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000
Counter Tops Units | 12-3601 | S | BUILDING | Torrey Pines | Unit | 363 | 1629 | 0% | 1629 | 591327
Counter Tops Common Areas | 12-3605 | A | BUILDING | Allowance | LS | 1 | 65000 | 0% | 65000 | 65000
Counter Tops Pool Area | 12-3608 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Top | 12-3609 | S | POOL AREA | Allowance | LS | 4 | 6000 | 0% | 6000 | 24000
Furnishings | 12 | [9 empty] | 2059949
Pools and Spas | 13-1113 | S | POOL AREA | Torrey Pines | LS | 1 | 245000 | 0% | 245000 | 245000 |  | Unchanged
Carports | 13-3401 | S | CARPORT | Torrey Pines | Count | 286 | 2292 | 0% | 2292 | 655512 |  | Proposal
Pool Equipment Cover | 13-3402 | S | POOL EQUIP | Decatur | Count | 1 | 7049 | 0% | 7049 | 7049
Special Construction | 13 | [9 empty] | 907561
Trash Chute | 13-G | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Trash Chute | 13-G | [9 empty] | 0
Elevator | 14-2400 | S | BUILDING | Decatur | Stop | 12 | 35546.6667 | 0% | 35546.6667 | 426560 |  | Decatur 3 Stop Hydrolift.
Pool and Spa Lifts | 14-4101 | S | POOL AREA | Allowance | Count | 2 | 6500 | 0% | 6500 | 13000
Conveying Equipment | 14 | [9 empty] | 439560
Sprinkler Design & Permit | 21-0600 | S | BUILDING | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Sprinkler System | 21-1313 | S | BUILDING | Bruner | SF | 362571 | 2.65 | 0% | 2.65 | 960813.15 |  | SNF Proposal at Bruner.
Fire Pump | 21-3000 | S | PUMPHOUSE | Bruner | Count | 1 | 125000 | 0% | 125000 | 125000 |  | Focus Bruner proposal (2nd lowest) | [5 empty] | 0.081633
Fire Suppression | 21 | [9 empty] | 1110813.15
1 Bathroom Unit | 22-1001 | S | BUILDING | Bruner | Count | 363 | 10069 | 0% | 10069 | 3655047 |  | Bruner pricing by Focus with comventional DWV.
2 Bathroom Unit | 22-1001 | S | BUILDING | N/A | 0 | 0 | 0 | 0% | 0 | 0
Plumbing - Pump House | 22-1001S | S | PUMPHOUSE | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pool Area | 22-1003 | S | POOL AREA | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Pool Equipment | 22-1007 | S | POOL EQUIP | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Plumbing | 22 | [9 empty] | 3688547
HVAC Standard | 23-3001 | S | BUILDING | Bruner | Unit | 363 | 9845.3608 | 0% | 9845.3608 | 3573865.9794 |  | Allstate signed off proposal
HVAC - Pump House | 23-3001S | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
HVAC | 23 | [9 empty] | 3588865.9794
Electrical | 26-1001 | S | BUILDING | Bruner | SF | 362571 | 10.0719 | 0% | 10.0719 | 3651772.9827 |  | Sigma proposal.
Electrical Fixtures | 26-5001 | S | BUILDING | Pebble | Unit | 363 | 600 | 0% | 600 | 217800
Building Electrical Fixtures | 26-5002 | S | BUILDING | Russell IV | Unit | 363 | 119 | 0% | 119 | 43197
Hall Lighting Fixtures | 26-5003 | S | BUILDING | Russell IV | Unit | 363 | 112 | 0% | 112 | 40656
Carports Electrical | 26-1001 | S | CARPORT | Russell IV | Space | 286 | 138 | 0% | 138 | 39468
Carport Fixtures | 26-5001 | S | CARPORT | Allowance | Space | 286 | 25 | 0% | 25 | 7150
Cabana Electrical | 26-1001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Cabana Fixtures | 26-5004 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Street Lights | 26-5613 | S | Offsite | Budget | Count | 4 | 25000 | 0% | 25000 | 100000
Site Lighting Electrical | 26-1005 | S | ON-SITE | Allowance | Acre | 17.35 | 1200 | 0% | 1200 | 20820
Site Lighting Fixtures | 26-5602 | S | ON-SITE | Allowance | Acre | 17.35 | 1200 | 0% | 1200 | 20820
Pool Lighting Electrical | 26-1004 | S | POOL AREA | Allowance | LS | 1 | 20000 | 0% | 20000 | 20000
Pool Lighting Fixtures | 26-5603 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Equipment Electrical | 26-1007 | S | POOL EQUIP | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pump House Electrical | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 17500 | 0% | 17500 | 17500
Pump House Fixtures | 26-5001 | S | PUMPHOUSE | Allowance | LS | 1 | 750 | 0% | 750 | 750
Electrical | 26 | [9 empty] | 4194933.9827
TV and Media | 27-2201 | A | BUILDING | Allowance | LS | 3 | 1000 | 0% | 1000 | 3000 |  | Per Building
DAS System | 27-3010 | S | BUILDING | Torrey Pines | SF | 362571 | 0.45 | 0% | 0.45 | 163156.95
Pool ADA Phone | 27-3201 | S | POOL AREA | Allowance | LS | 1 | 800 | 0% | 800 | 800 |  | Per Pool
Communications | 27 | [9 empty] | 166956.95
Security System | 28-1001 | S | BUILDING | Torrey Pines | Unit | 363 | 448 | 0% | 448 | 162624 |  | Previously used Russell pricing.
Site Security System | 28-2001 | S | ON-SITE | Pebble | Mo | 30 | 5642.8571 | 0% | 5642.8571 | 169285.7143 |  | Pebble monthly cost to date.
Fire Alarm / Two Way Comm AOR | 28-4601 | S | BUILDING | Bruner | SF | 361641 | 1.3348 | 5% | 1.4015 | 506841.6422 |  | Bruner SNF proposal plus 5% escalation due to more buildings needing more main panels and equipment.
Fire Alarm - Pump House | 28-4601S | S | PUMPHOUSE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Electronic Safety & Security | 28 | [9 empty] | 848751.3565
Construction Water | 31-0121 | S | ON-SITE | Allowance | Acre | 17.35 | 6500 | 0% | 6500 | 112775
Dust Control | 31-0122 | S | ON-SITE | Allowance | Acre | 17.35 | 3500 | 0% | 3500 | 60725
Track Out Pad / DEMO | 31-0505 | S | ON-SITE | Budget | LS | 1 | 25000 | 0% | 25000 | 25000 |  | Budget Details
Rock Dirt Haul Off | 31-1492 | S | ON-SITE | Budget | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Budget Details
Mass Grading | 31-2201 | S | ON-SITE | Budget | LS | 1 | 1067126 | 0% | 1067126 | 1067126 |  | Budget Details
Fine Grade | 31-2216 | S | ON-SITE | Budget | LS | 1 | 37727 | 0% | 37727 | 37727 |  | Budget Details
Hard Dig | 31-2319 | S | ON-SITE | Budget | LS | 1 | 150000 | 0% | 150000 | 150000 |  | Budget Details
Dewatering | 31-2322 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Storm Water Prevention | 31-2501 | S | ON-SITE | Allowance | Acre | 17.35 | 2500 | 0% | 2500 | 43375
Earthwork | 31 | [9 empty] | 1546728
Bond Repair | 32-0100 | RR | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000 | [6 empty] | 5000 | 0
Street Cleaning | 32-0111 | S | OTHER SITE | Allowance | LS | 2 | 2500 | 0% | 2500 | 5000 | [6 empty] | 5000 | 0
Asphalt Sawcut and Removal | 32-0506 | S | ON-SITE | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 |  | See Budget File |  |  |  |  | 30000 | 0
Paving | 32-1216 | S | ON-SITE | Torrey Pines | LS | 1 | 670743 | 0% | 670743 | 670743 |  | See Budget File |  |  |  |  | 670743 | 0
Seal Coat | 32-1236 | S | ON-SITE | Allowance | SF | 215053 | 0.25 | 0% | 0.25 | 53763.25 | [6 empty] | 53763.25 | 0
Pavers | 32-1401 | S | OTHER SITE | Pebble | SF | 3000 | 8.5 | 0% | 8.5 | 25500 |  | Allowance |  |  |  |  | 25500 | 0
Pool Decks | 32-1402 | S | POOL AREA | Pebble | SF | 8023 | 8.5 | 0% | 8.5 | 68195.5 |  | Pool Deck |  |  |  |  | 68195.5 | 0
Curbs and Gutters | 32-1613 | S | ON-SITE | Torrey Pines | LS | 1 | 112240 | 0% | 112240 | 112240 |  | See Budget File |  |  |  |  | 112240 | 0
Tack On Curb | 32-1614 | S | ON-SITE | Torrey Pines | LS | 1 | 140670 | 0% | 140670 | 140670 |  | See Budget File |  |  |  |  | 140670 | 0
Concrete Flatwork | 32-1623 | S | ON-SITE | Torrey Pines | LS | 1 | 273468 | 0% | 273468 | 273468 |  | See Budget File |  |  |  |  | 273468 | 0
Bus Pad | 32-1625 | S | OTHER SITE | N/A |  |  |  | 0% | 0 | 0 | [6 empty] | 0 | 0
Pool Hardscape | 32-1626 | S | POOL AREA | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 | [6 empty] | 10000 | 0
Street Signs / Striping | 32-1700 | S | ON-SITE | Allowance | Acre | 17.35 | 3000 | 0% | 3000 | 52050 | [6 empty] | 52050 | 0
Walls Iron | 32-3101 | S | ON-SITE | Torrey Pines | LS | 1 | 91085 | 0% | 91085 | 91085 |  | See Budget File |  |  |  |  | 91085 | 0
Trash Enclosure Iron Gates | 32-3103 | S | OTHER SITE | Torrey Pines | Count | 14 | 2485 | 0% | 2485 | 34790 | [6 empty] | 34790 | 0
Site Railings | 32-3104 | A | OTHER SITE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000 | [6 empty] | 15000 | 0
Dog Run Fence | 32-3105 | S | ON-SITE | Allowance | LF | 300 | 75 | 0% | 75 | 22500 | [6 empty] | 22500 | 0
Pool Fence | 32-3106 | S | POOL AREA | Torrey Pines | LS | 1 | 27900 | 0% | 27900 | 27900 | [6 empty] | 27900 | 0
Pool Fence Gates | 32-3106 | S | POOL AREA | Torrey Pines | Count | 2 | 1950 | 0% | 1950 | 3900 | [6 empty] | 3900 | 0
Entry Security Gates | 32-3111 | S | ON-SITE | Torrey Pines | LS | 1 | 6000 | 0% | 6000 | 6000 |  | Crash Gate |  |  |  |  | 6000 | 0
Entry Security Gates Electrical | 32-3112 | S | ON-SITE | N/A |  |  | 3555 | 0% | 3555 | 0 | [6 empty] | 0 | 0
Entry Gate Transmitters | 32-3113 | S | ON-SITE | N/A |  |  | 44 | 0% | 44 | 0 | [6 empty] | 0 | 0
Entry Gates | 32-3114 | S | ON-SITE | Budget | LS | 2 | 1950 | 0% | 1950 | 3900 | [6 empty] | 3900 | 0
Temp Fencing | 32-3120 | S | ON-SITE | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 | [6 empty] | 30000 | 0
Walls Masonry | 32-3201 | S | ON-SITE | Budget | LS | 1 | 376743 | 0% | 376743 | 376743 |  | Budget based on Project Due Diligence report prepared by Impulse Civil Eng. 3/5/25 |  |  |  |  | 376743 | 0
Walls Pilaster Caps | 32-3202 | S | ON-SITE | Included | LS | 1 | 31250 | 0% | 31250 | 31250 |  | Budget based on Project Due Diligence report prepared by Impulse Civil Eng. 3/5/25 |  |  |  |  | 31250 | 0
Retaining Walls | 32-3204 | S | ON-SITE | Budget | LS | 1 | 331457 | 0% | 331457 | 331457 |  | Budget based on Project Due Diligence report prepared by Impulse Civil Eng. 3/5/25 |  |  |  |  | 331457 | 0
Pool Walls | 32-3208 | A | POOL AREA | Allowance | LS | 2 | 7500 | 0% | 7500 | 15000 | [6 empty] | 15000 | 0
Site Furniture Permanent | 32-3343 | A | BUILDING | Allowance | LS | 1 | 7000 | 0% | 7000 | 7000 | [6 empty] | 7000 | 0
Site Landscaping | 32-9001 | S | ON-SITE | Torrey Pines | SF | 331082 | 12.01 | 0% | 12.01 | 3976294.82 |  | Previous budget used Decatur per unit cost. |  |  |  |  | 3976294.82 | 0
Site Landscaping Lighting | 32-9001 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0 | [6 empty] | 0 | 0
Site Landscaping Planter Pots | 32-9433 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0 | [6 empty] | 0 | 0
Offsite Asphalt Sawcut and Removal | 32-0506 | S | Offsite | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000 | [6 empty] | 5000 | 0
Offsite Paving | 32-1216 | S | Offsite | Torrey Pines | LS | 1 | 413660 | 0% | 413660 | 413660 |  | See Budget File. |  |  |  |  | 413660 | 0
Offsite Curbs and Gutters | 32-1613 | S | Offsite | Torrey Pines | LS | 1 | 32717 | 0% | 32717 | 32717 |  | See Budget File |  |  |  |  | 32717 | 0
Offsite Concrete Flatwork | 32-1623 | S | Offsite | Torrey Pines | LS | 1 | 37000 | 0% | 37000 | 37000 |  | See Budget File |  |  |  |  | 37000 | 0
Offsite Parvin Realignment | 32-5500 | S | Offsite | Budget | LS | 1 | 0 | 0% | 0 | 0
Exterior Improvements | 32 | [9 empty] | 6907826.57
Temp Power | 33-0501 | A |  | Allowance | Unit | 363 | 375 | 0% | 375 | 136125
Traffic Control, AC Removal and Patch | 33-1001 | A | Offsite | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Water | 33-1001 | S | ON-SITE | Torrey Pines | LS | 1 | 1306636 | 0% | 1306636 | 1306636 |  | See Budget File. It includes $110k in hard dig.
Sewer | 33-3001 | S | ON-SITE | Torrey Pines | LS | 1 | 823398 | 0% | 823398 | 823398 |  | Budget includes $200k for lift station. Pete doesn't believe is needed.
Storm Drain | 33-4001 | S | ON-SITE | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000
Sub Drains | 33-4116 | A |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Gas | 33-5001 | S | Offsite | Budget | LS | 1 | 0 | 15% | 0 | 0
Electric | 33-7101 | S |  | Torrey Pines | LS | 1 | 452076 | 0% | 452076 | 452076 |  | See Budget File (Includes $111K in Hard Dig)
Secondary Conduit | 33-7102 | A |  | Allowance | LS | 0 | 0 | 0% | 0 | 0 |  | Included in budget for Onsite.
Bollards | 33-7103 | S |  | Allowance | LS | 1 | 15600 | 0% | 15600 | 15600
Cable TV | 33-8201 | S |  | N/A |  |  |  | 0% | 0 | 0
Phone | 33-8202 | S |  | N/A |  |  |  | 0% | 0 | 0
Off Site Water | 33-1001 | S | Offsite | Budget | LS | 1 | 345550 | 0% | 345550 | 345550 |  | POC on Robindale water lines.
Off Site Sewer | 33-3001 | S | Offsite | Alowance | LS | 1 | 75000 | 0% | 75000 | 75000 |  | Allowance. Per Pete POC are onsite.
Off Site Storm Drain | 33-4001 | S | Offsite | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Off Site Electric | 33-7101 | S | Offsite | Torrey Pines | LS | 1 | 61000 | 0% | 61000 | 61000 |  | $50k allowance plus rough street work allowance.
Utilities | 33 | [9 empty] | 3305385
Bridge |  |  | ON-SITE | Allowance | LS | 2 | 594250 | 0% | 594250 | 1188500
Other |  |  | ON-SITE | Allowance | LS | 1 | 100000 | 0% | 100000 | 100000 |  | Allowance for cutting the chanel concrete.
Brigde Over Duct Creek Wash | 33 | [9 empty] | 1288500
Traffic Control | 34-4116 | A | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Transportation | 34 | [9 empty] | 7500
Solar PV System | 48-1413 | S |  | Allowance | LS | 1 | 977434 | 0% | 977434 | 977434
Solar PV Conduit | 48-1414 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Increase allowance to account for EV new requirements.
Car Charging Stations | 48-1913 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000
Electrical Power Generation | 48 | [9 empty] | 1077434
Staking | 49-0601 | S |  | Pebble | LS | 17.35 | 9972 | 0% | 9972 | 173014.2 |  | Using Pebble Cost to Date as Benchmark.
Re Staking | 49-0602 | S |  | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Using Pebble Cost to Date as Benchmark.
Certs and Verifications | 49-0603 | S |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000 |  | Using Pebble Cost to Date as Benchmark.
Slab Testing | 49-0801 | S |  | Pebble | LS | 17.35 | 5775 | 0% | 5775 | 100196.25 |  | Using Pebble Cost to Date as Benchmark.
Grading Testing | 49-0802 | S |  | Pebble | LS | 17.35 | 7500 | 0% | 7500 | 130125 |  | Using Pebble Cost to Date as Benchmark.
Other Testing | 49-0803 | S |  | Pebble | LS | 17.35 | 7500 | 0% | 7500 | 130125 |  | Using Pebble Cost to Date as Benchmark.
Masonry Testing | 49-0807 | S |  | Allowance | LS | 17.35 | 1000 | 0% | 1000 | 17350 |  | Using Pebble Cost to Date as Benchmark.
Pavement Testing | 49-0808 | S |  | Allowance | LS | 17.35 | 1000 | 0% | 1000 | 17350 |  | Using Pebble Cost to Date as Benchmark.
Third Party Inspections | 49-0950 | S |  | Pebble | LS | 17.35 | 2500 | 0% | 2500 | 43375 |  | Using Pebble Cost to Date as Benchmark.
Field Surveys, Staking | 49 | [9 empty] | 626535.45
BABA | [5 empty] | 0% |  |  |  | 0
Bid Risk | [5 empty] | 2% |  |  |  | 1112398.67
Bid Risk & BABA | Bid Risk | [9 empty] | 1112398.67
Golf Carts | 11-1001 | S |  | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Convenience Store Equipment | 11-2101 | S |  | N/A |  |  |  | 0% | 0 | 0
Pet Wash | 11-2102 | S |  | N/A | LS | 0 | 21000 | 0% | 21000 | 0
Office Equipment | 11-2801 | S |  | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Gym Exercise Equipment | 11-6613 | S |  | Decatur | LS | 2 | 47324 | 0% | 47324 | 94648
Playground / Basketball Hoop | 11-6813 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 3720000
Maintenance Shop Equipment | 11-8101 | S |  | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Maintenance Shop Start Up Supplies | 11-8102 | S |  | Alowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fixed Asset Misc. | 11-8105 | S |  | N/A |  |  |  | 0% | 0 | 0
Interior Furniture | 12-5000 | S |  | Allowance | LS | 3 | 500000 | 0% | 500000 | 1500000
Exterior Furniture | 12-5483 | S |  | Allowance | LS | 3 | 100000 | 0% | 100000 | 300000
Rec Building TV Media Computer | 27-2201 | S |  | Allowance | LS | 1 | 20000 | 0% | 20000 | 20000
Rec Building Telephone System | 27-3202 | S |  | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Maintenance Radios | 27-3243 | S |  | Allowance | LS | 1 | 1200 | 0% | 1200 | 1200
FFE | FFE Extra | [9 empty] | 1972848
Construction Contingency | 55-9800 |  |  |  |  | 5% |  |  |  | 2782346.675
Construction Contingency | 55 | [9 empty] | 2782346.675
Sub Bonds | 50-9950 | B |  |  |  | 1.7% |  |  |  | 945538.8695
Sub Bonds | 50 | [9 empty] | 945538.8695
GL Insurance | 50-0001 |  |  |  | 3.03 per $1,000 | 5 |  |  |  | 310599.6675
Misc. | 50-0001 |  |  |  | 5% of GL Ins. | 5% |  |  |  | 15529.9834
Umbrella | 50-0001 |  |  |  | 95% of GL Ins. | 0.95 |  |  |  | 295069.6841
GL Insurance | 50 | [9 empty] | 621199.335
Overhead | 56 |  |  |  |  | 2% |  |  |  | 1112938.67
Contractor Fee | 56 |  |  |  |  | 6% |  |  |  | 3338816.01
OH & Contractor Fee | 56 | [9 empty] | 4451754.68
Total Hard Costs | [10 empty] | 68871987.7394
0
General Requirements | 01 |  |  | 3338816.01 | [8 empty] | 6% General Conditions
Existing Conditions | 02 |  |  | 16000 | [8 empty] | 55619933.4999
Concrete | 03 |  |  | 2785657.8839 | [8 empty] | 3337196.01 | 2780996.675
Parking Garage | 03-G |  |  | #N/A | [8 empty] | 111239.867
Masonry | 04 |  |  | 255200
Metals | 05 |  |  | 459954
Wood, Plastics, & Composites | 06 |  |  | 8327162.38
Thermal & Moisture Protection | 07 |  |  | 2157341.9423
Openings | 08 |  |  | 597923
Finishes | 09 |  |  | 5644662.8447
Specialties | 10 |  |  | 468431
Equipment | 11 |  |  | 1168905.0105
Furnishings | 12 |  |  | 2059949
Special Construction | 13 |  |  | 907561
Trash Chute | 13-G |  |  | 0
Conveying Equipment | 14 |  |  | 439560
Fire Suppression | 21 |  |  | 1110813.15
Plumbing | 22 |  |  | 3688547
HVAC | 23 |  |  | 3588865.9794
Electrical | 26 |  |  | 4194933.9827
Communications | 27 |  |  | 166956.95
Electronic Safety & Security | 28 |  |  | 848751.3565
Earthwork | 31 |  |  | 1546728
Exterior Improvements | 32 |  |  | 6907826.57
Utilities | 33 |  |  | 3305385
Transportation | 34 |  |  | 7500
Electrical Power Generation | 48 |  |  | 1077434
Field Surveys, Staking | 49 |  |  | 626535.45
5th Story Factor |  |  |  | #N/A
Bid Risk |  |  |  | 0
FFE |  |  |  | 1972848
Construction Contingency | 55 |  |  | 0
Sub Bonds | 50 |  |  | 0
GL Insurance | 50 |  |  | 621199.335
Contractor Fee | 56 |  |  | 0
Total Hard Costs |  |  |  | 68871987.7394
#N/A
Cost Code
Total
01 - General Requirements | 01 |  |  |  | 3338816.01
02 - Existing Conditions | 02 |  |  |  | 16000
03 - Concrete | 03 |  |  |  | 2785657.8839
04 - Masonry | 04 |  |  |  | 255200
05 - Metals | 05 |  |  |  | 459954
06 - Wood, Plastics, & Composites | 06 |  |  |  | 8327162.38
07 - Thermal & Moisture Protection | 07 |  |  |  | 2157341.9423
08 - Openings | 08 |  |  |  | 597923
09 - Finishes | 09 |  |  |  | 5644662.8447
10 - Specialties | 10 |  |  |  | 468431
11 - Equipment | 11 |  |  |  | 1168905.0105
12 - Furnishings | 12 |  |  |  | 2059949
13 - Special Construction | 13 |  |  |  | 907561
14 - Conveying Equipment | 14 |  |  |  | 439560
21 - Fire Suppression | 21 |  |  |  | 1110813.15
22 - Plumbing | 22 |  |  |  | 3688547
23 - HVAC | 23 |  |  |  | 3588865.9794
26 - Electrical | 26 |  |  |  | 4194933.9827
27 - Communications | 27 |  |  |  | 166956.95
28 - Electronic Safety & Security | 28 |  |  |  | 848751.3565
31 - Earthwork | 31 |  |  |  | 1546728
32 - Exterior Improvements | 32 |  |  |  | 6907826.57
33 - Utilities | 33 |  |  |  | 4593885
34 - Transportation | 34 |  |  |  | 7500
48 - Electrical Power Generation | 48 |  |  |  | 1077434
49 - Field Surveys, Staking | 49 |  |  |  | 626535.45
Bid Risk | Bid Risk |  |  |  | 1112398.67
FFE Extra | FFE Extra |  |  |  | 1972848
50 - Sub Bonds | 50 |  |  |  | 1566738.2045
55 - Construction Contingency | 55 |  |  |  | 2782346.675
56 - Contractor Fee | 56 |  |  |  | 4451754.68
Total |  |  |  |  | 68871987.7394
check |  |  |  |  | 0
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units | 09-6001 |  |  |  | 538541.7 | 09
Common Wood | 09-6401 |  |  |  | 0 | 09
Common Vinyl | 09-6517 |  |  |  | 0 | 09
Hall Flooring | 09-6520 |  |  |  | 170408.37 | 09
Hall Flooring - Elevators | 09-6520A |  |  |  | 4500 | 09
Common - Plank | 09-6521 |  |  |  | 0 | 09
Common - VCT | 09-6522 |  |  |  | 0 | 09
Common - Rubber Floor | 09-6566 |  |  |  | 0 | 09
Common - Carpet | 09-6802 |  |  |  | 33266.5714 | 09
Appliances | 11-3013 |  |  |  | 1168905.0105 | 11
Blinds | 12-2100 |  |  |  | 160809 | 12
Total Appliances, Flooring & Blinds |  |  |  |  | 2076430.652
Site Work
Major Categories
Existing Conditions | 2 |  |  |  | 16000
Earthwork | 31 |  |  |  | 1546728
Exterior Improvements | 32 |  |  |  | 6907826.57
Utilities | 33 |  |  |  | 4593885
Transportation | 34 |  |  |  | 7500
Electrical Power Generation | 48 |  |  |  | 1077434
Minor Categories
Carports | 13-3401 |  |  |  | 655512
Dumpsters | 06-0111 |  |  |  | 0
Gazebo |  |  |  |  | 0
Other Site |  |  |  |  | 0
Pools and Spas | 13-1113 |  |  |  | 245000
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Pump House Concrete | 03-3101 |  |  |  | 2146124.3359
Total Site Work |  |  |  |  | 17196009.9059
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  | already included in 32
Offsite Paving | 32-1216OFFSITE |  |  | already included in 32
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  | already included in 32
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  | already included in 32
Storm Drain | 33-4001OFFSITE |  |  | already included in 33
Off Site Water | 33-1001OFFSITE |  |  | already included in 33
Off Site Sewer | 33-3001OFFSITE |  |  | already included in 33
Off Site Electric | 33-7101OFFSITE |  |  | already included in 33
Traffic Control | 34-4116OFFSITE |  |  | already included in 34
Pump House Concrete | 03-3101
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  |  | 0
Offsite Paving | 32-1216OFFSITE |  |  |  | 0
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  |  | 0
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  |  | 0
Off Site Water | 33-1001OFFSITE |  |  |  | 0
Off Site Sewer | 33-3001OFFSITE |  |  |  | 0
Storm Drain | 33-4001OFFSITE |  |  |  | 0
Off Site Electric | 33-7101OFFSITE |  |  |  | 0
Traffic Control | 34-4116OFFSITE |  |  |  | 0
Other Ineligible Costs
Major Categories
Parking Garage | 03-G |  |  |  | 0
Minor Categories
Pump House Concrete | 03-3101 |  |  |  | 2146124.3359
Pool Area Shower Concrete | 03-3105 |  |  |  | 20200
Cabana Concrete | 03-3107 |  |  |  | 0
Pool Equipment Foundation | 03-3108 |  |  |  | 10000
Deck Concrete | 03-5001 |  |  |  | 43318
Masonry Veneer Pool Area | 04-4305 |  |  |  | 5000
Pool Equipment Shower Stone | 04-4306 |  |  |  | 10000
Cabana Iron | 05-7004 |  |  |  | 0
Pool Equipment Gate | 05-7005 |  |  |  | 1950
Cabana Framing | 06-1109 |  |  |  | 0
BBQ Framing | 06-1110 |  |  |  | 10000
Fireplace Framing | 06-1111 |  |  |  | 0
Trellis | 06-1114 |  |  |  | 0
BBQ Trim | 06-2006 |  |  |  | 5000
Cabana Roofing | 07-3002 |  |  |  | 7500
Pump House Roofing | 07-3002 |  |  |  | 7500
Pool Equipment Windows | 08-5303 |  |  |  | 0
Pool Glass Walls | 08-8001 |  |  |  | 0
Stucco - Pump House | 09-2423 |  |  |  | 842819.6111
Stucco - Cabana | 09-2423 |  |  |  | 842819.6111
Stucco - Pool Wall | 09-2423 |  |  |  | 842819.6111
Unit Carport Signs | 10-1401 |  |  |  | 56265
Fire Places - Pool Area | 10-3200 |  |  |  | 0
BBQ Units | 10-3355 |  |  |  | 13440
BBQ Top | 12-3609 |  |  |  | 24000
Pools and Spas | 13-1113 |  |  |  | 245000
Carports | 13-3401 |  |  |  | 655512
Pool Equipment Cover | 13-3402 |  |  |  | 7049
Pool and Spa Lifts | 14-4101 |  |  |  | 13000
Pool Area | 22-1003 |  |  |  | 25000
Pool Equipment | 22-1007 |  |  |  | 6000
Carports Electrical | 26-1001 |  |  |  | 3708740.9827
Carport Fixtures | 26-5001 |  |  |  | 225700
Cabana Electrical | 26-1001 |  |  |  | 3708740.9827
Cabana Fixtures | 26-5004 |  |  |  | 0
Pool Lighting Electrical | 26-1004 |  |  |  | 20000
Pool Lighting Fixtures | 26-5603 |  |  |  | 12500
Pool Equipment Electrical | 26-1007 |  |  |  | 2500
Pump House Electrical | 26-1001 |  |  |  | 3708740.9827
Pump House Fixtures | 26-5001 |  |  |  | 225700
Pool Decks | 32-1402 |  |  |  | 68195.5
Pool Hardscape | 32-1626 |  |  |  | 10000
Pool Fence | 32-3106 |  |  |  | 31800
Pool Walls | 32-3208 |  |  |  | 15000
Pet Wash | 11-2102 |  |  |  | 0
Office Equipment | 11-2801 |  |  |  | 25000
Gym Exercise Equipment | 11-6613 |  |  |  | 94648
Playground / Basketball Hoop | 11-6813 |  |  |  | 0
Rec Building TV Media Computer | 27-2201 |  |  |  | 23000
Rec Building Telephone System | 27-3202 |  |  |  | 2000

## LEVEL 1.1 BUDGET
Project Details |  |  | Unit Breakdown |  |  |  | Unit Matrix | [5 empty] | List of Take offs |  |  | List of Take offs |  |  | List of Take offs
Project | Robindale &215 |  | Unit Type | Number | % |  | Unit Type | Number | % | SF |  |  | Slab SF | 174940 | GSF | Counter tops | 0 | SF | Fitness Center | 0 | SF
Budget Level | Level 1 |  | Studios | 0 | 0% |  | 1A | 170 | 46.83% | 676 |  |  | Elevators | 6 | Count | Blinds | 0 | [5 empty] | Railing Estimate |  |  | Building 3 | 147 | Stucco |  |  | Building 3 | 61455
Product | Senior |  | 1 Br - 1 Ba | 218 | 60.06% |  | 1B | 48 | 13.22% | 764 |  |  | Elevators Stops | 12 | Count | Landscaping | 331082 | SF |  |  |  |  | Building 1 |  |  |  | 98 | Building 1
Start Date | 2026-04-15 |  | 2 Br - 1 Ba | 145 | 39.94% |  | 2A | 127 | 34.99% | 901 |  |  | Trash Encl. | 14 | Site Plan | [7 empty] | Northwest | 190 |  |  | 176 | Northwest | 19256
Timeline | 30 |  | 2 Br - 2 Ba | 0 | 0% |  | 2B | 18 | 4.959% | 968 |  |  | Stairs | 18 | Count | 1x1 Decks | 3072 | SF |  |  |  |  | Southwest | 146 |  |  | 70 | Southwest | 8980
Floors | 2 |  | 3 Br - 2 Ba | 0 | 0% |  | Totals | 363 | 100% | 283443 |  |  | Pool | 1 |  | 2x1 Decks | 0 | SF |  |  |  |  | Northeast | 118 |  |  | 491 | Northeast | 8850
Bldg. SF | 361641 |  | Totals | 363 | 100% | [7 empty] | Gym | 1 |  | Lightweight | 0 | SF |  |  |  | 347 | Southeast | 306 |  |  |  | Southeast | 19965
Acres | 17.25 |  | Parking | [9 empty] | Iron Rail | 1648 | LF | Pavers | 0 | SF |  |  |  | 385 | More | 132 | 892 |  |  | More | 24325 | 81376
Site SF | 751410 |  | Cover Parking |  | 295 | [7 empty] | Roofing | 1749.4 | Square | Pool Deck | 0 | SF |  |  |  | 300
Buildings | 3 |  | Cover Accesible Parking | [9 empty] | Stucco | 20609.9794 | Square Yard | Pool Fence | 0 | LF |  |  |  |  | Building 2 & 5 |  |  | Building 4 | 112 | Building 2 & 5 |  |  | Building 4 | 29517
Reports Available |  |  | Open Parking |  | 147 | [7 empty] | Livable Area | 0 | SF | Dog Park Fence | 0 | LF |  |  |  |  | Northwest |  |  |  | 160 | Northwest
Site Evaluation Report (GCW) |  |  | Accessible Parking |  | 14 | [7 empty] | Carports | 295 | Count | Common Bldg. 1 | 0 | SF |  |  |  |  | Southwest |  |  |  | 144 | Southwest
Soils Report (Nova or Universal) |  |  | Waiver |  | 0 |  | TOTAL COST |  | 69361424.0868 |  |  |  | Stairs Landings | 0 | Landings | Asphalt | 0 | [5 empty] | Northeast |  |  |  | 84 | Northeast
Alta Survey (Wallace) |  |  | Total Parking Provided |  | 456 |  | PER UNIT |  | 191078.3033 |  |  |  | Pump House | 1 | EA | Pavers | 0 | [5 empty] | Southeast | 160 | 320 |  | 500 | Southeast | 14730 | 29460
Plans |  |  | Parking Ratio |  | 1.2562 |  | PER GSF |  | 191.7964 |  |  |  | Lock Boxes | 0 | EA | Pavers Pool | 0
[7 empty] | Efficiency Factor |  | 78.38% |  |  |  | Awning Small | 30 | EA | [7 empty] | B1B Railings | 775 |  |  |  | B1B Railings | 775
[13 empty] | Awning Large | 10 | EA
Description | Cost Code | Cost Category | Sub job | Source | UMO | Quantity | U.P. | Escal % | Total U.P. | Sub Total | Total | Description / Details
General Requirements | 01 | [9 empty] | 3443297.7151
General Requirement | 01 | S |  |  | Mo | 30 | 114776.5905 | 0% | 114776.5905 | 3443297.7151 |  | Change timeline from 24 to 30 months due to complexcity of bridges, underground and project size 17.25 acres/363 units.
Existing Conditions | 02 | [9 empty] | 16000
Potholing | 02-3213 | S | ON-SITE | Allowance |  | 1 | 16000 | 0% | 16000 | 16000
Concrete | 03 | [9 empty] | 2697268.48
Slabs | 03-3101 | S | BUILDING | Torrey Pines | SF | 174940 | 11.99 | 0% | 11.99 | 2097530.6
Deepened Footings | 03-3101 | S | BUILDING | N/A |  |  |  |  | 0 | 0
Concrete Slab Repairs | 03-3101 | RR | BUILDING | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pump House Concrete | 03-3101 | S | PUMPHOUSE | Torrey Pines | SF | 300 | 11.99 |  | 11.99 | 3597
Trash Enclosure Concrete | 03-3102 | S | OTHER SITE | Allowance | SF | 1344 | 11.99 | 0% | 11.99 | 16114.56
Pool Area Shower Concrete | 03-3105 | S | POOL AREA | Torrey Pines | LS | 1 | 2500 | 0% | 2500 | 2500
Cabana Concrete | 03-3107 | S | POOL AREA | N/A |  |  |  |  | 0 | 0
Pool Equipment Foundation | 03-3108 | S | POOL EQUIP | N/A |  |  |  |  | 0 | 0
Lightweight Concrete | 03-3116 | S | BUILDING | Torrey Pines | SF | 174940 | 2.94 | 0% | 2.94 | 514323.6
Deck Concrete | 03-5001 | S | BUILDING | Torrey Pines | SF | 3072 | 19.76 | 0% | 19.76 | 60702.72
Masonry | 04 | [9 empty] | 207800
Elevator Shaft | 04-2201 | S | BUILDING | Torrey Pines | Stop | 12 | 9500 | 0% | 9500 | 114000
Trash Enclosure | 04-2202 | S | OTHER SITE | Torrey Pines | Count | 14 | 5700 | 0% | 5700 | 79800
Masonry Veneer | 04-4301 | S | ON-SITE | N/A |  |  | 0 |  | 0 | 0
Masonry Veneer Pool Area | 04-4305 | S | POOL AREA | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Pool Eq. Shower Stone | 04-4306 | A | POOL EQUIP | Torrey Pines | LS | 1 | 9000 | 0% | 9000 | 9000
Metals | 05 | [9 empty] | 349806
Structural Steel | 05-1201 | S | BUILDING | Torrey Pines | LS | 1 | 100000 | 0% | 100000 | 100000
Elevator Shaft Iron | 05-1202 | S | BUILDING | Torrey Pines | Count | 6 | 4040 | 0% | 4040 | 24240
Stair Handrails | 05-5201 | S | BUILDING | Torrey Pines | Flight | 36 | 2000 | 0% | 2000 | 72000
Garage Stair Railings | 05-5201 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Cabana Iron | 05-7004 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
Pool Equipment Gate | 05-7005 | S | POOL EQUIP | Torrey Pines | Count | 1 | 1950 | 0% | 1950 | 1950
Iron Railings | 05-7300 | S | BUILDING | Torrey Pines | LF | 1648 | 92 | 0% | 92 | 151616
Cable Railings | 05-7316 | S | COMMON AREA | N/A |  |  | 0 | 0% | 0 | 0
Wood, Plastics, & Composites | 06 | [9 empty] | 8880630.8
Dumpsters | 06-0111 | S | DUMPSTERS |  |  |  |  | 0% | 0 | 0 |  | Included in Construction Cleaning Contract
Framing | 06-1100 | S | BUILDING | Moving Ave | SF | 361641 | 20.5 | 0% | 20.5 | 7413640.5
Framing - Crane | 06-1100 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Framing | 06-1109 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Framing | 06-1110 | S | COMMON AREA | Allowance | LS | 4 | 2500 | 0% | 2500 | 10000
Fireplace Framing | 06-1111 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Trellis | 06-1114 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Pool Equipment Framing | 06-1114 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Finish Carpentry - Units | 06-2001 | S | BUILDING | Torrey Pines | Unit | 363 | 3192.5 | 0% | 3192.5 | 1158877.5
Finish Carpentry - Common | 06-2001 | S | COMMON AREA | Torrey Pines | SF | 361641 | 0.8 | 0% | 0.8 | 289312.8
Finish Carpentry - Pump House | 06-2001S | S | PUMPHOUSE | Flamingo | LS | 1 | 4000 | 0% | 4000 | 4000
BBQ Trim | 06-2006 | S | COMMON AREA | Allowance | LS | 4 | 1200 | 0% | 1200 | 4800
Shutters | 06-4919 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Thermal & Moisture Protection | 07 | [9 empty] | 2198832.23
Insulation | 07-2101 | S | BUILDING | Torrey Pines | SF | 361641 | 2.7 | 0% | 2.7 | 976430.7 |  | It includes the material increased since for 2nd half of 2024.
Roofing | 07-3001 | S | BUILDING | Torrey Pines | Squares | 1749.4 | 603 | 0% | 603 | 1054888.2
Cabana Roofing | 07-3002 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Pump House Roofing | 07-3002 | S | PUMPHOUSE | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Pool Equipment Roofing | 07-3003 | S | POOL EQUIP | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Trash Enclosure Cover | 07-6101 | S | OTHER SITE | Decatur | Count | 14 | 5800 | 0% | 5800 | 81200
Pigeon Proofing | 07-7001 | S | BUILDING | Torrey Pines | SF | 361641 | 0.08 | 0% | 0.08 | 28931.28
Gutters and Downspouts | 07-7124 | S | BUILDING | Torrey Pines | SF | 361641 | 0.05 | 0% | 0.05 | 18082.05
Roof Ladders | 07-7210 | S | BUILDING | Torrey Pines | Count | 6 | 1550 | 0% | 1550 | 9300 |  | 2 Per building
Roof Access Doors | 07-7233 | S | BUILDING | Torrey Pines | Count | 6 | 2500 | 0% | 2500 | 15000 |  | 2 Per building
Roof Winch | 07-7250 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Openings | 08 | [9 empty] | 516935.7895
Dumpsters | 08-0151 | S | DUMPSTERS |  |  |  |  | 0% | 0 | 0 |  | Inclunded with Construction Cleaning Contract.
Entry Doors | 08-1001 | S | COMMON AREA | Allowance | Count | 1 | 8000 | 0% | 8000 | 8000
Common Doors | 08-1002 | S | COMMON AREA | Included |  |  |  | 0% | 0 | 0
Pocket Doors - 3 Panel | 08-1002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Garage Doors | 08-3619 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Windows and Sliding Glass Doors | 08-5301 | S | BUILDING | Torrey Pines | Per Unit | 363 | 1157.8947 | 0% | 1157.8947 | 420315.7895
Windows Repair and Replacement | 08-5301 | RR | BUILDING | Allowance | Per Unit | 363 | 75 | 0% | 75 | 27225
Pool Equipment Windows | 08-5303 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0
Pool Glass Walls | 08-8001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Fixed Glass | 08-8002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - LED Install | 08-8302 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Framed | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Mirrors - Polished Edges (Units) | 08-8301 | S | BUILDING | Pebble | Unit | 363 | 165 | 0% | 165 | 59895
Mirrors - Polished Edges (Restrooms) | 08-8301 | S | BUILDING | Allowance | Count | 6 | 250 | 0% | 250 | 1500
Finishes | 09 | [9 empty] | 5549735.2782
Cost Prep Labor | 09-0101 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cost Prep Mat - Home Depot | 09-0102 | S | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Clean Up - Final | 09-0103 | S | BUILDING | Torrey Pines | SF | 361641 | 0.85 | 0% | 0.85 | 307394.85 |  | Includes Dumpters
Clean Up - During Construction - Labor | 09-0104 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000
Dumpsters | 09-0113 | S | DUMPSTERS | Allowance | Unit | 363 | 79 | 0% | 79 | 28677
Clean Up - Hauling Exterior | 09-0121 | S | ON-SITE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Included in Construction Cleaning Contract.
Stucco | 09-2423 | S | BUILDING | Torrey Pines | SY | 20609.9794 | 40.82 | 0% | 40.82 | 841299.3587 |  | 12 Month Moving Average
Stucco - Pump House | 09-2423S | A | PUMPHOUSE | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Stucco - Walls | 09-2424 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Area | 09-2428 | A | POOL AREA | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Stucco - Cabana | 09-2429 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Stucco - Pool Equipment | 09-2430 | S | POOL EQUIP | Pebble | LS | 1 | 5000 | 0% | 5000 | 5000
Stucco - Repairs | 09-2423A | RR | BUILDING | Allowance | LS | 1 | 1500 | 0% | 1500 | 1500
Drywall | 09-2905 | S | BUILDING | Torrey Pines | SF | 361641 | 8.02 | 0% | 8.02 | 2900360.82
Drywall - Repairs | 09-2905A | RR | BUILDING | Allowance | Unit | 363 | 85 | 0% | 85 | 30855
Drywall - Pump House | 09-2905S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Tile Tubs and Showers | 09-3001 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Common Tile | 09-3002 | S | COMMON AREA | Pebble | LS | 1 | 67657 | 0% | 67657 | 67657
Kitchen Backsplash | 09-3003 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Cabana Tile | 09-3008 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Flooring - Units | 09-6001 | S | BUILDING | Decatur | SY | 16642 | 17.37 | 0% | 17.37 | 289071.54 |  | Sheet Vinyl - Seamless
Common Wood | 09-6401 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common Vinyl | 09-6517 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Hall Flooring | 09-6520 | S | COMMON AREA | Pebble | SF | 361641 | 0.37 | 0% | 0.37 | 133807.17
Hall Flooring - Elevators | 09-6520A | A | COMMON AREA | Allowance | Count | 6 | 750 | 0% | 750 | 4500
Common - Plank | 09-6521 | S | COMMON AREA | N/A |  | 0 | 0 | 0% | 0 | 0
Common - VCT | 09-6522 | S | COMMON AREA | N/A | SF | 0 | 0 | 0% | 0 | 0
Common - Rubber Floor (Ecore) | 09-6566 | S | COMMON AREA | Pebble | SF | 0 | 16.5334 | 0% | 16.5334 | 0
Common - Carpet Stairs | 09-6802 | S | COMMON AREA | Pebble | Count | 18 | 1848.1429 | 0% | 1848.1429 | 33266.5714
Hall Runner Install | 09-6803 | S | COMMON AREA | Pebble | SF | 361641 | 0.051209 | 0% | 0.051209 | 18519.3003 |  | Assumption of 25% of corridor SF.
Hall Runner Materials | 09-6804 | S | COMMON AREA | Pebble | SF | 361641 | 0.297 | 0% | 0.297 | 107407.2277 |  | Assumption of 25% of corridor SF.
Painting - Repairs | 09-9101A | RR | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Painting | 09-9101 | S | BUILDING | Torrey Pines | SF | 361641 | 1.84 | 0% | 1.84 | 665419.44
Painting - Pump House | 09-9101S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Painting - Walls | 09-9102 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Painting - Pool Area | 09-9106 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Wall Covering |  | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Walls - Specialty | 09-9110 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0
Specialties | 10 | [9 empty] | 424275
Entry Directory | 10-1300 | S | ON-SITE | N/A |  |  | 5478 | 0% | 5478 | 0
Unit Carport Signs | 10-1401 | S | CARPORT | Russell IV | Unit | 363 | 155 | 0% | 155 | 56265
Site Signage | 10-1404 | S | ON-SITE | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000
Entry Sign Letters | 10-1419 | S | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Offsite Street Signs | 10-1454 | S | Offsite | Allowance | LS | 1 | 7000 | 0% | 7000 | 7000
Bath Accessories | 10-2816 | S | BUILDING | Russell IV | Unit | 363 | 17 | 0% | 17 | 6171
Shower Doors | 10-2919 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places | 10-3000 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0
Fire Places - Pool Area | 10-3200 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0
BBQ Units | 10-3355 | S | POOL AREA | Arzano | LS | 4 | 3360 | 0% | 3360 | 13440
Lock Boxes | 10-4116 | S | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fire Extinguishers | 10-4416 | S | BUILDING | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 |  | Is this not included in the sprinkler contract? Yes but seperate cost code.
Mail Boxes | 10-5523 | S | BUILDING | Rainbow | Unit | 363 | 153 | 0% | 153 | 55539
Closet Shelving | 10-5723 | S | BUILDING | Torrey Pines | Unit | 363 | 220 | 0% | 220 | 79860
Window Awnings Small | 10-7313 | S | BUILDING | Torrey Pines | Count | 30 | 2500 | 0% | 2500 | 75000
Window Awnings Large | 10-7313 | S | BUILDING | Torrey Pines | Count | 10 | 8500 | 0% | 8500 | 85000
Equipment | 11 | [9 empty] | 1253975.6087
Appliances | 11-3013 | S | BUILDING | Decatur | Unit | 363 | 3454.4783 | 0% | 3454.4783 | 1253975.6087
Furnishings | 12 | [9 empty] | 2274288.4959
Dumpsters | 12-0131 | S | DUMPSTERS | N/A | 0 | 0 | 0 | 0% | 0 | 0 |  | Included in Construction Cleaning Contract
Blinds | 12-2100 | S | BUILDING | Torrey Pines | Per Unit | 363 | 454.6579 | 0% | 454.6579 | 165040.8158
Cabinets Units | 12-3531 | S | BUILDING | Decatur | Unit | 363 | 3778.0053 | 0% | 3778.0053 | 1371415.9105 |  | Decatur Option 1 Corona White 949 Thurmofoil (most afforable).
Cabinet Common Areas | 12-3535 | S | BUILDING | Allowance | LS | 1 | 75000 | 0% | 75000 | 75000
Counter Tops Units | 12-3601 | S | BUILDING | Decatur | Unit | 363 | 1622.1261 | 0% | 1622.1261 | 588831.7696 |  | Decatur Option 3 & 4 - MSI Calcuta Miksa or Carrera Triato (Regular units).
Counter Tops Common Areas | 12-3605 | A | BUILDING | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000
Counter Tops Pool Area | 12-3608 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
BBQ Top | 12-3609 | S | POOL AREA | Allowance | LS | 4 | 6000 | 0% | 6000 | 24000
Special Construction | 13 | [9 empty] | 821104
Pools and Spas | 13-1113 | S | POOL AREA | Torrey Pines | LS | 1 | 245000 | 0% | 245000 | 245000
Carports | 13-3401 | S | CARPORT | Decatur | Count | 295 | 1929 | 0% | 1929 | 569055
Pool Equipment Cover | 13-3402 | S | POOL EQUIP | Decatur | Count | 1 | 7049 | 0% | 7049 | 7049
Trash Chute | 13-G | [9 empty] | 0
Trash Chute | 13-G | S | BUILDING | N/A |  |  |  | 0% | 0 | 0
Conveying Equipment | 14 | [9 empty] | 439560
Elevator | 14-2400 | S | BUILDING | Decatur | Stop | 12 | 35546.6667 | 0% | 35546.6667 | 426560 |  | Decatur 3 Stop Hydrolift.
Pool and Spa Lifts | 14-4101 | S | POOL AREA | Allowance | Count | 2 | 6500 | 0% | 6500 | 13000
Fire Suppression | 21 | [9 empty] | 1029020.45
Sprinkler Design | 21-0600 | S | BUILDING | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Sprinkler System | 21-1313 | S | BUILDING | Torrey Pines | SF | 361641 | 2.45 | 0% | 2.45 | 886020.45
Fire Pump | 21-3000 | S | PUMPHOUSE | Torrey Pines | Count | 1 | 133000 | 0% | 133000 | 133000
Plumbing | 22 | [9 empty] | 3852664.6316
1 Bathroom Unit | 22-1001 | S | BUILDING | Torrey Pines | Count | 363 | 10526.3158 | 0% | 10526.3158 | 3821052.6316 |  | Raptor Sovent system at Torrey Pines.
2 Bathroom Unit | 22-1001 | S | BUILDING | N/A | 0 | 0 | 0 | 0% | 0 | 0
Plumbing - Pump House | 22-1001S | S | PUMPHOUSE | Allowance | LS | 1 | 1000 | 0% | 1000 | 1000
Pool Area | 22-1003 | S | POOL AREA | Torrey Pines | LS | 1 | 24612 | 0% | 24612 | 24612 |  | Budgeted at Torrey Pines
Pool Equipment | 22-1007 | S | POOL EQUIP | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000 |  | Budgeted at Torrey Pines
HVAC | 23 | [9 empty] | 3939796.656
HVAC Standard | 23-3001 | S | BUILDING | Torrey Pines | Unit | 363 | 10812.112 | 0% | 10812.112 | 3924796.656 |  | Includes new refrigerant .
HVAC - Pump House | 23-3001S | S | PUMPHOUSE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Electrical | 26 | [9 empty] | 3964403.0774
Electrical | 26-1001 | S | BUILDING | Torrey Pines | SF | 361641 | 9.27 | 5% | 9.7335 | 3520015.0774 |  | Includes 5% for Additional EV Requirements Allowance, No Gear Expediting
Electrical Fixtures | 26-5001 | S | BUILDING | Pebble | Unit | 363 | 600 | 0% | 600 | 217800
Building Electrical Fixtures | 26-5002 | S | BUILDING | Russell IV | Unit | 363 | 119 | 0% | 119 | 43197
Hall Lighting Fixtures | 26-5003 | S | BUILDING | Russell IV | Unit | 363 | 112 | 0% | 112 | 40656
Carports Electrical | 26-1001 | S | CARPORT | Russell IV | Space | 295 | 138 | 0% | 138 | 40710
Carport Fixtures | 26-5001 | S | CARPORT | Allowance | Space | 295 | 25 | 0% | 25 | 7375
Cabana Electrical | 26-1001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Cabana Fixtures | 26-5004 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0
Street Lights | 26-5613 | S | Offsite | Budget | Count | 0 | 25000 | 0% | 25000 | 0
Site Lighting Electrical | 26-1005 | S | ON-SITE | Allowance | Acre | 17.25 | 1200 | 0% | 1200 | 20700
Site Lighting Fixtures | 26-5602 | S | ON-SITE | Allowance | Acre | 17.25 | 1200 | 0% | 1200 | 20700
Pool Lighting Electrical | 26-1004 | S | POOL AREA | Allowance | LS | 1 | 20000 | 0% | 20000 | 20000
Pool Lighting Fixtures | 26-5603 | S | POOL AREA | Allowance | LS | 1 | 12500 | 0% | 12500 | 12500
Pool Equipment Electrical | 26-1007 | S | POOL EQUIP | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Pump House Electrical | 26-1001 | S | PUMPHOUSE | Allowance | LS | 1 | 17500 | 0% | 17500 | 17500
Pump House Fixtures | 26-5001 | S | PUMPHOUSE | Allowance | LS | 1 | 750 | 0% | 750 | 750
Communications | 27 | [9 empty] | 217168.19
TV and Media | 27-2201 | A | BUILDING | Allowance | LS | 3 | 1000 | 0% | 1000 | 3000 |  | Per Building
DAS System | 27-3010 | S | BUILDING | Pebble | SF | 361641 | 0.59 | 0% | 0.59 | 213368.19
Pool ADA Phone | 27-3201 | S | POOL AREA | Allowance | LS | 1 | 800 | 0% | 800 | 800 |  | Per Pool
Electronic Safety & Security | 28 | [9 empty] | 942311.9738
Security System | 28-1001 | S | BUILDING | Torrey Pines | Unit | 363 | 447.8947 | 0% | 447.8947 | 162585.7895 |  | Previously used Decatur pricing.
Site Security System | 28-2001 | S | ON-SITE | Pebble | Mo | 30 | 5642.8571 | 0% | 5642.8571 | 169285.7143 |  | Pebble monthly cost to date.
Fire Alarm / Two Way Comm AOR | 28-4601 | S | BUILDING | Torrey Pines | SF | 361641 | 1.67 | 0% | 1.67 | 603940.47 |  | Changed U.Mea to SF versus unit.
Fire Alarm - Pump House | 28-4601S | S | PUMPHOUSE | Allowance | LS | 1 | 6500 | 0% | 6500 | 6500
Earthwork | 31 | [9 empty] | 1264963.85
Construction Water | 31-0121 | S | ON-SITE | Allowance | Acre | 17.25 | 6500 | 0% | 6500 | 112125
Dust Control | 31-0122 | S | ON-SITE | Allowance | Acre | 17.25 | 3500 | 0% | 3500 | 60375
Demolition | 31-0505 | S | ON-SITE | Budget | LS | 1 | 25000 | 0% | 25000 | 25000 |  | Budget Details
Rock Dirt Haul Off | 31-1492 | S | ON-SITE | Budget | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Budget Details
Mass Grading | 31-2201 | S | ON-SITE | Budget | LS | 1 | 793445 | 0% | 793445 | 793445 |  | Budget Details
Fine Grade | 31-2216 | S | ON-SITE | Budget | LS | 1 | 30893.85 | 0% | 30893.85 | 30893.85 |  | Budget Details
Hard Dig | 31-2319 | S | ON-SITE | Budget | LS | 1 | 150000 | 0% | 150000 | 150000 |  | Budget Details
Dewatering | 31-2322 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Storm Water Prevention | 31-2501 | S | ON-SITE | Allowance | Acre | 17.25 | 2500 | 0% | 2500 | 43125
Exterior Improvements | 32 | [9 empty] | 7051690.4948
Bond Repair | 32-0100 | RR | ON-SITE | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Street Cleaning | 32-0111 | S | OTHER SITE | Allowance | LS | 1 | 2500 | 0% | 2500 | 2500
Asphalt Sawcut and Removal | 32-0506 | S | ON-SITE | Allowance | LS | 1 | 30000 | 0% | 30000 | 30000 |  | See Budget File
Paving | 32-1216 | S | ON-SITE | Torrey Pines | LS | 1 | 587370 | 0% | 587370 | 587370 |  | See Budget File
Seal Coat | 32-1236 | S | ON-SITE | Allowance | SF | 0 | 0.2 | 0% | 0.2 | 0
Pavers | 32-1401 | S | OTHER SITE | Pebble | SF | 0 | 8.5 | 0% | 8.5 | 0
Pool Decks | 32-1402 | S | POOL AREA | Pebble | SF | 0 | 8.5 | 0% | 8.5 | 0
Curbs and Gutters | 32-1613 | S | ON-SITE | Torrey Pines | LS | 1 | 66295 | 0% | 66295 | 66295 |  | See Budget File
Tack On Curb | 32-1614 | S | ON-SITE | Torrey Pines | LS | 1 | 42120 | 0% | 42120 | 42120 |  | See Budget File
Concrete Flatwork | 32-1623 | S | ON-SITE | Torrey Pines | LS | 1 | 89086 | 0% | 89086 | 89086 |  | See Budget File
Bus Pad | 32-1625 | S | OTHER SITE | N/A |  |  |  | 0% | 0 | 0
Pool Hardscape | 32-1626 | S | POOL AREA | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Street Signs / Striping | 32-1700 | S | ON-SITE | Allowance | Acre | 17.25 | 2500 | 0% | 2500 | 43125
Walls Iron | 32-3101 | S | ON-SITE | Torrey Pines | LS | 1 | 92505 | 0% | 92505 | 92505 |  | See Budget File
Trash Enclosure Iron Gates | 32-3103 | S | OTHER SITE | Torrey Pines | Count | 14 | 2485 | 0% | 2485 | 34790
Site Railings | 32-3104 | A | OTHER SITE | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Dog Run Fence | 32-3105 | S | ON-SITE | Allowance | LF | 150 | 70 | 0% | 70 | 10500
Pool Fence | 32-3106 | S | POOL AREA | Torrey Pines | LF | 300 | 70 | 0% | 70 | 21000
Pool Fence Gates | 32-3106 | S | POOL AREA | Torrey Pines | Count | 2 | 1950 | 0% | 1950 | 3900
Entry Security Gates | 32-3111 | S | ON-SITE | Torrey Pines | LS | 1 | 6000 | 0% | 6000 | 6000 |  | Crash Gate
Entry Security Gates Electrical | 32-3112 | S | ON-SITE | N/A |  |  | 3555 | 0% | 3555 | 0
Entry Gate Transmitters | 32-3113 | S | ON-SITE | N/A |  |  | 44 | 0% | 44 | 0
Entry Gates | 32-3114 | S | ON-SITE | Budget | LS | 2 | 1950 | 0% | 1950 | 3900
Temp Fencing | 32-3120 | S | ON-SITE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Walls Masonry | 32-3201 | S | ON-SITE | Budget | LS | 1 | 98343 | 0% | 98343 | 98343 |  | See Budget File
Walls Pilaster Caps | 32-3202 | S | ON-SITE | Included | LS | 1 | 0 | 0% | 0 | 0 |  | See Budget File
Retaining Walls | 32-3204 | S | ON-SITE | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Pool Walls | 32-3208 | A | POOL AREA | Allowance | LS | 1 | 11000 | 0% | 11000 | 11000
Site Furniture Permanent | 32-3343 | A | BUILDING | Allowance | LS | 1 | 7000 | 0% | 7000 | 7000
Site Landscaping | 32-9001 | S | ON-SITE | Torrey Pines | SF | 331082 | 15.5846 | 0% | 15.5846 | 5159764.8448 |  | Pricing based on Torrey Pines desity of 40k SF and GTI proposal.
Site Landscaping Lighting | 32-9001 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Site Landscaping Planter Pots | 32-9433 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0
Offsite Asphalt Sawcut and Removal | 32-0506 | S | Offsite | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Offsite Paving | 32-1216 | S | Offsite | Torrey Pines | LS | 1 | 302930.65 | 0% | 302930.65 | 302930.65 |  | See Budget File.
Offsite Curbs and Gutters | 32-1613 | S | Offsite | Torrey Pines | LS | 1 | 50205 | 0% | 50205 | 50205 |  | See Budget File
Offsite Concrete Flatwork | 32-1623 | S | Offsite | Torrey Pines | LS | 1 | 32531 | 0% | 32531 | 32531 |  | See Budget File
Offsite Parvin Realignment | 32-5500 | S | Offsite | Budget | LS | 1 | 296825 | 0% | 296825 | 296825 |  | Per Clark County on 10/30/24
Utilities | 33 | [9 empty] | 3217799
Temp Power | 33-0501 | A |  | Allowance | Unit | 363 | 375 | 0% | 375 | 136125
Traffic Control, AC Removal and Patch | 33-1001 | A | Offsite | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Water | 33-1001 | S | ON-SITE | Torrey Pines | LS | 1 | 1166027 | 0% | 1166027 | 1166027 |  | See Budget File. It includes $110k in hard dig.
Sewer | 33-3001 | S | ON-SITE | Torrey Pines | LS | 1 | 645121 | 0% | 645121 | 645121 |  | See Budget File
Storm Drain | 33-4001 | S | ON-SITE | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000
Sub Drains | 33-4116 | A |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000
Gas | 33-5001 | S | Offsite | Budget | LS | 1 | 0 | 15% | 0 | 0 |  | See Budget File (Further Negotiations with SWG Needed)
Electric | 33-7101 | S |  | Torrey Pines | LS | 1 | 436476 | 0% | 436476 | 436476 |  | See Budget File (Includes $34K in Hard Dig)
Secondary Conduit | 33-7102 | A |  | Allowance | LS | 0 | 0 | 0% | 0 | 0 |  | Included in budget for Onsite.
Bollards | 33-7103 | S |  | Allowance | LS | 1 | 15600 | 0% | 15600 | 15600
Cable TV | 33-8201 | S |  | N/A |  |  |  | 0% | 0 | 0
Phone | 33-8202 | S |  | N/A |  |  |  | 0% | 0 | 0
Off Site Water | 33-1001 | S | Offsite | Torrey Pines | LS | 1 | 540210 | 0% | 540210 | 540210 |  | See Budget File
Off Site Sewer | 33-3001 | S | Offsite | Torrey Pines | LS | 1 | 154740 | 0% | 154740 | 154740 |  | See Budget File
Off Site Storm Drain | 33-4001 | S | Offsite | Allowance | LS | 1 | 25000 | 0% | 25000 | 25000
Off Site Electric | 33-7101 | S | Offsite | Torrey Pines | LS | 1 | 33500 | 0% | 33500 | 33500 |  | See Budget File (Includes $35k in Hard Dig and street light rough).
Brigde Over Duct Creek Wash | 33 | [9 empty] | 1288500
Bridge |  |  | ON-SITE | Allowance | LS | 2 | 644250 | 0% | 644250 | 1288500
Other |  |  | ON-SITE | Allowance | LS | 0 | 0 | 0% | 0 | 0
Transportation | 34 | [9 empty] | 7500
Traffic Control | 34-4116 | A | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500
Electrical Power Generation | 48 | [9 empty] | 100000
Solar PV System | 48-1413 | S |  | Allowance | LS | 1 | 0 | 0% | 0 | 0
Solar PV Conduit | 48-1414 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000 |  | Increase allowance to account for EV new requirements.
Car Charging Stations | 48-1913 | A |  | Allowance | LS | 1 | 50000 | 0% | 50000 | 50000
Field Surveys, Staking | 49 | [9 empty] | 623010.75
Staking | 49-0601 | S |  | Pebble | LS | 17.25 | 9972 | 0% | 9972 | 172017 |  | Using Pebble Cost to Date as Benchmark.
Re Staking | 49-0602 | S |  | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000 |  | Using Pebble Cost to Date as Benchmark.
Certs and Verifications | 49-0603 | S |  | Allowance | LS | 1 | 5000 | 0% | 5000 | 5000 |  | Using Pebble Cost to Date as Benchmark.
Slab Testing | 49-0801 | S |  | Pebble | LS | 17.25 | 5775 | 0% | 5775 | 99618.75 |  | Using Pebble Cost to Date as Benchmark.
Grading Testing | 49-0802 | S |  | Pebble | LS | 17.25 | 7500 | 0% | 7500 | 129375 |  | Using Pebble Cost to Date as Benchmark.
Other Testing | 49-0803 | S |  | Pebble | LS | 17.25 | 7500 | 0% | 7500 | 129375 |  | Using Pebble Cost to Date as Benchmark.
Masonry Testing | 49-0807 | S |  | Allowance | LS | 17.25 | 1000 | 0% | 1000 | 17250 |  | Using Pebble Cost to Date as Benchmark.
Pavement Testing | 49-0808 | S |  | Allowance | LS | 17.25 | 1000 | 0% | 1000 | 17250 |  | Using Pebble Cost to Date as Benchmark.
Third Party Inspections | 49-0950 | S |  | Pebble | LS | 17.25 | 2500 | 0% | 2500 | 43125 |  | Using Pebble Cost to Date as Benchmark.
Bid Risk & BABA | Bid Risk | [9 empty] | 1062580.8151
BABA | [5 empty] | 0% |  |  |  | 0
Bid Risk | [5 empty] | 2% |  |  |  | 1062580.8151
FFE | FFE Extra | [9 empty] | 2460200
Golf Carts | 11-1001 | S |  | Allowance | LS | 1 | 10000 | 0% | 10000 | 10000
Convenience Store Equipment | 11-2101 | S |  | N/A |  |  |  | 0% | 0 | 0
Pet Wash | 11-2102 | S |  | N/A | LS | 0 | 21000 | 0% | 21000 | 0
Office Equipment | 11-2801 | S |  | Allowance | LS | 1 | 22000 | 0% | 22000 | 22000
Gym Exercise Equipment | 11-6613 | S |  | Pebble | LS | 3 | 45000 | 0% | 45000 | 135000
Playground / Basketball Hoop | 11-6813 | S |  | N/A |  |  |  | 0% | 0 | 0
Maintenance Shop Equipment | 11-8101 | S |  | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000
Maintenance Shop Start Up Supplies | 11-8102 | S |  | Alowance | LS | 1 | 5000 | 0% | 5000 | 5000
Fixed Asset Misc. | 11-8105 | S |  | N/A |  |  |  | 0% | 0 | 0
Interior Furniture | 12-5000 | S |  | Allowance | LS | 3 | 650000 | 0% | 650000 | 1950000
Exterior Furniture | 12-5483 | S |  | Allowance | LS | 3 | 100000 | 0% | 100000 | 300000
Rec Building TV Media Computer | 27-2201 | S |  | Allowance | LS | 1 | 20000 | 0% | 20000 | 20000
Rec Building Telephone System | 27-3202 | S |  | Allowance | LS | 1 | 2000 | 0% | 2000 | 2000
Maintenance Radios | 27-3243 | S |  | Allowance | LS | 1 | 1200 | 0% | 1200 | 1200
Construction Contingency | 55 | [9 empty] | 3004755.9643
Construction Contingency | 55-9800 |  |  |  |  | 5% |  |  |  | 3004755.9643
Sub Bonds | 50 | [9 empty] | 736473.6804
Sub Bonds | 50-9950 | B |  |  |  | 1.3% |  |  |  | 736473.6804
GL Insurance | 50 | [9 empty] | 387191.8904
GL Insurance | 50-0001 |  |  |  | 3.03 per $1,000 | 3.03 |  |  |  | 193595.9452
Misc. | 50-0001 |  |  |  | 5% of GL Ins. | 5% |  |  |  | 9679.7973
Umbrella | 50-0001 |  |  |  | 95% of GL Ins. | 95% |  |  |  | 183916.1479
Contractor Fee | 56 | [9 empty] | 5137883.2657
Overhead | 56 |  |  |  |  | 2% |  |  |  | 1284470.8164
Contractor Fee | 56 |  |  |  |  | 6% |  |  |  | 3853412.4493
Total Hard Costs | [10 empty] | 69361424.0868
0
General Requirements | 01 |  |  | 3443297.7151 | [8 empty] | 6% General Conditions
Existing Conditions | 02 |  |  | 16000 | [8 empty] | 55589240.7558
Concrete | 03 |  |  | 2697268.48 | [8 empty] | 3335354.4454
Parking Garage | 03-G |  |  | #N/A | [8 empty] | 111178.4815
Masonry | 04 |  |  | 207800
Metals | 05 |  |  | 349806
Wood, Plastics, & Composites | 06 |  |  | 8880630.8
Thermal & Moisture Protection | 07 |  |  | 2198832.23
Openings | 08 |  |  | 516935.7895
Finishes | 09 |  |  | 5549735.2782
Specialties | 10 |  |  | 424275
Equipment | 11 |  |  | 1253975.6087
Furnishings | 12 |  |  | 2274288.4959
Special Construction | 13 |  |  | 821104
Trash Chute | 13-G |  |  | 0
Conveying Equipment | 14 |  |  | 439560
Fire Suppression | 21 |  |  | 1029020.45
Plumbing | 22 |  |  | 3852664.6316
HVAC | 23 |  |  | 3939796.656
Electrical | 26 |  |  | 3964403.0774
Communications | 27 |  |  | 217168.19
Electronic Safety & Security | 28 |  |  | 942311.9738
Earthwork | 31 |  |  | 1264963.85
Exterior Improvements | 32 |  |  | 7051690.4948
Utilities | 33 |  |  | 3217799
Transportation | 34 |  |  | 7500
Electrical Power Generation | 48 |  |  | 100000
Field Surveys, Staking | 49 |  |  | 623010.75
5th Story Factor |  |  |  | #N/A
Bid Risk |  |  |  | 0
FFE |  |  |  | 2460200
Construction Contingency | 55 |  |  | 3004755.9643
Sub Bonds | 50 |  |  | 736473.6804
GL Insurance | 50 |  |  | 387191.8904
Contractor Fee | 56 |  |  | 5137883.2657
Total Hard Costs |  |  |  | 69361424.0868
#N/A
Cost Code
Total
01 - General Requirements | 01 |  |  |  | 3443297.7151
02 - Existing Conditions | 02 |  |  |  | 16000
03 - Concrete | 03 |  |  |  | 2697268.48
04 - Masonry | 04 |  |  |  | 207800
05 - Metals | 05 |  |  |  | 349806
06 - Wood, Plastics, & Composites | 06 |  |  |  | 8880630.8
07 - Thermal & Moisture Protection | 07 |  |  |  | 2198832.23
08 - Openings | 08 |  |  |  | 516935.7895
09 - Finishes | 09 |  |  |  | 5549735.2782
10 - Specialties | 10 |  |  |  | 424275
11 - Equipment | 11 |  |  |  | 1253975.6087
12 - Furnishings | 12 |  |  |  | 2274288.4959
13 - Special Construction | 13 |  |  |  | 821104
14 - Conveying Equipment | 14 |  |  |  | 439560
21 - Fire Suppression | 21 |  |  |  | 1029020.45
22 - Plumbing | 22 |  |  |  | 3852664.6316
23 - HVAC | 23 |  |  |  | 3939796.656
26 - Electrical | 26 |  |  |  | 3964403.0774
27 - Communications | 27 |  |  |  | 217168.19
28 - Electronic Safety & Security | 28 |  |  |  | 942311.9738
31 - Earthwork | 31 |  |  |  | 1264963.85
32 - Exterior Improvements | 32 |  |  |  | 7051690.4948
33 - Utilities | 33 |  |  |  | 4506299
34 - Transportation | 34 |  |  |  | 7500
48 - Electrical Power Generation | 48 |  |  |  | 100000
49 - Field Surveys, Staking | 49 |  |  |  | 623010.75
Bid Risk | Bid Risk |  |  |  | 1062580.8151
FFE Extra | FFE Extra |  |  |  | 2460200
50 - Sub Bonds | 50 |  |  |  | 1123665.5708
55 - Construction Contingency | 55 |  |  |  | 3004755.9643
56 - Contractor Fee | 56 |  |  |  | 5137883.2657
Total |  |  |  |  | 69361424.0868
check |  |  |  |  | 0
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units | 09-6001 |  |  |  | 289071.54 | 09
Common Wood | 09-6401 |  |  |  | 0 | 09
Common Vinyl | 09-6517 |  |  |  | 0 | 09
Hall Flooring | 09-6520 |  |  |  | 133807.17 | 09
Hall Flooring - Elevators | 09-6520A |  |  |  | 4500 | 09
Common - Plank | 09-6521 |  |  |  | 0 | 09
Common - VCT | 09-6522 |  |  |  | 0 | 09
Common - Rubber Floor | 09-6566 |  |  |  | 0 | 09
Common - Carpet | 09-6802 |  |  |  | 33266.5714 | 09
Appliances | 11-3013 |  |  |  | 1253975.6087 | 11
Blinds | 12-2100 |  |  |  | 165040.8158 | 12
Total Appliances, Flooring & Blinds |  |  |  |  | 1879661.7059
Site Work
Major Categories
Existing Conditions | 2 |  |  |  | 16000
Earthwork | 31 |  |  |  | 1264963.85
Exterior Improvements | 32 |  |  |  | 7051690.4948
Utilities | 33 |  |  |  | 4506299
Transportation | 34 |  |  |  | 7500
Electrical Power Generation | 48 |  |  |  | 100000
Minor Categories
Carports | 13-3401 |  |  |  | 569055
Dumpsters | 06-0111 |  |  |  | 0
Gazebo |  |  |  |  | 0
Other Site |  |  |  |  | 0
Pools and Spas | 13-1113 |  |  |  | 245000
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Pump House Concrete | 03-3101 |  |  |  | 2103627.6
Total Site Work |  |  |  |  | 15864135.9448
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  | already included in 32
Offsite Paving | 32-1216OFFSITE |  |  | already included in 32
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  | already included in 32
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  | already included in 32
Storm Drain | 33-4001OFFSITE |  |  | already included in 33
Off Site Water | 33-1001OFFSITE |  |  | already included in 33
Off Site Sewer | 33-3001OFFSITE |  |  | already included in 33
Off Site Electric | 33-7101OFFSITE |  |  | already included in 33
Traffic Control | 34-4116OFFSITE |  |  | already included in 34
Pump House Concrete | 03-3101
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  |  | 0
Offsite Paving | 32-1216OFFSITE |  |  |  | 0
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  |  | 0
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  |  | 0
Off Site Water | 33-1001OFFSITE |  |  |  | 0
Off Site Sewer | 33-3001OFFSITE |  |  |  | 0
Storm Drain | 33-4001OFFSITE |  |  |  | 0
Off Site Electric | 33-7101OFFSITE |  |  |  | 0
Traffic Control | 34-4116OFFSITE |  |  |  | 0
Other Ineligible Costs
Major Categories
Parking Garage | 03-G |  |  |  | 0
Minor Categories
Pump House Concrete | 03-3101 |  |  |  | 2103627.6
Pool Area Shower Concrete | 03-3105 |  |  |  | 2500
Cabana Concrete | 03-3107 |  |  |  | 0
Pool Equipment Foundation | 03-3108 |  |  |  | 0
Deck Concrete | 03-5001 |  |  |  | 60702.72
Masonry Veneer Pool Area | 04-4305 |  |  |  | 5000
Pool Equipment Shower Stone | 04-4306 |  |  |  | 9000
Cabana Iron | 05-7004 |  |  |  | 0
Pool Equipment Gate | 05-7005 |  |  |  | 1950
Cabana Framing | 06-1109 |  |  |  | 0
BBQ Framing | 06-1110 |  |  |  | 10000
Fireplace Framing | 06-1111 |  |  |  | 0
Trellis | 06-1114 |  |  |  | 0
BBQ Trim | 06-2006 |  |  |  | 4800
Cabana Roofing | 07-3002 |  |  |  | 7500
Pump House Roofing | 07-3002 |  |  |  | 7500
Pool Equipment Windows | 08-5303 |  |  |  | 0
Pool Glass Walls | 08-8001 |  |  |  | 0
Stucco - Pump House | 09-2423 |  |  |  | 841299.3587
Stucco - Cabana | 09-2423 |  |  |  | 841299.3587
Stucco - Pool Wall | 09-2423 |  |  |  | 841299.3587
Unit Carport Signs | 10-1401 |  |  |  | 56265
Fire Places - Pool Area | 10-3200 |  |  |  | 0
BBQ Units | 10-3355 |  |  |  | 13440
BBQ Top | 12-3609 |  |  |  | 24000
Pools and Spas | 13-1113 |  |  |  | 245000
Carports | 13-3401 |  |  |  | 569055
Pool Equipment Cover | 13-3402 |  |  |  | 7049
Pool and Spa Lifts | 14-4101 |  |  |  | 13000
Pool Area | 22-1003 |  |  |  | 24612
Pool Equipment | 22-1007 |  |  |  | 6000
Carports Electrical | 26-1001 |  |  |  | 3578225.0774
Carport Fixtures | 26-5001 |  |  |  | 225925
Cabana Electrical | 26-1001 |  |  |  | 3578225.0774
Cabana Fixtures | 26-5004 |  |  |  | 0
Pool Lighting Electrical | 26-1004 |  |  |  | 20000
Pool Lighting Fixtures | 26-5603 |  |  |  | 12500
Pool Equipment Electrical | 26-1007 |  |  |  | 2500
Pump House Electrical | 26-1001 |  |  |  | 3578225.0774
Pump House Fixtures | 26-5001 |  |  |  | 225925
Pool Decks | 32-1402 |  |  |  | 0
Pool Hardscape | 32-1626 |  |  |  | 10000
Pool Fence | 32-3106 |  |  |  | 24900
Pool Walls | 32-3208 |  |  |  | 11000
Pet Wash | 11-2102 |  |  |  | 0
Office Equipment | 11-2801 |  |  |  | 22000
Gym Exercise Equipment | 11-6613 |  |  |  | 135000
Playground / Basketball Hoop | 11-6813 |  |  |  | 0
Rec Building TV Media Computer | 27-2201 |  |  |  | 23000
Rec Building Telephone System | 27-3202 |  |  |  | 2000

## Combined - vErik
Project Details |  |  | Unit Breakdown |  |  |  | Breakdown Per Building |  |  |  |  | List of Take offs |  |  | List of Take offs
Project | Robindale & 215 |  | Unit Type | Number | % |  | Bldg. | Unit | GSF |  |  | Slab SF | 164597 | GSF / 2 | 1x1 Counter tops | 14292 | SF
Budget Level | Level 1 |  | Studios | 0 | 0% |  | 1 | 102 | 94252 |  |  | Elevators | 6 | Count Est. | 2x1 Counter Tops | 10833 | SF
Product | Senior |  | 1 Br - 1 Ba | 218 | 60.06% |  | 2 | 127 | 113176 |  |  | Trash Encl. | 10.5429 | Count Est. 1 per 35 Units | 1x1 Cab Boxes | 0 | Boxes
Start Date | 2025-06-01 |  | 2 Br - 1 Ba | 145 | 39.94% |  | 3 | 134 | 121766 |  |  | Stairs | 16 | Count | 2x1 Cab Boxes | 0 | Boxes
Timline | 24 |  | 2 Br - 2 Ba | 0 | 0% |  | Totals | 363 | 329194 |  |  | Pool | 2 |  | 1x1 Decks | 3984 | SF
Floors | Bldg 1 = 2, Bldg 2 =2, Bldg 3=2 |  | 3 Br - 2 Ba | 0 | 0% | [6 empty] | Gym | 2 |  | 2x1 Decks | 0 | SF
Bldg SF | 329194 |  | Totals | 363 | 100% |  | TOTAL COST |  | 69293293.7366 |  |  | Iron Rail | 2682.74 | Prorate to Bruner SF | Pavers | 0 | SF
Acres | 17.25 |  | Parking |  |  |  | PER UNIT |  | 190890.6164 |  |  | Roofing | 1693.23 | Square | Site Landscaping | 77100 | Building 1 SF
Site SF | 751410 |  | Garage Parking |  | 0 |  | PER GSF |  | 210.4938 |  |  | Stucco | 18377.3333 | Square Yard | Site Landscaping | 94000 | Building 2 SF
Buildings | 3 |  | Cover Parking |  | 0 | [6 empty] | Liavable Area | 282874 | SF | Site Landscaping | 97500 | Building 3 SF
Reports Available |  |  | Open Parking |  | 706 | [6 empty] | Carports | 423.6 | 60% of spaces (Bruner) | Pool Fence | 254
Site Evaluation Report (GCW) |  |  | Accessible Parking |  | 8 | [6 empty] | Seal Coat | 285447 | Asphalt SF | Dog Park Fence | 255
Soils Report (Universal) |  |  | Private Garages |  | 0 | [6 empty] | Building Perimeter | 1699.5 | Bldg 1 LF | Corridor | 9315 | Building 1 SF
Alta Survey (Wallace) |  |  | Total Parking Provided |  | 706 | [6 empty] | Building Perimeter | 1815 | Bldg 2 LF | Corridor | 12738 | Building 2 SF
Plans |  |  | Parking Ratio |  | 1.9449 | [6 empty] | Building Perimeter | 2392.5 | Bldg 3 LF | Corridor | 14079 | Building 3 SF | 219566.7725
[15 empty] | Pool Deck | 7800 | SF
Description | Cost Code | Cost Category | Subjob | Source | Unit Meas. | Quantity | Unit Cost | Escalation % | T. Unit Cost | Sub Total | Total | Description / Details
General Requirements | 01 | [9 empty] | 3514986.3 | [8 empty] | 3514986.3 | 0 | 0
General Requirements | 01 | S |  |  | Mo | 42 | 83690.15 | 0% | 83690.15 | 3514986.3 | [8 empty] | 3514986.3 |  | 0 | 0
Existing Conditions | 02 | [9 empty] | 16000 | [8 empty] | 16000 | 0 | 0
Potholing | 02-3213 | S | ON-SITE | Allowance |  | 1 | 16000 | 0% | 16000 | 16000 | [8 empty] | 16000 |  | 0 | 0
Concrete | 03 | [9 empty] | 2594295.6786 | [6 empty] | 7146.8201 |  | 2594295.6786 | 0 | 0
Slabs | 03-3101 | S | BUILDING | Torrey Pines | SF | 164597 | 11.99 | 0% | 11.99 | 1973518.03 | [8 empty] | 1973518.03 |  | 0 | 0
Deepened Footings | 03-3101 | S | BUILDING | N/A |  | 0 | 0 | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Concrete Slab Repairs | 03-3101 | RR | BUILDING | Allowance | LS | 1 | 15000 | 0% | 15000 | 15000 | [8 empty] | 15000 |  | 0 | 0
Pump House Concrete | 03-3101 | S | PUMPHOUSE | Torrey Pines | SF | 600 | 11.99 | 0% | 11.99 | 7194 | [8 empty] | 7194 |  | 0 | 0
Trash Enclosure Concrete | 03-3102 | S | OTHER SITE | Russell IV | Count | 10.5429 | 2698 | 0% | 2698 | 28444.6286 | [8 empty] | 28444.6286 |  | 0 | 0
Pool Area Shower Concrete | 03-3105 | S | POOL AREA | Torrey Pines | LS | 3 | 2500 | 0% | 2500 | 7500 | [8 empty] | 7500 |  | 0 | 0
Cabana Concrete | 03-3107 | S | POOL AREA | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Equipment Foundation | 03-3108 | S | POOL EQUIP | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Lightweight Concrete | 03-3116 | S | BUILDING | Torrey Pines | SF | 164597 | 2.94 | 0% | 2.94 | 483915.18 | [8 empty] | 483915.18 |  | 0 | 0
Deck Concrete | 03-5001 | S | BUILDING | Torrey Pines | SF | 3984 | 19.76 | 0% | 19.76 | 78723.84 | [8 empty] | 78723.84 |  | 0 | 0
Parking Garage | 03-G | [9 empty] | 0 | [8 empty] | 0 | 0 | 0
Parking Garage Structure |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Core Slab Precast Concrete |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Concrete Slab on Grade |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Concrete Topping Slab 4" / Level |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Electrical |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Dry Sprinklers |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Mechanical Ventilation |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Stairs and Railings |  | S |  | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Masonry | 04 | [9 empty] | 174094.2857 | [8 empty] | 174094.2857 | 0 | 0
Elevator Shaft | 04-2201 | S | BUILDING | Torrey Pines | Count | 6 | 19000 | 0% | 19000 | 114000 | [8 empty] | 114000 |  | 0 | 0
Trash Enclosure | 04-2202 | S | OTHER SITE | Torrey Pines | Count | 10.5429 | 5700 | 0% | 5700 | 60094.2857 | [8 empty] | 60094.2857 |  | 0 | 0
Masonry Veneer | 04-4301 | S | ON-SITE | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Masonry Veneer Pool Area | 04-4305 | S | POOL AREA | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Eq. Shower Stone | 04-4306 | S | POOL EQUIP | N/A |  |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Metals | 05 | [9 empty] | 413758.9122 | [8 empty] | 413758.9122 | 0 | 0
Structural Steel | 05-1201 | S | BUILDING | N/A |  |  | 186154 | 0% | 186154 | 0 |  | Per Derek No Structural Steel in Common Areas | [6 empty] | 0 |  | 0 | 0
Elevator Shaft Iron | 05-1202 | S | BUILDING | Russell IV | Count | 6 | 5990 | 0% | 5990 | 35940 | [8 empty] | 35940 |  | 0 | 0
Stair Handrails | 05-5201 | S | BUILDING | Russell IV | LS | 16 | 7833.3333 | 0% | 7833.3333 | 125333.3333 | [8 empty] | 125333.3333 |  | 0 | 0
Garage Stair Railings | 05-5201 | S | BUILDING | N/A |  |  | 0 | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Cabana Iron | 05-7004 | S | POOL AREA | N/A |  |  | 0 | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Equipment Gate | 05-7005 | S | POOL EQUIP | Russell IV | Count | 2 | 1950 | 0% | 1950 | 3900 | [8 empty] | 3900 |  | 0 | 0
Iron Railings | 05-7300 | S | BUILDING | Russell IV | Linear Foot | 2682.74 | 92.6611 | 0% |  | 248585.5788 | [8 empty] | 248585.5788 |  | 0 | 0
Cable Railings | 05-7316 | S | COMMON AREA | N/A |  |  | 0 | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Wood, Plastics, & Composites | 06 | [9 empty] | 8101853.52 | [8 empty] | 8101853.52 | 0 | 0
Dumpsters | 06-0111 | S | DUMPSTERS | Torrey Pines | Unit | 363 | 79 | 0% | 79 | 28677 | [8 empty] | 28677 |  | 0 | 0
Framing | 06-1100 | S | BUILDING | Torrey Pines | SF | 329194 | 19.92 | 0% | 19.92 | 6557544.48 | [8 empty] | 6557544.48 |  | 0 | 0
Framing - Crane | 06-1100 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Cabana Framing | 06-1109 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
BBQ Framing | 06-1110 | S | COMMON AREA | Pebble | LS | 4 | 2810 | 0% | 2810 | 11240 | [8 empty] | 11240 |  | 0 | 0
Fireplace Framing | 06-1111 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Trellis | 06-1114 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Equipment Framing | 06-1114 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Finish Carpentry - Units | 06-2001 | S | BUILDING | Pebble | Unit | 363 | 3081 | 0% | 3081 | 1118403 | [8 empty] | 1118403 |  | 0 | 0
Finish Carpentry - Common | 06-2001 | S | COMMON AREA | Pebble | SF | 329194 | 1.16 | 0% | 1.16 | 381865.04 | [8 empty] | 381865.04 |  | 0 | 0
BBQ Trim | 06-2006 | S | COMMON AREA | Pebble | LS | 4 | 1031 | 0% |  | 4124 | [8 empty] | 4124 |  | 0 | 0
Shutters | 06-4919 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Thermal & Moisture Protection | 07 | [9 empty] | 2004765.67 | [8 empty] | 2004765.67 | 0 | 0
Insulation | 07-2101 | S | BUILDING | Torrey Pines | SF | 329194 | 2.54 | 0% | 2.54 | 836152.76 | [8 empty] | 836152.76 |  | 0 | 0
Roofing | 07-3001 | S | BUILDING | Torrey Pines | Square | 1693.23 | 603 | 0% | 603 | 1021017.69 | [8 empty] | 1021017.69 |  | 0 | 0
Cabana Roofing | 07-3002 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pump House Roofing | 07-3002 | S | PUMPHOUSE | Allowance | LS | 1 | 6700 | 0% | 6700 | 6700 | [8 empty] | 6700 |  | 0 | 0
Pool Equipment Roofing | 07-3003 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Trash Enclosure Cover | 07-6101 | S | OTHER SITE | Torrey Pines | Count | 10.5429 | 7000 | 0% | 7000 | 73800 | [8 empty] | 73800 |  | 0 | 0
Pigeon Proofing | 07-7001 | S | BUILDING | Torrey Pines | SF | 329194 | 0.08 | 0% | 0.08 | 26335.52 | [8 empty] | 26335.52 |  | 0 | 0
Gutters and Downspouts | 07-7124 | S | BUILDING | Torrey Pines | SF | 329194 | 0.05 | 0% | 0.05 | 16459.7 | [8 empty] | 16459.7 |  | 0 | 0
Roof Ladders | 07-7210 | S | BUILDING | Torrey Pines | Count | 6 | 1550 | 0% | 1550 | 9300 |  | 2 Per building | [6 empty] | 9300 |  | 0 | 0
Roof Access Doors | 07-7233 | S | BUILDING | Torrey Pines | Count | 6 | 2500 | 0% | 2500 | 15000 |  | 2 Per building | [6 empty] | 15000 |  | 0 | 0
Roof Winch | 07-7250 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Openings | 08 | [9 empty] | 574050.3 | [8 empty] | 574050.3 | 0 | 0
Dumpsters | 08-0151 | S | DUMPSTERS |  | Per Unit | 363 | 79 | 0% | 79 | 28677 | [8 empty] | 28677 |  | 0 | 0
Entry Doors | 08-1001 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Common Doors | 08-1002 | S | COMMON AREA | Included |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pocket Doors - 3 Panel | 08-1002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Garage Doors | 08-3619 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Windows and Sliding Glass Doors | 08-5301 | S | BUILDING | Decatur | Per Unit | 363 | 1244.1 | 0% | 1244.1 | 451608.3 |  | Per Solar Industries include +10% Due to New Energy Star U Factor Requirement Less than or equall to 0.28 | [6 empty] | 451608.3 |  | 0 | 0
Windows Repair and Replacement | 08-5301 | RR | BUILDING | Allowance | Per Unit | 363 | 75 | 0% | 75 | 27225 | [8 empty] | 27225 |  | 0 | 0
Pool Equipment Windows | 08-5303 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Glass Walls | 08-8001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Fixed Glass | 08-8002 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Mirrors - LED | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Mirrors - LED Install | 08-8302 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Mirrors - Framed | 08-8301 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Mirrors - Polished Edges (Units) | 08-8301 | S | BUILDING | Russell IV | Unit | 363 | 180 | 0% | 180 | 65340 | [8 empty] | 65340 |  | 0 | 0
Mirrors - Polished Edges (Restrooms) | 08-8301 | S | BUILDING | Russell IV | Count | 6 | 200 | 0% | 200 | 1200 | [8 empty] | 1200 |  | 0 | 0
Finishes | 09 | [9 empty] | 5615983.3453 | [8 empty] | 5615983.3453 | 0 | 0
Cost Prep Labor | 09-0101 | S | BUILDING | Wigwam | SF | 329194 | 0.05 | 0% | 0.05 | 16459.7 | [8 empty] | 16459.7 |  | 0 | 0
Cost Prep Mat | 09-0102 | S | BUILDING | Wigwam | SF | 329194 | 0.08 | 0% | 0.08 | 26335.52 | [8 empty] | 26335.52 |  | 0 | 0
Clean Up - Final | 09-0103 | S | BUILDING | Wigwam | SF | 329194 | 0.6 | 0% | 0.6 | 197516.4 | [8 empty] | 197516.4 |  | 0 | 0
Clean Up - During Construction | 09-0104 | S | BUILDING | Wigwam | SF | 329194 | 0.36 | 0% | 0.36 | 118509.84 | [8 empty] | 118509.84 |  | 0 | 0
Dumpsters | 09-0113 | S | DUMPSTERS | Latest | Unit | 363 | 79 | 0% | 79 | 28677 | [8 empty] | 28677 |  | 0 | 0
Clean Up - Hauling Exterior | 09-0121 | S | ON-SITE | Wigwam |  |  | 0.11 | 0% | 0.11 | 36211.34 | [8 empty] | 36211.34 |  | 0 | 0
Stucco | 09-2423 | S | BUILDING | Torrey Pines | SY | 18377.3333 | 40.8187 | 0% | 40.8187 | 750138.3762 |  | TP cost & rough take off. | [6 empty] | 750138.3762 |  | 0 | 0
Stucco - Pump House | 09-2423 | A | PUMPHOUSE | Allowance | LS | 1 | 6000 | 0% | 6000 | 6000 | [8 empty] | 6000 |  | 0 | 0
Stucco - Walls | 09-2424 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Stucco - Pool Area | 09-2428 | A | POOL AREA | Allowance | LS | 2 | 2000 | 0% | 2000 | 4000 | [8 empty] | 4000 |  | 0 | 0
Stucco - Cabana | 09-2429 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Stucco - Pool Equipment | 09-2430 | S | POOL EQUIP | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Stucco - Repairs | 09-2423A | RR | BUILDING | Allowance | LS | 1 | 9000 | 0% | 9000 | 9000 | [8 empty] | 9000 |  | 0 | 0
Drywall | 09-2905 | S | BUILDING | Torrey Pines | SF | 329194 | 8.02 | 0% | 8.02 | 2640135.88 | [8 empty] | 2640135.88 |  | 0 | 0
Drywall - Repairs | 09-2905A | RR | BUILDING | Allowance | Unit | 363 | 85 | 0% | 85 | 30855 | [8 empty] | 30855 |  | 0 | 0
Tile Tubs and Showers | 09-3001 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Common Tile | 09-3002 | S | COMMON AREA | Russell IV | LS | 4 | 17191 | 0% | 17191 | 68764 | [8 empty] | 68764 |  | 0 | 0
Kitchen Backsplash | 09-3003 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Cabana Tile | 09-3008 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Flooring - Units | 09-6001 | S | BUILDING | Arzano | SF | 282874 | 1.83 | 0% | 1.83 | 517659.42 | [8 empty] | 517659.42 |  | 0 | 0
Common Wood | 09-6401 | S | COMMON AREA | Wigwam | LS | 3 | 30184 | 0% | 30184 | 90552 | [8 empty] | 90552 |  | 0 | 0
Common Vinyl | 09-6517 | S | COMMON AREA | Wigwam | LS | 3 | 1994 | 0% | 1994 | 5982 | [8 empty] | 5982 |  | 0 | 0
Hall Flooring | 09-6520 | S | COMMON AREA | Wigwam | SF | 329194 | 0.5 | 0% | 0.5 | 164597 | [8 empty] | 164597 |  | 0 | 0
Hall Flooring - Elevators | 09-6520A | A | COMMON AREA | Allowance | Count | 6 | 1500 | 0% | 1500 | 9000 | [8 empty] | 9000 |  | 0 | 0
Common - Plank | 09-6521 | S | COMMON AREA | Wigwam | SF | 329194 | 0.090909 | 0% | 0.090909 | 29926.6973 | [8 empty] | 29926.6973 |  | 0 | 0
Common - VCT | 09-6522 | S | COMMON AREA | Wigwam | SF | 329194 | 0.182 | 0% | 0.182 | 59913.308 | [8 empty] | 59913.308 |  | 0 | 0
Common - Rubber Floor (Ecore) | 09-6566 | S | COMMON AREA | Russell IV | SF | 2600 | 15.91 | 0% | 15.91 | 41366 |  | Per Derek 2 Gyms, 1,300 SF Each, Larger Gym | [6 empty] | 41366 |  | 0 | 0
Common - Carpet Stairs | 09-6802 | S | COMMON AREA | Wigwam | SF | 329194 | 0.0727 | 0% | 0.0727 | 23932.4038 | [8 empty] | 23932.4038 |  | 0 | 0
Hall Runner Install | 09-6803 | S | COMMON AREA | Russell IV | SF | 9033 | 1.5 | 0% | 1.5 | 13549.5 |  | Assumption of 25% of corridor SF. | [6 empty] | 13549.5 |  | 0 | 0
Hall Runner Materials | 09-6804 | S | COMMON AREA | Russell IV | SF | 9033 | 10 | 0% | 10 | 90330 |  | Assumption of 25% of corridor SF. | [6 empty] | 90330 |  | 0 | 0
Painting - Repairs | 09-9101A | RR | BUILDING | Allowance | Unit | 363 | 85 | 0% | 85 | 30855 | [8 empty] | 30855 |  | 0 | 0
Painting | 09-9101 | S | BUILDING | Torrey Pines | SF | 329194 | 1.84 | 0% | 1.84 | 605716.96 | [8 empty] | 605716.96 |  | 0 | 0
Painting - Walls | 09-9102 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Painting - Pool Area | 09-9106 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Wall Covering |  | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Walls - Specialty | 09-9110 | S | COMMON AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Specialties | 10 | [9 empty] | 373369 | [8 empty] | 373369 | 0 | 0
Entry Directory | 10-1300 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Unit Carport Signs | 10-1401 | S | CARPORT | Russell IV | Unit | 363 | 155 | 0% | 155 | 56265 | [8 empty] | 56265 |  | 0 | 0
Site Signage | 10-1404 | S | ON-SITE | Russell IV | LS | 1 | 5688 | 0% | 5688 | 5688 | [8 empty] | 5688 |  | 0 | 0
Entry Sign Letters | 10-1419 | S | ON-SITE | Russell IV | LS | 1 | 4500 | 0% | 4500 | 4500 | [8 empty] | 4500 |  | 0 | 0
Offsite Street Signs | 10-1454 | S | Offsite | Allowance | LS | 1 | 7000 | 0% | 7000 | 7000 | [8 empty] | 7000 |  | 0 | 0
Bath Accessories | 10-2816 | S | BUILDING | Russell IV | Unit | 363 | 17 | 0% | 17 | 6171 | [8 empty] | 6171 |  | 0 | 0
Shower Doors | 10-2919 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Fire Places | 10-3000 | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Fire Places - Pool Area | 10-3200 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
BBQ Units | 10-3355 | S | POOL AREA | Arzano | LS | 4 | 3360 | 0% | 3360 | 13440 | [8 empty] | 13440 |  | 0 | 0
Lock Boxes | 10-4116 | S | ON-SITE | Allowance | Count | 8 | 550 | 0% | 550 | 4400 | [8 empty] | 4400 |  | 0 | 0
Fire Extinguishers | 10-4416 | S | BUILDING | Russell IV | Unit | 363 | 79 | 0% | 79 | 28677 | [8 empty] | 28677 |  | 0 | 0
Mail Boxes | 10-5523 | S | BUILDING | Rainbow | Unit | 363 | 153 | 0% | 153 | 55539 | [8 empty] | 55539 |  | 0 | 0
Closet Shelving | 10-5723 | S | BUILDING | Pebble | Unit | 363 | 203 | 0% | 203 | 73689 | [8 empty] | 73689 |  | 0 | 0
Window Awnings Small | 10-7313 | S | BUILDING | Flamingo | Count | 20 | 2500 | 0% | 2500 | 50000 |  | Design Item Could be removed from Budget | [6 empty] | 50000 |  | 0 | 0
Window Awnings Large | 10-7313 | S | BUILDING | Flamingo | Count | 8 | 8500 | 0% | 8500 | 68000 |  | Design Item Could be removed from Budget | [6 empty] | 68000 |  | 0 | 0
Equipment | 11 | [9 empty] | 1160874 | [8 empty] | 1160874 | 0 | 0
Appliances | 11-3013 | S | BUILDING | Russell IV | Unit | 363 | 3198 | 0% | 3198 | 1160874 | [8 empty] | 1160874 |  | 0 | 0
Furnishings | 12 | [9 empty] | 2185435.16 | [8 empty] | 2185435.16 | 0 | 0
Dumpsters | 12-0131 | S | DUMPSTERS | Latest | Unit | 363 | 79 | 0% | 79 | 28677 | [8 empty] | 28677 |  | 0 | 0
Blinds | 12-2100 | S | BUILDING | Russell IV | Per Unit | 363 | 252.82 | 0% | 252.82 | 91773.66 | [8 empty] | 91773.66 |  | 0 | 0
Cabinets Units | 12-3531 | S | BUILDING | Pebble | Unit | 363 | 3114 | 0% | 3114 | 1130382 | [8 empty] | 1130382 |  | 0 | 0
Cabinet Common Areas | 12-3535 | S | BUILDING | Pebble | LS | 4 | 15700 | 0% | 15700 | 62800 | [8 empty] | 62800 |  | 0 | 0
Counter Tops Units | 12-3601 | S | BUILDING | Arzano | SF | 25125 | 29.62 | 0% | 29.62 | 744202.5 |  | Arzano cost and rough take off. | [6 empty] | 744202.5 |  | 0 | 0
Counter Tops Common Areas | 12-3605 | A | BUILDING | Allowance | LS | 3 | 28333.3333 | 0% |  | 85000 |  | Each building considered to have common area. Allowance per building. | [6 empty] | 85000 |  | 0 | 0
Counter Tops Pool Area | 12-3608 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
BBQ Top | 12-3609 | S | POOL AREA | Russell IV | LS | 4 | 10650 | 0% | 10650 | 42600 |  | Each building considered to have 1 BBQ. Allowance per building. | [6 empty] | 42600 |  | 0 | 0
Special Construction | 13 | [9 empty] | 1491093.7608 | [8 empty] | 1491093.7608 | 0 | 0
Pools and Spas | 13-1113 | S | POOL AREA | Torrey Pines | LS | 2 | 245000 | 0% | 245000 | 490000 | [8 empty] | 490000 |  | 0 | 0
Carports | 13-3401 | S | CARPORT | Russell IV | Count | 423.6 | 2330.3441 | 0% | 2330.3441 | 987133.7608 |  | 60% of parking spaces. | [6 empty] | 987133.7608 |  | 0 | 0
Pool Equipment Cover | 13-3402 | S | POOL EQUIP | Russell IV | Count | 2 | 6980 | 0% | 6980 | 13960 | [8 empty] | 13960 |  | 0 | 0
Trash Chute | 13-G | [9 empty] | 0 | [8 empty] | 0 | 0 | 0
Trash Chute | 13-G | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Conveying Equipment | 14 | [9 empty] | 670462 | [8 empty] | 670462 | 0 | 0
Elevator | 14-2400 | S | BUILDING | Decatur | Stop | 14 | 46033 | 0% | 46033 | 644462 | [8 empty] | 644462 |  | 0 | 0
Pool and Spa Lifts | 14-4101 | S | POOL AREA | Russell IV | Count | 4 | 6500 | 0% | 6500 | 26000 | [8 empty] | 26000 |  | 0 | 0
Fire Suppression | 21 | [9 empty] | 959276.94 | [8 empty] | 959276.94 | 0 | 0
Sprinkler Design | 21-0600 | S | BUILDING | Allowance | SF | 329194 | 0.06 | 0% | 0.06 | 19751.64 | [8 empty] | 19751.64 |  | 0 | 0
Sprinkler System | 21-1313 | S | BUILDING | Torrey Pines | SF | 329194 | 2.45 | 0% | 2.45 | 806525.3 | [8 empty] | 806525.3 |  | 0 | 0
Fire Pump | 21-3000 | S | PUMPHOUSE | Torrey Pines | Count | 1 | 133000 | 0% | 133000 | 133000 | [8 empty] | 133000 |  | 0 | 0
Plumbing | 22 | [9 empty] | 3882162 | [8 empty] | 3882162 | 0 | 0
1 Bathroom Unit | 22-1001 | S | BUILDING | Torrey Pines | Count | 363 | 10526 | 0% | 10526 | 3820938 | [8 empty] | 3820938 |  | 0 | 0
2 Bathroom Unit | 22-1001 | S | BUILDING | N/A |  | 0 |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Tiny Homes |  | S | BUILDING | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Area | 22-1003 | S | POOL AREA | Russell IV | LS | 2 | 24612 | 0% | 24612 | 49224 | [8 empty] | 49224 |  | 0 | 0
Pool Equipment | 22-1007 | S | POOL EQUIP | Allowance | LS | 2 | 6000 | 0% | 6000 | 12000 | [8 empty] | 12000 |  | 0 | 0
HVAC | 23 | [9 empty] | 3888782.7 | [8 empty] | 3888782.7 | 0 | 0
HVAC Standard | 23-3001 | S | BUILDING | Torrey Pines | Unit | 363 | 10712.9 | 0% | 10712.9 | 3888782.7 |  | Enix include 10% for New Refrigerent Upgrade to R-454B | [6 empty] | 3888782.7 |  | 0 | 0
Electrical | 26 | [9 empty] | 3679076.58 | [8 empty] | 3679076.58 | 0 | 0
Electrical | 26-1001 | S | BUILDING | Torrey Pines | SqFt | 329194 | 9.27 | 0% | 9.27 | 3051628.38 | [8 empty] | 3051628.38 |  | 0 | 0
Electrical Fixtures | 26-5001 | S | BUILDING | Russell IV | Unit | 363 | 594 | 0% | 594 | 215622 | [8 empty] | 215622 |  | 0 | 0
Building Electrical Fixtures | 26-5002 | S | BUILDING | Russell IV | Unit | 363 | 119 | 0% | 119 | 43197 | [8 empty] | 43197 |  | 0 | 0
Hall Lighting Fixtures | 26-5003 | S | BUILDING | Russell IV | Unit | 363 | 112 | 0% | 112 | 40656 | [8 empty] | 40656 |  | 0 | 0
Carports Electrical | 26-1001 | S | CARPORT | Russell IV | Space | 423.6 | 138 | 0% | 138 | 58456.8 | [8 empty] | 58456.8 |  | 0 | 0
Carport Fixtures | 26-5001 | S | CARPORT | Russell IV | Space | 423.6 | 24 | 0% | 24 | 10166.4 | [8 empty] | 10166.4 |  | 0 | 0
Cabana Electrical | 26-1001 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Cabana Fixtures | 26-5004 | S | POOL AREA | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Street Lights | 26-5613 | S | Offsite | Budget | Count | 6 | 25000 | 0% | 25000 | 150000 | [8 empty] | 150000 |  | 0 | 0
Site Lighting Electrical | 26-1005 | S | ON-SITE | Russell IV | Acre | 17.25 | 1000 | 0% | 1000 | 17250 | [8 empty] | 17250 |  | 0 | 0
Site Lighting Fixtures | 26-5602 | S | ON-SITE | Russell IV | Acre | 17.25 | 1000 | 0% | 1000 | 17250 | [8 empty] | 17250 |  | 0 | 0
Pool Lighting Electrical | 26-1004 | S | POOL AREA | Russell IV | LS | 2 | 17000 | 0% | 17000 | 34000 | [8 empty] | 34000 |  | 0 | 0
Pool Lighting Fixtures | 26-5603 | S | POOL AREA | Russell IV | LS | 2 | 11000 | 0% | 11000 | 22000 | [8 empty] | 22000 |  | 0 | 0
Pool Equipment Electrical | 26-1007 | S | POOL EQUIP | Russell IV | LS | 2 | 2000 | 0% | 2000 | 4000 | [8 empty] | 4000 |  | 0 | 0
Pump House Electrical | 26-1001 | S | PUMPHOUSE | Russell IV | LS | 1 | 14250 | 0% | 14250 | 14250 | [8 empty] | 14250 |  | 0 | 0
Pump House Fixtures | 26-5001 | S | PUMPHOUSE | Russell IV | LS | 1 | 600 | 0% | 600 | 600 | [8 empty] | 600 |  | 0 | 0
Communications | 27 | [9 empty] | 198524.46 | [8 empty] | 198524.46 | 0 | 0
TV and Media | 27-2201 | A | BUILDING | Allowance | LS | 3 | 900 | 0% | 900 | 2700 |  | Per Building | [6 empty] | 2700 |  | 0 | 0
DAS System | 27-3010 | S | BUILDING | Pebble | SF | 329194 | 0.59 | 0% | 0.59 | 194224.46 | [8 empty] | 194224.46 |  | 0 | 0
Pool ADA Phone | 27-3201 | S | POOL AREA | N/A | LS | 2 | 800 | 0% | 800 | 1600 |  | Per Pool | [6 empty] | 1600 |  | 0 | 0
Electronic Safety & Security | 28 | [9 empty] | 908865 | [8 empty] | 908865 | 0 | 0
Security System | 28-1001 | S | BUILDING | Russell IV | Unit | 363 | 580 | 0% | 580 | 210540 | [8 empty] | 210540 |  | 0 | 0
Site Security System | 28-2001 | S | ON-SITE | Russell IV | Unit | 363 | 327 | 0% | 327 | 118701 | [8 empty] | 118701 |  | 0 | 0
Fire Alarm / Two Way Comm AOR | 28-4601 | S | BUILDING | Torrey Pines | Unit | 363 | 1596.7603 | 0% |  | 579624 | [8 empty] | 579624 |  | 0 | 0
Earthwork | 31 | [9 empty] | 1317559.3375 | [8 empty] | 1317559.3375 | 0 | 0
Construction Water | 31-0121 | S | ON-SITE | Wigwam | Acre | 17.25 | 6331.55 | 0% | 6331.55 | 109219.2375 | [8 empty] | 109219.2375 |  | 0 | 0
Dust Control | 31-0122 | S | ON-SITE | Wigwam | Acre | 17.25 | 3485.6 | 0% | 3485.6 | 60126.6 | [8 empty] | 60126.6 |  | 0 | 0
Demolition | 31-0505 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Rock Dirt Haul Off | 31-1492 | S | ON-SITE | Budget | LS | 2 | 62500 | 0% |  | 125000 |  | See Budget File | [6 empty] | 125000 |  | 0 | 0
Mass Grading | 31-2201 | S | ON-SITE | Budget | LS | 2 | 330561 | 0% |  | 661122 |  | See Budget File | [6 empty] | 661122 |  | 0 | 0
Fine Grade | 31-2216 | S | ON-SITE | Budget | LS | 2 | 8707 | 0% |  | 17414 |  | See Budget File | [6 empty] | 17414 |  | 0 | 0
Hard Dig | 31-2319 | S | ON-SITE | Budget | LS | 2 | 150000 | 0% |  | 300000 |  | See Budget File | [6 empty] | 300000 |  | 0 | 0
Dewatering | 31-2322 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Storm Water Prevention | 31-2501 | S | ON-SITE | Wigwam | Acre | 17.25 | 2590 | 0% | 2590 | 44677.5 | [8 empty] | 44677.5 |  | 0 | 0
Exterior Improvements | 32 | [9 empty] | 6058984.0669 | [8 empty] | 6212777.8154 | 0 | 153793.7485
Bond Repair | 32-0100 | RR | ON-SITE | Russell IV | LS | 2 | 5000 | 0% |  | 10000 | [8 empty] | 10000 |  | 0 | 0
Street Cleaning | 32-0111 | S | OTHER SITE | Russell IV | LS | 2 | 7500 | 0% |  | 15000 | [8 empty] | 15000 |  | 0 | 0
Asphalt Sawcut and Removal | 32-0506 | S | ON-SITE | Budget | LS | 2 | 11250 | 0% |  | 22500 |  | See Budget File | [6 empty] | 22500 |  | 0 | 0
Paving | 32-1216 | S | ON-SITE | Budget | LS | 2 | 372987.97 | 0% |  | 745975.94 |  | See Budget File | [6 empty] | 745975.94 |  | 0 | 0
Seal Coat | 32-1236 | S | ON-SITE | Russell IV | SF | 285447 | 0.15 | 0% | 0.15 | 42817.05 | [8 empty] | 42817.05 |  | 0 | 0
Pavers | 32-1401 | S | N/A | Russell IV |  |  | 7.5 | 0% | 7.5 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Decks | 32-1402 | S | POOL AREA | Russell IV | SF | 15600 | 7.5 | 0% | 7.5 | 117000 | [8 empty] | 117000 |  | 0 | 0
Curbs and Gutters | 32-1613 | S | ON-SITE | Budget | LS | 2 | 58143.5 | 0% |  | 116287 |  | See Budget File | [6 empty] | 116287 |  | 0 | 0
Tack On Curb | 32-1614 | S | ON-SITE | Budget | LS | 2 | 48966 | 0% |  | 97932 |  | See Budget File | [6 empty] | 97932 |  | 0 | 0
Concrete Flatwork | 32-1623 | S | ON-SITE | Budget | LS | 2 | 147951 | 0% |  | 295902 |  | See Budget File | [6 empty] | 295902 |  | 0 | 0
Bus Pad | 32-1625 | S | OTHER SITE | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pool Hardscape | 32-1626 | S | POOL AREA | Russell IV | LS | 2 | 9660 | 0% | 9660 | 19320 | [8 empty] | 19320 |  | 0 | 0
Street Signs / Striping | 32-1700 | S | ON-SITE | Russell IV | Acre | 17.25 | 2476 | 0% | 2476 | 42711 | [8 empty] | 42711 |  | 0 | 0
Walls Iron | 32-3101 | S | ON-SITE | Budget | LS | 2 | 92900 | 0% |  | 185800 |  | See Budget File | [6 empty] | 185800 |  | 0 | 0
Trash Enclosure Iron Gates | 32-3103 | S | OTHER SITE | Budget | Count | 10.5429 | 2485 | 0% | 2485 | 26199 | [8 empty] | 26199 |  | 0 | 0
Site Railings | 32-3104 | A | OTHER SITE | Allowance | LS | 2 | 12500 | 0% |  | 25000 | [8 empty] | 25000 |  | 0 | 0
Dog Run Fence | 32-3105 | S | ON-SITE | Torrey Pines | LF | 510 | 70 | 0% | 70 | 35700 |  | Per Derek 2 Dog Parks | [6 empty] | 35700 |  | 0 | 0
Pool Fence | 32-3106 | S | POOL AREA | Budget | LF | 508 | 75 | 0% | 75 | 38100 |  | Per Derek (2) Pools | [6 empty] | 38100 |  | 0 | 0
Pool Fence Gates | 32-3106 | S | POOL AREA | Budget | Count | 4 | 1950 | 0% | 1950 | 7800 |  | Per Derek (2) Pools | [6 empty] | 7800 |  | 0 | 0
Entry Security Gates | 32-3111 | S | ON-SITE | N/A |  |  | 96000 | 0% | 96000 | 0 | [8 empty] | 0 |  | 0 | 0
Entry Security Gates Electrical | 32-3112 | S | ON-SITE | N/A |  |  | 3555 | 0% | 3555 | 0 | [8 empty] | 0 |  | 0 | 0
Entry Gate Transmitters | 32-3113 | S | ON-SITE | N/A |  |  | 44 | 0% | 44 | 0 | [8 empty] | 0 |  | 0 | 0
Entry Gates | 32-3114 | S | ON-SITE | N/A |  |  | 1950 | 0% | 1950 | 0 | [8 empty] | 0 |  | 0 | 0
Temp Fencing | 32-3120 | S | ON-SITE | Russell IV | Acre | 17.25 | 2500 | 0% | 2500 | 43125 | [8 empty] | 43125 |  | 0 | 0
Walls Masonry | 32-3201 | S | ON-SITE | Budget | LS | 2 | 131434 | 0% |  | 262868 |  | See Budget File | [6 empty] | 262868 |  | 0 | 0
Walls Pilaster Caps | 32-3202 | S | ON-SITE | Included | LS | 1 | 0 | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Retaining Walls | 32-3204 | S | ON-SITE | Allowance | LS | 2 | 100000 | 0% |  | 200000 |  | See Budget File | [6 empty] | 200000 |  | 0 | 0
Pool Walls | 32-3208 | A | POOL AREA | Allowance | LS | 1 | 11000 | 0% | 11000 | 11000 | [8 empty] | 11000 |  | 0 | 0
Site Furniture Permanent | 32-3343 | A | BUILDING | Allowance | LS | 2 | 7000 | 0% |  | 14000 | [8 empty] | 14000 |  | 0 | 0
Site Landscaping | 32-9001 | S | ON-SITE | Decatur | SF | 363 | 10010.284 | 0% | 10010.284 | 3633733.0769 | [8 empty] | 3787526.8254 |  | 153793.7485 | 0
Site Landscaping Lighting | 32-9001 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Site Landscaping Planter Pots | 32-9433 | S | ON-SITE | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Offsite Asphalt Sawcut and Removal | 32-0506 | S | Offsite | Budget | LS | 1 | 4500 | 0% | 4500 | 4500 |  | See Budget File | [6 empty] | 4500 |  | 0 | 0
Offsite Paving | 32-1216 | S | Offsite | Budget | LS | 1 | 19250 | 0% | 19250 | 19250 |  | See Budget File | [6 empty] | 19250 |  | 0 | 0
Offsite Curbs and Gutters | 32-1613 | S | Offsite | Budget | LS | 1 | 920 | 0% | 920 | 920 |  | See Budget File | [6 empty] | 920 |  | 0 | 0
Offsite Concrete Flatwork | 32-1623 | S | Offsite | Budget | LS | 1 | 25544 | 0% | 25544 | 25544 |  | See Budget File | [6 empty] | 25544 |  | 0 | 0
Utilities | 33 | [9 empty] | 3596130.8846 | [8 empty] | 3596130.8846 | 0 | 0
Temp Power | 33-0501 | A |  | Flamingo | Unit | 363 | 360.1154 | 0% | 360.1154 | 130721.8846 |  | Flamingo actual per unit | [6 empty] | 130721.8846 |  | 0 | 0
Traffic Control, AC Removal and Patch | 33-1001 | A | Offsite | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Water | 33-1001 | S | ON-SITE | Budget | LS | 2 | 927597.5 | 0% |  | 1855195 |  | See Budget File | [6 empty] | 1855195 |  | 0 | 0
Sewer | 33-3001 | S | ON-SITE | Budget | LS | 1 | 546750 | 0% | 546750 | 546750 |  | See Budget File | [6 empty] | 546750 |  | 0 | 0
Storm Drain | 33-4001 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Sub Drains | 33-4116 | A |  | Allowance | LS | 2 | 5000 | 0% |  | 10000 | [8 empty] | 10000 |  | 0 | 0
Electric | 33-7101 | S |  | Budget | LS | 2 | 137500 | 0% |  | 275000 | [8 empty] | 275000 |  | 0 | 0
Secondary Conduit | 33-7102 | A |  | Allowance | LS | 2 | 10000 | 0% |  | 20000 | [8 empty] | 20000 |  | 0 | 0
Bollards | 33-7103 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Cable TV | 33-8201 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Phone | 33-8202 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Off Site Water | 33-1001 | S | Offsite |  | LS | 1 | 499900 | 0% | 499900 | 499900 |  | See Budget File | [6 empty] | 499900 |  | 0 | 0
Off Site Sewer | 33-3001 | S | Offsite |  | LS | 1 | 132664 | 0% | 132664 | 132664 |  | See Budget File | [6 empty] | 132664 |  | 0 | 0
Storm Drain | 33-4001 | S | Offsite | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Off Site Electric | 33-7101 | S | Offsite | N/A |  | 1 | 125900 | 0% | 125900 | 125900 | [8 empty] | 125900 |  | 0 | 0
Transportation | 34 | [9 empty] | 7500 | [8 empty] | 7500 | 0 | 0
Traffic Control | 34-4116 | A | Offsite | Allowance | LS | 1 | 7500 | 0% | 7500 | 7500 | [8 empty] | 7500 |  | 0 | 0
Electrical Power Generation | 48 | [9 empty] | 1019108 | [8 empty] | 1019108 | 0 | 0
Solar PV System | 48-1413 | S |  | Wigwam | Unit | 1 | 977434 | 0% | 977434 | 977434 | [8 empty] | 977434 |  | 0 | 0
Solar PV Conduit | 48-1414 | A |  | Allowance | LS | 2 | 20837 | 0% |  | 41674 | [8 empty] | 41674 |  | 0 | 0
Car Charging Stations | 48-1913 | A |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Field Surveys, Staking | 49 | [9 empty] | 465812.1 | [8 empty] | 465812.1 | 0 | 0
Staking | 49-0601 | S |  | Wigwam | LS | 17.25 | 2914 | 0% | 2914 | 50266.5 | [8 empty] | 50266.5 |  | 0 | 0
Re Staking | 49-0602 | S |  | Wigwam | LS | 17.25 | 1542 | 0% | 1542 | 26599.5 | [8 empty] | 26599.5 |  | 0 | 0
Certs and Verifications | 49-0603 | S |  | Wigwam | LS | 17.25 | 1870 | 0% | 1870 | 32257.5 | [8 empty] | 32257.5 |  | 0 | 0
Slab Testing | 49-0801 | S |  | Wigwam | LS | 17.25 | 6618.4 | 0% | 6618.4 | 114167.4 | [8 empty] | 114167.4 |  | 0 | 0
Grading Testing | 49-0802 | S |  | Wigwam | LS | 17.25 | 4006 | 0% | 4006 | 69103.5 | [8 empty] | 69103.5 |  | 0 | 0
Other Testing | 49-0803 | S |  | Wigwam | LS | 17.25 | 3544.2 | 0% | 3544.2 | 61137.45 | [8 empty] | 61137.45 |  | 0 | 0
Masonry Testing | 49-0807 | S |  | Wigwam | LS | 17.25 | 816 | 0% | 816 | 14076 | [8 empty] | 14076 |  | 0 | 0
Pavement Testing | 49-0808 | S |  | Wigwam | LS | 17.25 | 716.4 | 0% | 716.4 | 12357.9 | [8 empty] | 12357.9 |  | 0 | 0
Third Party Inspections | 49-0950 | S |  | Wigwam | LS | 17.25 | 4976.6 | 0% | 4976.6 | 85846.35 | [8 empty] | 85846.35 |  | 0 | 0
5th Story Factor | 03 | [9 empty] | 1288500 | [8 empty] | 1288500 | 0 | 0
Bridge Over Duct Creek Wash |  |  |  | Budget | LS | 2 | 644250 | 0% | 644250 | 1288500 |  | Olson Concrete Propsoal 7/23/24 Includes $50,000 each bridge for demo of the concrete channel, excavation for the hybrid box invert and backfill. | [6 empty] | 1288500 |  | 0 | 0
|  |  |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
|  |  |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
|  |  |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
|  |  |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
|  |  |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
|  |  |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
|  |  |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Bid Risk | Bid Risk | [9 empty] | 1052926.354 | [8 empty] | 1056002.229 | 0 | 3075.875
Bid Risk | [5 empty] | 2% |  |  |  | 1052926.354 | [8 empty] | 1056002.229 |  | 3075.875 | 0
FFE | FFE Extra | [9 empty] | 3014642.8 | [8 empty] | 3014642.8 | 0 | 0
Golf Carts | 11-1001 | S |  | Alper | LS | 1 | 10000 | 0% | 10000 | 10000 | [8 empty] | 10000 |  | 0 | 0
Convenience Store Equipment | 11-2101 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Pet Wash | 11-2102 | S |  | Alper | LS | 1 | 21000 | 0% | 21000 | 21000 | [8 empty] | 21000 |  | 0 | 0
Office Equipment | 11-2801 | S |  | Russell IV | LS | 1 | 21900 | 0% | 21900 | 21900 | [8 empty] | 21900 |  | 0 | 0
Gym Exercise Equipment | 11-6613 | S |  | Russell IV | LS / Gym | 2 | 95000 | 0% | 95000 | 190000 | [8 empty] | 190000 |  | 0 | 0
Playground / Basketball Hoop | 11-6813 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Maintenance Shop Equipment | 11-8101 | S |  | Russell IV | LS | 1 | 15000 | 0% | 15000 | 15000 | [8 empty] | 15000 |  | 0 | 0
Maintenance Shop Start Up Supplies | 11-8102 | S |  | Russell IV | LS | 1 | 5000 | 0% | 5000 | 5000 | [8 empty] | 5000 |  | 0 | 0
Fixed Asset Misc. | 11-8105 | S |  | N/A |  |  |  | 0% | 0 | 0 | [8 empty] | 0 |  | 0 | 0
Interior Furniture | 12-5000 | S |  | Wigwam | LS / Bldg | 3 | 823200 | 0% | 823200 | 2469600 | [8 empty] | 2469600 |  | 0 | 0
Exterior Furniture | 12-5483 | S |  | Wigwam | LS / Bldg | 3 | 72147.6 | 0% | 72147.6 | 216442.8 | [8 empty] | 216442.8 |  | 0 | 0
Rec Building TV Media Computer | 27-2201 | S |  | Russell IV | LS | 3 | 19500 | 0% |  | 58500 | [8 empty] | 58500 |  | 0 | 0
Rec Building Telephone System | 27-3202 | S |  | Russell IV | LS | 3 | 2000 | 0% |  | 6000 | [8 empty] | 6000 |  | 0 | 0
Maintenance Radios | 27-3243 | S |  | Russell IV | LS | 1 | 1200 | 0% | 1200 | 1200 | [8 empty] | 1200 |  | 0 | 0
Construction Contingency | 55 | [9 empty] | 2860711.5178 | [8 empty] | 2868554.999 | 0 | 7843.4812
Construction Contingency | 55-9800 |  |  |  |  | 5% |  |  |  | 2860711.5178 | [8 empty] | 2868554.999 |  | 7843.4812 | 0
Sub Bonds | 50 | [9 empty] | 684402.1301 | [8 empty] | 686401.4489 | 0 | 1999.3187
Sub Bonds | 50-9950 | B |  |  |  | 1.3% |  |  |  | 684402.1301 | [8 empty] | 686401.4489 |  | 1999.3187 | 0
GL Insurance | 50 | [9 empty] | 386470.36 | [8 empty] | 387480.6373 | 0 | 1010.2773
GL Insurance | 50-0001 |  |  |  | 3.03 per $1,000 | 3.03 |  |  |  | 193235.18 | [8 empty] | 193740.3187 |  | 505.1386 | 0
Misc. | 50-0001 |  |  |  | 5% of GL Ins. | 5% |  |  |  | 9661.759 | [8 empty] | 9687.0159 |  | 25.2569 | 0
Umbrella | 50-0001 |  |  |  | 95% of GL Ins. | 95% |  |  |  | 183573.421 | [8 empty] | 184053.3027 |  | 479.8817 | 0
Contractor Fee | 56 | [9 empty] | 5132836.5731 | [8 empty] | 5146254.3891 | 0 | 13417.8161
Overhead & Contractor Fee | 56 |  |  |  |  | 8% |  |  |  | 5132836.5731 | [8 empty] | 5146254.3891 |  | 13417.8161 | 0
Total Hard Costs | [10 empty] | 69293293.7366 | [8 empty] | 69474434.2533 | 0 | 181140.5167
0
General Requirements | 01 |  |  | 3514986.3
Existing Conditions | 02 |  |  | 16000
Concrete | 03 |  |  | 2594295.6786
Parking Garage | 03-G |  |  | 0
Masonry | 04 |  |  | 174094.2857
Metals | 05 |  |  | 413758.9122
Wood, Plastics, & Composites | 06 |  |  | 8101853.52
Thermal & Moisture Protection | 07 |  |  | 2004765.67
Openings | 08 |  |  | 574050.3
Finishes | 09 |  |  | 5615983.3453
Specialties | 10 |  |  | 373369
Equipment | 11 |  |  | 1160874
Furnishings | 12 |  |  | 2185435.16
Special Construction | 13 |  |  | 1491093.7608
Trash Chute | 13-G |  |  | 0
Conveying Equipment | 14 |  |  | 670462
Fire Suppression | 21 |  |  | 959276.94
Plumbing | 22 |  |  | 3882162
HVAC | 23 |  |  | 3888782.7
Electrical | 26 |  |  | 3679076.58
Communications | 27 |  |  | 198524.46
Electronic Safety & Security | 28 |  |  | 908865
Earthwork | 31 |  |  | 1317559.3375
Exterior Improvements | 32 |  |  | 6058984.0669
Utilities | 33 |  |  | 3596130.8846
Transportation | 34 |  |  | 7500
Electrical Power Generation | 48 |  |  | 1019108
Field Surveys, Staking | 49 |  |  | 465812.1
5th Story Factor |  |  |  | 1288500
Bid Risk |  |  |  | 1052926.354
FFE |  |  |  | 3014642.8
Construction Contingency | 55 |  |  | 2860711.5178
Sub Bonds | 50 |  |  | 684402.1301
GL Insurance | 50 |  |  | 386470.36
Contractor Fee | 56 |  |  | 5132836.5731
Total Hard Costs |  |  |  | 69293293.7366
0
Cost Code
Total
01 - General Requirements | 01 |  |  |  | 3514986.3
02 - Existing Conditions | 02 |  |  |  | 16000
03 - Concrete | 03 |  |  |  | 3882795.6786
04 - Masonry | 04 |  |  |  | 174094.2857
05 - Metals | 05 |  |  |  | 413758.9122
06 - Wood, Plastics, & Composites | 06 |  |  |  | 8101853.52
07 - Thermal & Moisture Protection | 07 |  |  |  | 2004765.67
08 - Openings | 08 |  |  |  | 574050.3
09 - Finishes | 09 |  |  |  | 5615983.3453
10 - Specialties | 10 |  |  |  | 373369
11 - Equipment | 11 |  |  |  | 1160874
12 - Furnishings | 12 |  |  |  | 2185435.16
13 - Special Construction | 13 |  |  |  | 1491093.7608
14 - Conveying Equipment | 14 |  |  |  | 670462
21 - Fire Suppression | 21 |  |  |  | 959276.94
22 - Plumbing | 22 |  |  |  | 3882162
23 - HVAC | 23 |  |  |  | 3888782.7
26 - Electrical | 26 |  |  |  | 3679076.58
27 - Communications | 27 |  |  |  | 198524.46
28 - Electronic Safety & Security | 28 |  |  |  | 908865
31 - Earthwork | 31 |  |  |  | 1317559.3375
32 - Exterior Improvements | 32 |  |  |  | 6058984.0669
33 - Utilities | 33 |  |  |  | 3596130.8846
34 - Transportation | 34 |  |  |  | 7500
48 - Electrical Power Generation | 48 |  |  |  | 1019108
49 - Field Surveys, Staking | 49 |  |  |  | 465812.1
Bid Risk | Bid Risk |  |  |  | 1052926.354
FFE Extra | FFE Extra |  |  |  | 3014642.8
50 - Sub Bonds | 50 |  |  |  | 1070872.4901
55 - Construction Contingency | 55 |  |  |  | 2860711.5178
56 - Contractor Fee | 56 |  |  |  | 5132836.5731
Total |  |  |  |  | 69293293.7366
check |  |  |  |  | 0
FOR ADJUSTMENTS
Appliances, Flooring & Blinds
Flooring - Units | 09-6001 |  |  |  | 517659.42 | 09
Common Wood | 09-6401 |  |  |  | 90552 | 09
Common Vinyl | 09-6517 |  |  |  | 5982 | 09
Hall Flooring | 09-6520 |  |  |  | 164597 | 09
Hall Flooring - Elevators | 09-6520A |  |  |  | 9000 | 09
Common - Plank | 09-6521 |  |  |  | 29926.6973 | 09
Common - VCT | 09-6522 |  |  |  | 59913.308 | 09
Common - Rubber Floor | 09-6566 |  |  |  | 41366 | 09
Common - Carpet | 09-6802 |  |  |  | 23932.4038 | 09
Appliances | 11-3013 |  |  |  | 1160874 | 11
Blinds | 12-2100 |  |  |  | 91773.66 | 12
Total Appliances, Flooring & Blinds |  |  |  |  | 2195576.4891
Site Work
Major Categories
Existing Conditions | 2 |  |  |  | 16000
Earthwork | 31 |  |  |  | 1317559.3375
Exterior Improvements | 32 |  |  |  | 6058984.0669
Utilities | 33 |  |  |  | 3596130.8846
Transportation | 34 |  |  |  | 7500
Electrical Power Generation | 48 |  |  |  | 1019108
Minor Categories
Carports | 13-3401 |  |  |  | 987133.7608
Dumpsters | 06-0111 |  |  |  | 28677
Gazebo |  |  |  |  | 0
Other Site |  |  |  |  | 0
Pools and Spas | 13-1113 |  |  |  | 490000
Offsite Street Signs | 10-1454OFFSITE |  |  |  | 0
Street Lights | 26-5613OFFSITE |  |  |  | 0
Pump House Concrete | 03-3101 |  |  |  | 1995712.03
Total Site Work |  |  |  |  | 15516805.0798
Offsite Asphalt Sawcut and Removal | 32-0506OFFSITE |  |  | already included in 32
Offsite Paving | 32-1216OFFSITE |  |  | already included in 32
Offsite Curbs and Gutters | 32-1613OFFSITE |  |  | already included in 32
Offsite Concrete Flatwork | 32-1623OFFSITE |  |  | already included in 32
Storm Drain | 33-4001OFFSITE |  |  | already included in 33
Off Site Water | 33-1001OFFSITE |  |  | already included in 33
Off Site Sewer | 33-3001OFFSITE |  |  | already included in 33
Off Site Electric | 33-7101OFFSITE |  |  | already included in 33
Traffic Control | 34-4116OFFSITE |  |  | already included in 34
Pump House Concrete | 03-3101
HOME FUNDS INELIGIBLE COSTS
Offsite Work
Offsite Street Signs | Offsite |  |  |  | 973178 |  | 10-1454OFFSITE
Street Lights | [6 empty] | 26-5613OFFSITE
Offsite Asphalt Sawcut and Removal | [6 empty] | 32-0506OFFSITE
Offsite Paving | [6 empty] | 32-1216OFFSITE
Offsite Curbs and Gutters | [6 empty] | 32-1613OFFSITE
Offsite Concrete Flatwork | [6 empty] | 32-1623OFFSITE
Off Site Water | [6 empty] | 33-1001OFFSITE
Off Site Sewer | [6 empty] | 33-3001OFFSITE
Storm Drain | [6 empty] | 33-4001OFFSITE
Off Site Electric | [6 empty] | 33-7101OFFSITE
Traffic Control | [6 empty] | 34-4116OFFSITE
Other Ineligible Costs
Major Categories
Parking Garage | 03-G |  |  |  | 0
Minor Categories
Pump House Concrete | 03-3101 |  |  |  | 1995712.03
Pool Area Shower Concrete | 03-3105 |  |  |  | 7500
Cabana Concrete | 03-3107 |  |  |  | 0
Pool Equipment Foundation | 03-3108 |  |  |  | 0
Deck Concrete | 03-5001 |  |  |  | 78723.84
Masonry Veneer Pool Area | 04-4305 |  |  |  | 0
Pool Equipment Shower Stone | 04-4306 |  |  |  | 0
Cabana Iron | 05-7004 |  |  |  | 0
Pool Equipment Gate | 05-7005 |  |  |  | 3900
Cabana Framing | 06-1109 |  |  |  | 0
BBQ Framing | 06-1110 |  |  |  | 11240
Fireplace Framing | 06-1111 |  |  |  | 0
Trellis | 06-1114 |  |  |  | 0
BBQ Trim | 06-2006 |  |  |  | 4124
Cabana Roofing | 07-3002 |  |  |  | 6700
Pump House Roofing | 07-3002 |  |  |  | 6700
Pool Equipment Windows | 08-5303 |  |  |  | 0
Pool Glass Walls | 08-8001 |  |  |  | 0
Stucco - Pump House | 09-2423 |  |  |  | 756138.3762
Stucco - Cabana | 09-2423 |  |  |  | 756138.3762
Stucco - Pool Wall | 09-2423 |  |  |  | 756138.3762
Unit Carport Signs | 10-1401 |  |  |  | 56265
Fire Places - Pool Area | 10-3200 |  |  |  | 0
BBQ Units | 10-3355 |  |  |  | 13440
BBQ Top | 12-3609 |  |  |  | 42600
Pools and Spas | 13-1113 |  |  |  | 490000
Carports | 13-3401 |  |  |  | 987133.7608
Pool Equipment Cover | 13-3402 |  |  |  | 13960
Pool and Spa Lifts | 14-4101 |  |  |  | 26000
Pool Area | 22-1003 |  |  |  | 49224
Pool Equipment | 22-1007 |  |  |  | 12000
Carports Electrical | 26-1001 |  |  |  | 3124335.18
Carport Fixtures | 26-5001 |  |  |  | 226388.4
Cabana Electrical | 26-1001 |  |  |  | 3124335.18
Cabana Fixtures | 26-5004 |  |  |  | 0
Pool Lighting Electrical | 26-1004 |  |  |  | 34000
Pool Lighting Fixtures | 26-5603 |  |  |  | 22000
Pool Equipment Electrical | 26-1007 |  |  |  | 4000
Pump House Electrical | 26-1001 |  |  |  | 3124335.18
Pump House Fixtures | 26-5001 |  |  |  | 226388.4
Pool Decks | 32-1402 |  |  |  | 117000
Pool Hardscape | 32-1626 |  |  |  | 19320
Pool Fence | 32-3106 |  |  |  | 45900
Pool Walls | 32-3208 |  |  |  | 11000
Pet Wash | 11-2102 |  |  |  | 21000
Office Equipment | 11-2801 |  |  |  | 21900
Gym Exercise Equipment | 11-6613 |  |  |  | 190000
Playground / Basketball Hoop | 11-6813 |  |  |  | 0
Rec Building TV Media Computer | 27-2201 |  |  |  | 61200
Rec Building Telephone System | 27-3202 |  |  |  | 6000

## Sheet2
| Robindale Senior Apartments | [8 empty] | Hard Costs Budget
Las Vegas, NV
|  | Hard Cost Item | Cost Code | ROM Total |  | "% Factor" Adj. | $ | $ / GSF | $ / U
01 |  | 01 - General Requirements | 01 | 3514986.3 | 6% | 3435049.9795 | 3435049.9795 | 11.0401 | 9462.9476
02-49 |  | 02 - Existing Conditions | 02 | 16000 |  |  | 16000 | 0.051423 | 44.0771
02-49 |  | 03 - Concrete | 03 | 3882795.6786 |  |  | 3882795.6786 | 12.4792 | 10696.4068
02-49 |  | 04 - Masonry | 04 | 174094.2857 |  |  | 174094.2857 | 0.55953 | 479.5986
02-49 |  | 05 - Metals | 05 | 413758.9122 |  |  | 413758.9122 | 1.3298 | 1139.8317
02-49 |  | 06 - Wood, Plastics, & Composites | 06 | 8101853.52 |  |  | 8101853.52 | 26.0391 | 22319.1557
02-49 |  | 07 - Thermal & Moisture Protection | 07 | 2004765.67 |  |  | 2004765.67 | 6.4432 | 5522.7704
02-49 |  | 08 - Openings | 08 | 574050.3 |  |  | 574050.3 | 1.845 | 1581.4058
02-49 |  | 09 - Finishes | 09 | 5615983.3453 |  |  | 5615983.3453 | 18.0496 | 15471.0285
02-49 |  | 10 - Specialties | 10 | 373369 |  |  | 373369 | 1.2 | 1028.5647
02-49 |  | 11 - Equipment | 11 | 1160874 |  |  | 1160874 | 3.731 | 3198
02-49 |  | 12 - Furnishings | 12 | 2185435.16 |  |  | 2185435.16 | 7.0239 | 6020.4825
02-49 |  | 13 - Special Construction | 13 | 1491093.7608 |  |  | 1491093.7608 | 4.7923 | 4107.6963
02-49 |  | 14 - Conveying Equipment | 14 | 670462 |  |  | 670462 | 2.1548 | 1847.0028
02-49 |  | 21 - Fire Suppression | 21 | 959276.94 |  |  | 959276.94 | 3.0831 | 2642.6362
02-49 |  | 22 - Plumbing | 22 | 3882162 |  |  | 3882162 | 12.4771 | 10694.6612
02-49 |  | 23 - HVAC | 23 | 3888782.7 |  |  | 3888782.7 | 12.4984 | 10712.9
02-49 |  | 26 - Electrical | 26 | 3679076.58 |  |  | 3679076.58 | 11.8244 | 10135.1972
02-49 |  | 27 - Communications | 27 | 198524.46 |  |  | 198524.46 | 0.63805 | 546.8993
02-49 |  | 28 - Electronic Safety & Security | 28 | 908865 |  |  | 908865 | 2.9211 | 2503.7603
02-49 |  | 31 - Earthwork | 31 | 1317559.3375 |  |  | 1317559.3375 | 4.2346 | 3629.64
02-49 |  | 32 - Exterior Improvements | 32 | 6058984.0669 |  |  | 6058984.0669 | 19.4734 | 16691.4162
02-49 |  | 33 - Utilities | 33 | 3596130.8846 |  |  | 3596130.8846 | 11.5578 | 9906.6967
02-49 |  | 34 - Transportation | 34 | 7500 |  |  | 7500 | 0.024105 | 20.6612
02-49 |  | 48 - Electrical Power Generation | 48 | 1019108 |  |  | 1019108 | 3.2754 | 2807.4601
02-49 |  | 49 - Field Surveys, Staking | 49 | 465812.1 |  |  | 465812.1 | 1.4971 | 1283.2289
Bid Risk |  | Bid Risk | Bid Risk | 1052926.354 | 0% | 0 | 0 | 0 | 0
FFE Extra |  | FFE Extra | FFE Extra | 3014642.8 |  |  | 3014642.8 | 9.689 | 8304.8011
50 |  | 50 - Sub Bonds / Contractor Insurance | 50 | 1070872.4901 |  | 519000 | 1589872.4901 | 5.1098 | 4379.814
55 |  | 55 - Construction Contingency | 55 | 2860711.5178 | 5% | 3263297.4805 | 3263297.4805 | 10.4881 | 8989.8002
56 |  | 56 - Contractor Fee | 56 | 5132836.5731 | 8% | 4580066.6393 | 4580066.6393 | 14.7202 | 12617.2635
|  | Total Hard Costs |  | 69293293.7366 |  |  | 68529247.0911 | 220.2507 | 188785.8047

## Sheet3
Differences Onsite Water
Hard Dig | 125000
Fire Hydrants | 83450
6" Domestic | 192908.16 | 8" line
10" Fire Line | 17036
Fittings & Valves | 157505
Total | 575899.16